PREFACE

The annual plant turnaround for the year 2013 was taken form 9 th APRIL 2013, for carrying out preventive maintenance of static and rotary equipments, statutory IBR inspection, Preventive maintenance of Electrical  and instrument systems, Civil related jobs and for attending jobs which were pending for shut down.

After ensuring the availability of all the required material for shutdown and awarding contracts for various shut down jobs. It was decided to stop the plants as per the following.

Plant			            Stopped on 				Started on

DAP Train A 			: 10th APRIL 2013			20th APRIL 2013

DAP Train B 			: 07th APRIL 2013			20th APRIL 2013

DAP Train C 			: 10th APRIL 2013			10th MAY    2013

PAP 				: 09th APRIL 2013			21st APRIL 2013

SAP Train 1			: 09th APRIL 2013		            24th APRIL 2013

Steam Shutdown 		: 11th APRIL 2013 		            18th APRIL 2013

The Turnaround was carried out smoothly due to meticulous planning of all activities like planning of man power, material and other resources. Due to exemplary efforts put in by all personnel at all levels, turnaround jobs could be completed in the scheduled period.

Safety was one of the major aspects, which was given top most priority during the execution of various jobs. Necessary training for safe working in the plant was given to the manpower employed by all contractors and strict vigilance was kept by fire and safety section during execution of shut down works. All The jobs were carried out considering all safety aspects and the use of safety equipments was ensured during execution of jobs.

The shutdown report contains plant wise and section wise details of jobs carried out.

INDEX

PREFACE						:	2

INDEX							:	3

DAP TRAIN A						:	4	  -   16

DAP TRAIN B						:	17	  -   20

DAP TRAIN C						:	21      -   32

PHOSPHORIC ACID PLANT 			:	33	  -   65

SULPHURIC ACID PLANT			:	66	  -   80

BAGGING PLANT					:	81

ENERGY CENTER					:	82	  -   112

AFBC BOILER						:       113	  -   134

UTILITY AND OFFSITES			:       135	  -   139

INSTRUMENTATION				:       140	  -   158

ELECTRICAL						:       159	  -   182

DAP PLANT

ANNUAL SHUTDOWN REPORT-2012-13

DAP TRAIN – A

PRIMARY ELEVATOR:

Primary elevator top hood to bottom hood cleaned with water by process deptt and handed over to mechanical deptt. for maint. work

- All old bucket replaced by new bucket

- Total old  chain replaced by new chain (Make:-M/S REXNORD,USA)

- Damaged top casing replaced by new fabricated casing and damaged guide angle replaced by new fabricated guide angles.

New bucket and chain assembly by torque wrench Old sprocket of elevator Chain with bucket fitting

Secondary Elevator:

- In Secondary elevator boot door, inspection door opened and elevator buckets and chain checked. Also drive and non drive bearing checked and lubricated.

Product Screen Elevator:

- Head & tail sprocket replaced with new sprockets (Make: M/S REXNORD USA).

- Damage bucket replaced and guide angle checked and replaced.

- CI block inspected and damaged block replaced by new one.

- DE & NDE bearing replaced with new bearing, DE Plummer block also replaced.

Product Elevator:

- All inspection boot door opened and All buckets inspection done and damage buckets replaced by new one also provided bolt in missing case.

Granulator:

Granulator base strengthening done by welding supporting structure and base of support roller and thrust roller structure and casting of supporting structure. This decreases vibration level in granulator.

- Torque Tube coupling replaced new one.

- Feed end side one thrust roller replaced by new thrust roller.

- Six number rubber panel replaced in granulator.

- In Forced lubrication system (FLS system) all filter, strainer, connecting pipe line opened and cleaned then boxed up.

- Granulator retainer ring refitted on position and welding done.

Fines Conveyor:

- Belt replaced with 1800mm MRF conveyor belt with hot vulcanizing.

- Drive chain replaced with new one and chain tightened.

- Drive chain replaced with new one and chain tightened

- Head pulley DE & NDE bearing and bend pulley 03 bearings replaced and rest

- Bearing inspected and lubricated.

- All skirt rubber replaced.

DDC Conveyor:

- Conveyor belt replaced with endless belt.

- Head pulley DE and NDE bearing with Plummer block replaced by new bearing and plummer block.

- Gear box to motor Coupling replaced with new coupling and Pulley to gear box coupling.

RM Conveyor :

- Tail Pulley Tr. B side bearing replaced and other side bearing checked and lubrication done.

- Pulley to Gear box coupling replaced and alignment done.

Product Conveyor (70A):

- Conveyor belt replaced by new belt with hot vulcanizing.

- Motor replaced with new motor to G/B coupling.

- Head pulley NDE and tail pulley both bearings replaced and rest bearings inspection and lubrication done.

Combustion Chamber:

- Damage inner shell plates replaced and refractory lining done.

- Chamber gun removed and overhauled then fitted.

Chain Mills:

- 14 A1 and A2 rotor replaced and new bearings and Plummer block.

- All chain mill rotor balancing and alignment with motor done.

- 14A2 and 13 A2 chain mill door replaced.

Oversize & product Screen :

- All connecting rod bolts tightening done.

- Missing and damage top rubber cover replaced/provided.

Winch

- Gear Box inspection and input shaft replacement done.

- Motor replaced two times.

- Drum type coupling arranged and fitted.

- Electromagnetic break modified and replaced.

Dust & Fume Fan

- Top and bottom impeller side casing damage portion replaced with new 6 mm plates and 100% rubber lining done.

- Damper side top casing 100% rubber lining and bottom side bulging/damage portion rubber lining done.

- Suction side bellow replaced with new metallic bellow.

Dryer Exhaust Fan

- Impeller side top casing removed & 100% rubber lining done.

- Impeller cleaned by blast cleaning method.

- Suction and discharge bellow replaced with new metallic bellow.

TG Common duct and tank

- All welding joints checked with DPT and damage area welding done

- 06 nos. of spray nozzles replaced.

- Damage nozzle pipe replaced and 01 pond water inlet piping with elbow replaced.

- Process water inlet pipe (2”) provided with new valve.

Dust & Fume Scrubber

- Separator shell revamping done approximately 1.5 mtrs in full circumference SS316 plate provided at MSRL area and damage welding area grinded and rewelded.

- Rubber lining done above SS316L plate where rubber chipping was done for SS           lining job.

- Separator nozzle piping replaced with new piping.

- Venturi nozzles (2”) replaced and 02 nos. of new valve provided.

- Down comer line (20”) tee piece modified for de‐choking from bottom.

Dryer Scrubber

- One MS patch provided and damage shell area and proper rubber lining done.

- Separator nozzle piping replaced with new piping.

- Venturi nozzles (2”) replaced.

- Down comer pipe (20”) opened for de‐choking and refitted.

Pre Neutrilizer Duct

- Approx. 8 mtrs damage duct replaced with new duct and joint near spray tower repaired properly.

- 02 nos of new manhole fabricated, fitted and welded with proper locking arrangement.

Agitators

- W/L agitator shaft lifted and properly locked with check nut and coupling done.

- Primary tank agitator motor replaced

Steam Air Heater

- Manhole opened for inside tubes cleaning and boxed up.

Combustion Air Fan

- Casing opened for cleaning and boxed up.

- Damper made free.

Quench Air Fan

- Casing opened for cleaning and boxed up.

- Damper made free.

- Both side bearings greasing done.

FO Area

- All 04 nos of strainers cleaned thoroughly.

Pipe line Jobs

- 60 series suction pipeline modification done.

- W/L to PN line up gradation done by SS316L 4” pipe.

- Strong acid to PN line up gradation done by SS 316L 6” pipe and provision made for line extension to primary tank.

- MP steam battery limit valve replaced.

- Ammonia battery limit 2nd isolation valve replaced.

- 22 pump steam flushing valve opened overhauled and boxed up.

- Ammonia vaporizer 1st and 2nd drain valve replaced.

- Ammonia line valve 1st battery limit valve gland and both gaskets replaced.

- LP steam battery limit valve gland replaced.

- 02 nos. of MP steam valve and 01 NRV overhauling done at PN floor.

- 12” 300# ammonia line valve gasket replaced at PN floor for arresting leakage.

TG Vaporizer

- All line made dummy for tube bundle replacement job.

- Water box removed and repairing done.

Preventive maintenance / Inspection

- All equipment bearing inspected and lubricated.

- All tanks man hole opened and cleaned.

- All gear box/fluid coupling  oil level checked and top up done

- All motor removed from base and handed over to electrical deptt for overhauling and after overhauling motor positioned on respective place.

DAP TRAIN - B

PRIMARY ELEVATOR:

Primary elevator top hood to bottom hood cleaned with water by process deptt and handed over to mechanical dept. for replacement work of chain, head sprocket ,tail sprocket, bucket and higher size gear box (KCH 560).

- Old head sprocket replaced by new head sprocket (Make-Rexnord) with new bearing and plummer block.

- Old gear box (KCH-450 Ratio:80:1) Replaced by new  higher size gear box  (KCH-560 Ratio:80:1)

- All old bucket replaced by new modified bucket and all bucket fitted in chain by tightening with pneumatic spanner.

- Old chain replaced by Rexnord make new chain (R4037) in primary elevator.

- All Cast iron block and guide angle replaced by new block and guide angle.

- Gear box base frame fabricated and modified.

- Primary elevator head sprocket bearing 01 no (23156k) replacement done

New bucket and chain assembly by torque wrench Old sprocket of elevatorChain with bucket fitting

New head and tail sprocket replaced in primary elevatorNewkch 560 gear box replaced in primary elevator

SECONDARY  ELEVATOR:

Secondary elevator top hood to bottom hood cleaned with water by process deptt and handed over to mechanical deptt. for replacement work of chain head sprocket ,tail sprocket, bucket .

- Old tail sprocket replaced by new tail sprocket (Make-Rexnord) with new one.

- All old bucket replaced by new modified bucket and all bucket refitted in chain by tightening with pneumatic spanner.

- Old chains replaced by Rexnord make new chain (R4037) in primary elevator.

- All Cast iron block and guide angle replaced by new block and guide angle.

Chain mill

TWO New modified chain mill (with anti-vibration pad, sliding arrangement for rotor replacement, Casing with liner, Chain with hammer, lumps breaker) changed in Train-B. Another 2 no chain mill already replaced in DEC-12.

- Discharge chute of chain mill newly fabricated and fitted on position.

- In let chute modification done as per new chain mill.

Old chain mill at ground floor  New chain mill for replacement

Granulator:

- Granulator’s both feed end and discharge end tire grinding done by 3 mm &4 mm radials respectively.

- Both end support roller adjusting done according to tire grinding.

- Torque tube coupling hub of pinion side replacement done.

- Feed end and discharge end thrust roller replacement done.

- Complete ammonia sparger replaced by newly fabricated Ammonia sparger.

- 06 no’s rubber panel replacement inside granulator.

- Ammonia line inlet stub-end newly fabricated.

- Granulator lube oil sump’s cleaning done and new oil filled.

- Granulator structure strengthening done.

Dryer:

- Dryer pinion replaced  by new  bearing and plummer blocks

- Higher side torque tube(BZGR- 75000 ) coupling replacement IN PLACE .Both torque tube and gear box to motor alignment done.

- Dryer lube oil system overhauling done, filters cleaning done.

Fines conveyor:

- Fines conveyor deck plate with skirt board fabrication job done, new skirt rubber replaced

- Conveyor belt replaced by new one.

- 60 no’s carrying idlers, 10 no’s return idlers and 01 no’s self cleaning idler replaced.

- Drive chain replaced by new chain.

- Gratings around 15 meters both side of fines conveyor fitted instead of chequor plate.

- Fines conveyor bend pulley and take up pulley both side bearing (22228EK) with sleeve replacement done.

RM Conveyor:

- R.M Conveyor head pulley’s both side bearing, new drive coupling replaced

- New gear box replaced with new motor.

Dryer Discharge conveyor:

- Old gear box replaced by new gear box with new overhauled motor.

- Old belt replaced by new belt.

- Head pulley both side bearing and Plummer block (22222EK) replacement done.

TANK:

- PN tank man hole opened, inspected and cleaned inside and boxed up.

- Primary tank man hole opened, inspected and cleaned inside and boxed up.

- Pre tank man hole opened, inspected and cleaned inside and boxed up.

Pipe line and valve:

- Both venturies ring header modification done.

- 6” 150# valves replacement done in 91 and 92 pump discharge line.

- T.G shell inside patch work done around 260 meters.

- 02 nozzles of T.G scrubber new fitted.

- Pinch area nozzle’s main header pipe modification done

- All safety valves in ammonia line opened and pressure testing done and again fitted in position. 01 No 2” N.R.V opened for repairing and again fitted in position with modified condensate drain line in steam line behind granulator.

- 02 No’s valve replacement done in steam line behind combustion chamber.

- 91,92 and wash liquor pumps suction line modification done.

FAN:

- Dust fan discharge duct up graded to SS 316 L.

- Both suction and discharge bellow replacement done.

- Bottom casing SS316L liner fitted.

- Top casing metal work done, rubber lining done, new cone of ss 316 l fitted.

- Damper side casing metal work done, rubber lining done.

- Dryer exhaust fan, Fumes fan, and Dust fans impeller cleaning done.

- Dust fan casing (top portion) rubber lining done and fitted in position.

- Quench air fan’s both side bearing replacement done, fan and motor pulley new replaced, cleaning done, alignment done, belts fitted.

- Quench air fan damper opened from position, overhauling done and made free. Again fitted in position.

Vaporizer:

- Ammonia vaporizer dome opened and hydro testing done at 20 kg/cm2 and again boxed up. Only 01 no tube found leakage.

- Ammonia pre heater replacement done.

Preventive and lubrication:

- All pump removed from casing and cleaned impeller burnt oil drained and pump boxed up.

- All bearing cover opened and clearance checked then greasing done.

- All gear box and fluid coupling oil level checked and oil level maintained.

DAP TRAIN - C

GRANULATOR

> Both tyre replaced and aligned

> Girth gear aligned

>One support roller replaced (Uphill B side)

> All support roller leveled and center distance maintained

> Girth gear root gap adjusted

> base strengthening done

>Motor replaced

> Fluid coupling oil seal replaced

> Ammonia sparger replaced

> 3 nos of damaged Rubber pannel replaced

> Lube oil system cleaned and new oil filled in sump

> Fluid coupling oil replaced

DRYER

> Gear Box replaced

> Motor replaced

> Fluid coupling replaced

>torque tube replaced

> One support roller (downhill PAP side) replaced

> FLS system replaced

> All bearings checked and greased

> Inlet duct replaced

> Dryer Grizly bar repaired

DDC

>Head pulley with new bearings replaced

>gear box and motor base modified

> Tail pulley bearing replaced

> Gear box oil replaced

> Head pulley coupling replaced

> Gear box output shaft coupling replaced

> Skirt rubber replaced

PRIMARY ELEVATOR

> Head sprocket assembly with new brgs replaced

> Gear Box replaced with KCH 560

> Fluid coupling replaced

> Motor base modified

> complete chain link and bucket checked, damaged bucket replaced

> 4 nos of damaged guide angle replaced

> CI block with guide channel replaced

>Damaged boot doors, both side doors, both back side door replaced

OVER SIZE SCREEN

> 9 nos of damaged screen replaced

CHAIN MILL

> All chain mill replaced

> 13 no chain Mill's inlet duct replaced

> All chain mill's discharge duct modified and rubber fixed on two side

> Vibration isolator provided in discharge duct of all chain mill

FINES CONVEYOR

> Belt replaced

> Skirt board replaced

> Skirt rubber replaced

> All carrying idlers and return idlers replaced

> Five nos of damaged carrying toughing idlers replaced

> Two Nos of carrying self aligning frame repaired

> All brgs checked and greased

> Both bend pulley's counter wt. pulley's bearing replaced

> Gear box oil replaced

SECONDARY ELEVATOR

> Head sprocket assembly with new bearing s replaced

> Gear Box replaced

> Fluid coupling replaced

> complete chain link and bucket checked, damaged bucket replaced

> 8 nos of damaged guide angle replaced

> CI block with guide channel replaced

> Damaged boot doors, both side doors, both back side door replaced

VIBRO FEEDER

> All link checked and strengthened

> Three sides skirt plate replaced

PRODUCT SCREEN ELEVATOR

> Complete chain link and bucket checked, damaged bucket replaced

> Both bearings checked and greased

> Gear box oil replaced

> Fluid coupling's oil replaced

> Boot door enlarged

PRODUCT SCREEN

> 11 nos of damaged screen replaced

> All screens inlet chute replaced

PRODUCT ELEVATOR

>Complete chain link and bucket checked, damaged bucket replaced

> Both bearings checked and greased

> Gear box oil replaced

> Fluid coupling's oil replaced

> Boot door replaced

70 Conveyor

> Belt replaced

> All damaged carrying idler and return idler replaced

> All brgs checked and greased. One tail pulley's brg replaced

> Gear coupling checked and greased

> Gear box oil replaced

> Counter weight leveled and modified

> Skirt rubber replaced

POTASH ELEVATOR

>complete chain link and bucket checked, damaged bucket replaced

> Both bearings checked and greased

> Gear box oil replaced

> Fluid coupling's oil replaced

> Tail pulley centered and leveled

POTASH TRANSFER CONVEYOR

> Belt replaced

> Head Pulley shifted towards Potash elevator

> All damaged idlers replaced

RM CONVEYOR

>Belt replaced

> All damaged carrying and return idler replaced

> Two nos of power return idler provided

> All four brgs checked and greased

> Grid coupling replaced with gear coupling

> Gear box oil replaced

POTASH CROSS CONVEYOR

> All brgs checked and greased

> damaged idler replaced

POTASH WEIGH FEEDER

> Weigh feeder replaced with new one

DUST AND FUMES FAN

> Impeller cleaned by sand blasting and balancing done

> both bearings replaced with new sleeve and plummer block.

> Euro flex coupling replaced

> Motor removed and after overhauling it is refitted

> Casing rubber lining removed and new rubber lining done

DRYER EXHAUST FAN

> Impeller cleaned by sand blasting and balancing done

> both bearings replaced with new sleeve and plummer block.

> Motor removed and after overhauling it is refitted

> Casing rubber lining removed and new rubber lining done

QUENCH AIR FAN

> Impeller cleaned

> Both bearings checked and greased

> Motor replaced and alignment done

COMBUSTION AIR FAN

> Impeller cleaned

COMUSTION CHAMBER

> Chamber replaced with new fabricated

> Resister with new burner replaced

> New brick lining done

PN AGITATOR

> New PN agitator installed (supplied by Delkor )

TG SHELL

> TG SS lining checked and cracked portion repaired

DUST AND FUMES SEPARATER

> SS 316L lining done in damaged and corroded portion of shell

PRE SCRUBBER SEPARATOR

> Damaged rubber lining removed and new rubber lining done

PRE SCRUBBER PUMPS (40 SERIES)

> Suction line modified

> Pump Replaced

> Motor replaced

TG SCRUBBER PUMPS (60 SERIES PUMPS)

> Suction line modified

> Pump Replaced

> Motor replaced

PHOSPHORIC ACID PLANT

Annual Turn Around – 2013

Annual shut down activity of Phosphoric acid plant in the year 2013 was started on 9th April and completed on 21st April. During this period many activities related to process and equipment overhauling, cleaning jobs at different points were undertaken. The area wise major cleaning activities are as per followings.

- Reactor.

- Slurry Surge Tank

- Fume scrubber and Pre scrubber

- Cold well, Cooling Tower Deck, Cooling Tower Mist eliminator and basin.

- Vac. Cooler Seal legs, Vac. Cooler Pre condenser seal tanks etc.

- Belt Filter

- Ball Mill & Ball Mill area

- New Pump tank

- Vessel & Line Cleaning

- RPSS area

- Gypsum Tank

- Modification Jobs

Reactor cleaning: Reactor emptying out process was started on 09.04.2013 at 08.00hrs. and completed in B-shift. Reactor was then put into Chemical washing for about 36 hrs. and the wash liquor was drained. During the chemical washing of reactor system reactor temperature was maintained at around 55oc by putting hot pond water through filter and adding steam directly to reactor. On 11.04.2013 all Reactor Man ways connected to reactor annular, adjustment tank, FFT, VCST were opened and agitator cover plates were started to be removed.

Bottom area of each and every annular section agitator except at the bottom of agitator 112 was found almost with nominal deposit. At the bottom of agitator 112, a deposition of height of 0.5 m was observed. Depositions could be seen at some corners of VCFT, VCST etc. Deposition was also noticed at the bottom of 130 agitator. Lot of hard scale was observed on shafts of annular section agitators and wall of reactor. All the bottom deposits have been cleaned. Majority of wall deposit have been cleaned & agitator shafts were cleaned completely.

Damage was observed over the ceiling of the reactor roof near the Mixing Tee zone. Hence damaged areas of the roof were repaired with grunting by civil dept. Ceiling of roof in all the compartments was also repaired & coated with Arfurathene except in VCFT where no coating was done. A pit of approx. depth 0.5 m & 3.5 m diameter was found to have formed at the bottom of agitator 120 where repairing was done in the previous year. Above the new concrete layer Carbon brick lining has been done. A small pit at the bottom of Agitator 150 in adjustment tank was found to have formed which was also repaired in the previous year has been repaired again.

Strengthening of corroded blades of agitators 111, 113, 150, 160 171 & 142 was carried out. Agitator 130 along with its Gear Box has been replaced. Damage was observed in outer pipe of all Mixing Tees, out of those it was replaced for 409 & 410. Damaged & thinned portion of the fumes duct which connects over reactor was repaired. Remaining portion of the old fumes duct has been replaced. The removed agitator cover plates were also cleaned.

Build up on all reactor agitator shafts             Scaling on reactor inside wall

Agitator while build up cleaning                    Reactor floor during cleaning

Reactor floor after cleaning                       Damaged portion of Reactor ceiling

Damaged Sulphuric acid Mixing Tee   Pit formed at the bottom of Agitator 130

SST cleaning: Problem of falling of agitator blades used to occur in previous years. That is why in this year also there was a requirement of strengthening of brackets of blades.  Deposition of Material was found at the bottom (Approx quantity was 100 MT). Same was cleaned to make access to the agitator.  All the blades of agitator were renewed, Gear Box was also checked & motor was overhauled. Damaged baffle plates were strengthened. Also patch up strengthening was carried out over thinned portions of the tank wall.

Deposition is being cleaned inside SST       Damaged & thinned baffle and wall

Fume scrubber cleaning: Deposited silica at Fumes scrubber inside floor, Pre scrubber inside and its outlet U-duct were thoroughly cleaned. No damage in rubber linings was observed. Cleaning was done in Fumes scrubber sump to remove deposited silica.

Fumes scrubber inside after cleaning         Cleaning of Fumes scrubber sump

Cold well, basin, strainers & Mist Eliminator cleaning: Cold well was emptied out and found to be deposited with silica and foreign materials (mist eliminators, wooden pieces, V-bars etc.). Pay loader and Excavator were utilized for cleaning the cold well basin. Strainers & Mist eliminators of all the cells were cleaned thoroughly. Damaged brick linings of cell walls of compartment no. 2, 7 & basin wall were repaired. Cooling Tower top deck was also thoroughly cleaned.

Cold well cell after cleaning                    Cold well basin before cleaning

Mist eliminators during cleaning           Cleaning of deposition is in progress

Vac. Cooler seal legs and Pre condenser seal tanks cleaning: Hard depositions over outside & inside surfaces of the seal legs of all the Vac. Coolers were thoroughly cleaned. Depositions in Pre condenser seal tanks (both old and new) were also cleaned.

Belt Filter cleaning: In the filter manifolds where ever scaling was observed, it was cleaned. Along with those Vac. Boxes, Filtrate hoses, Sluice headers, Cloth wash headers, Distributors, Receivers etc. were also cleaned.

Ball Mill & Ball Mill area cleaning: Grinding media balls of Ball Mill–A was unloaded to facilitate liner replacement job. After segregation, balls have been kept ready for recharging. MST of all Ball Mills were cleaned.  Apprx. 100 MT of spillage rock was removed from Ball Mill area. Feed chute & feed spouts of Ball Mill – B & D have been replaced. Product hopper of Ball Mill – B has been replaced.

New pump tank cleaning: New pump tank manhole was opened during the annual shut down and found to be containing gypsum depositions. Tank was cleaned thoroughly.

Vessel & Line Cleaning: Cloth wash tank was cleaned. Filtrate seal tanks of all the B/Filters were cleaned. All the control valves in Filtration area were cleaned. All the suction & discharge lines of Acid transfer pumps, T-412 overflow line etc. were cleaned thoroughly.

RPSS area cleaning:  Entire conveyor area spillage was cleaned. Belts of Conveyor 104, 106A & Weigh feeder – B were replaced.

Gypsum Tank: Deposition inside Gypsum Tank has been cleaned and base of its agitator has been strengthened.

Modifications: Following modifications have been carried out during shut down :

- Utility water header has been connected to Process water header leading to Belt filter condensers;

this will reduce Process water consumption in the plant.

- One additional manhole at the inlet duct of Fumes scrubber & one more manhole in the duct

leading to VCFT have been provided to facilitate better cleaning and inspection of the duct.

- Temporary lines made of PVC hose in Defoamer dosing pump area have been made permanent

and simplified. Also unused lines nearby have been removed.

- Various opening at reactor top have been encircled with concrete parapet wall on safety ground.

- Conveyor 104 discharge chute has been modified to reduce spillage.

REACTOR SECTION

- REVAMPING OF  FRP  FUMES DUCT IN REACTOR

------Replacement / Repairing job in FRP Duct: -------

- The damaged part of the duct was dismantled.

- New duct erected & jointed with super vinyl ester resin material.

- End cover manholes of the old duct opened for inspection & cleaning purposes.

- The subject duct was thoroughly cleaned by water washing.

- The leaking points in the subject duct was repaired / relined by super vinyl ester resin   material.

- The entire job completed on date: 24.04.2013 & handed over for operation.

Removal of Old / damaged Duct by Sany Crane

New FRP Duct of 1500 NB Dia. jointed at ground by super vinyl ester resin material & ready for erection.

Removal of old / damaged FRP Duct

Removal of damaged FRP fumes Duct

Dismantling of damaged FRP Fumes duct by EOT crane.

Damaged FRP Fumes Duct

Old FRP duct of Fume scrubber replaced with new FRP duct

NEW DUCT

------Provision of Manhole in adjustment tank fumes duct for online cleaning -------

- 500 mm OD size Piece was cut from the existing FRP fumes duct.

- Fabricated FRP manhole of size: Size: 500 mm OD nozzle with flange, Nozzle Height: 300 mm, Wall Thk. Of nozzle: 12 mm, Flange Thk. 20 mm was fitted by super vinyl ester resin material.

- Dummy flange (Thk. 20 mm) was fitted with fasteners.

New Manhole provision in fumes duct for online cleaning purpose

------Provision of Manhole in Fume Scrubber Inlet Duct for online cleaning -----

- 1 mtr. (L) x 600 mm (W) size Piece was cut from the existing FRP fume scrubber duct.

- Fabricated FRP manhole of size: 1 mtr. (L) x 600 mm (W), Nozzle with flange (Sqr. Type), Nozzle Height: 250 mm, wall thk. Of nozzle: 12 mm, flange thk. : 20 mm was fitted by super vinyl ester resin material.

- Dummy flange (Thk. 20 mm) was fitted with fasteners.

New Manhole Provision in Fume Scrubber Inlet Duct for Online Cleaning.

NEW MANHOLE PROVISION IN FUMES INLET DUCT

‘U’ duct removal & Prescrubber nozzle cleaning: ---------------------

- The ‘U’ Duct was removed from its position.

- The duct was cleaned by water washing on the ground & boxed up at its position.

- Necessary scaffolding made in the prescrubber.

- All nozzles were dismantled, cleaned & fitted.

‘U’ – Duct of Prescrubber boxed up after cleaning.

- REVAMPING OF REACTOR AGITATORS :

Agitator Tag No : 20-05.114

- Complete assembly of reactor agitator was removed from the position followed by gear box, motor, base frame.

- Gear box was overhauled.

- Oil pump was replaced with a new pump due to problems (Noise in bearing & flow problem) in the old pump.

- Old agitator was dismantled due to damages on blade. (Erosion on blades).

- The blades were repaired, strengthened by patch welding to suit the size.

- Complete unit of agitator assembly was erected followed by leveling, alignment & commissioning activities.

Agitator Tag No : 20-05.130

- Complete assembly of reactor agitator was removed from the position followed by gear box, motor, base frame

- Gear box was overhauled.

- Oil pump was replaced with a new pump due to problems (Noise in bearing & flow problem) in the old pump.

- Old agitator was dismantled due to damages on the shaft & blade.

- New (Repaired) agitator was fitted.

- Complete unit of agitator assembly was erected followed by leveling, alignment & commissioning activities.

Damages at various points on agitator shaft (Agitator Tag No. : 20 – 05 .130

Repairing / Strengthening of Agitator blades on position

Agitator Tag No : 20-05.150, 20-05.160, 20-05.111, 20-05.113, 20-05.115, 20-05.171, 20-05.172

- The blades of reactor agitator tag no. :20-05.150, 20-05.160, 20-05.111, 20-05.113, 20-05.115, 20-05.171 & 20-05.172 were repaired / strengthened by patch welding (25 mm thk. SS 904L Plates were patch welded according to damage portion of the agitator blades).

Strengthening done by SS 904L Plate of 25 mm thk. By patch welding in agitator tag no. : 20-05.171

Strengthening done by SS 904L Plate of 25 mm thk. By patch welding in agitator tag no. : 20-05.115

Strengthening done by SS 904L Plate of 25 mm thk. By patch welding in agitator tag no. : 20-05.160

Strengthening done by SS 904L Plate of 25 mm thk. By patch welding in agitator tag no. : 20-05.172

- MIXING TEE REPLACEMENT :

Mixing Tee Tag No : 20-05.409/410/415/416

- All Mixing Tee (total: 04nos.)  Were taken out for Inspection.

- PVDF Internals from two nos. of mixing tee i.e 20-37.409 & 20-37.416 found damaged, which was replaced with new one.

- Rest mixing tee assemblies were cleaned & re installed in position.

Mixing Tees taken out from position for inspection & cleaning purpose.

- OVERHAULING OF KNIFE EDGE GATE VALVE OF VACUUM COOLER CIRCULATION PUMP :

Knife Edge Gate Valve of Pump Tag No : 20-01.110, 20-01.112 & 20-01.113

- Three nos. of knife edge gate valves of size: 1050 NB were completely dismantled followed by inspection, bonnet removal, water washing, and liner & sheet removal.

- The damaged liner & sheet were removed.

- New liner & sheet fitted in the subject valves.

- The complete assemblies were boxed up.

- OVERHAULING OF VACUUM COOLER CIRCULATION PUMP :

Vacuum Cooler Circulation Pump Tag No : 20.01.113

- The suction spool piece, reducer & bellow of size: 1050 NB in the subject pump was removed.

- Damage Impeller & casing liner was removed.

- Bearing housing assembly was removed followed by removal of pulley, shaft & sleeve.

- New impeller along with complete bearing housing assembly fitted.

- New casing liner & stuffing box were fitted.

- New gland packing provided.

- Driven pulley was installed & aligned.

- New power transmission ‘V’ belts (Belt No. : SPC 7100) provided & safety guard fitted.

- The subject pump was handed over to operation.

Vacuum Cooler Circulation Pump (Tag No. : 20-01.113) in dismantled condition.

Impeller Removed

- OVERHAULING OF PRECONDENSOR  PUMP :

Precondenser Pump Tag No : 20.01.182

- The pump was completely dismantled.

- Damaged shaft, sleeve, lantern ring were replaced by providing new one.

- New Rubber bush in Pin Bush coupling of the subject pump provided.

- New casing gasket provided.

- Alignment & coupling done.

- The subject pump was handed over to operation.

Rotor assembly of Precondenser pump (Tag No. : 20-01.182 taken out for inspection & repairing purpose.

REPLACEMENT OF OLD FUME SCRUBBER FAN ASSEMBLY:

Fume Scrubber Tag No : 20.03.110

- The old fume scrubber was completely removed from the position due to high vibration report because of severe deposition of silica on the fan impellers.

- The spare fan assembly erected on position, pulley mounted, aligned.

- The power transmission belts (V – Belt No. : SPC: 6700) provided & Safety guard fitted.

- The complete Fan assembly was handed over for operation.

MISSCELLANEOUS JOB:

- Electric motor of agitator tag no. : 20-05.120, 20-05.150 & 20-05.160 were removed for overhauling purpose as per electrical requirement, reinstalled after overhauling & alignment done.

- Cover plate, rubber seal belt & safety cover mesh provided in the agitators as cited above.

- All agitators top cover plate along with safety cover mesh were removed for proper ventilation inside reactor & as per operation requirement.

- The damaged cover plates of agitator tag no. : 20-05.111, 20-05.171, 20-05.172 & 20-05.116 were replaced with new / repaired cover plates.

- Rest of the cover plates were reinstalled followed by rubber seal belt & safety cover mesh.

- All gear box filter element, oil level & quality of oil inspected, replaced with new as per observation.

- Manholes of fume scrubber chamber, stack, prescrubber, precondenser, intercondensor, PCST (Precondenser Seal Tank), CST (Condenser Seal Tank) was opened, inspected, cleaned & boxed up.

- Connecting fumes duct from belt filter to fume scrubber tank was isolated by putting a dummy of size: 2000 mm dia. Of SS 316L material plate of thickness 08 mm.

Fumes duct from Belt Filter to fume scrubber was isolated by putting a dummy .

Dummy (08 mm thk. SS 316L Plate) Inside

Isolation done

RPSS SECTION

REPLACEMENT OF CONVEYORS:

Conveyor Tag No : 20-29.104

- The old / damaged conveyor belt of length: 475 mtr. Of width: 1200 mm was replaced.

- New belt shifted to position.

- All carrying idlers & return idlers were checked & made free for smooth pulling of the belt.

- Drive side & non drive side i.e. snub pulley, bend pulley, take up pulley & tail pulley were checked & made free for smooth pulling of the belt.

- The electric motor (110 Kw) was replaced.

- Rubber lagging in non drive pulley i.e. in bend pulley was carried out.

- The belt was positioned and jointed by hot vulcanizing process.

Conveyor Tag No : 20-29.106 ‘A’

- The old / damaged conveyor belt of length: 42 mtr. & width: 1200 mm was replaced.

- New belt shifted to position.

- All carrying idlers & return idlers were checked & made free for smooth pulling of the belt.

- Drive side & non drive side i.e. snub pulley, bend pulley, take up pulley & tail pulley were checked & made free for smooth pulling of the belt.

- The belt was positioned and jointed by hot vulcanizing process.

MODIFICATION IN CONVEYOR RECEIVING CHUTE:

Conveyor Tag No. : 20-29.105

- Both side skirt plate, covering deck plate & bottom part of the receiving chute was completely dismantled.

- Bottom part receiving chute newly fabricated by reducing the opening size from 900 mm (width) to 550 mm (width), enable for minimizing of spillage of rock.

- Both side skirt plate & covering deck plate repaired.

- New rubber spillage block fitted.

- Complete assembly fitted in position.

- Complete damaged platform in receiving chute bottom floor (105 –Tail Pulley area) were replaced and new chq. Plate provided followed by strengthening from back side.

IDLER REPLACENT IN CONVEYORS:

Conveyor Tag No : 20-29.103 ‘A’ / ‘B’, 20-29.104, 20-29.105, 20-29.106 ‘A’ & ‘B’

- All the idlers i.e. carrying, return & impact from all conveyors i.e. 20-29.103 ‘A’ & ‘B’, 20-29.104,20-29. 105, 20-29.106 ‘A’ & ‘B’ were thoroughly checked & damaged idlers were replaced with new one.

OVERHAULING OF MANNUAL SLIDE GATES IN ROCK SILO:

Rock Silo Tag No : 20-15.010 ‘A’ / ‘B’ / ‘C’

- The entire manual slide gates of conveyor 20-29.103 ‘A’, 20-29.103 ‘B’ & 20-29.103 ‘C’ were thoroughly checked.  The damaged  bearing housings replaced , overhauling in the gates were carried out  followed by replacement of damaged sliding plates, greasing & diesel washing .idlers i.e. carrying, return & impact from all conveyors i.e. 20-29.103 ‘A’ & ‘B’, 20-29.104, 20-29.105, 20-29.106 ‘A’ & ‘B’

BALL MILL SECTION

BALL MILL ‘A’ TAG NO. :  20-27.010 ‘A’

RUBBER LINER & LIFTER BAR REPLACEMENT JOB IN BALL MILL ‘A’:

- The damaged liners & lifter bar from the Feed end, discharge end & shell were removed.

- The new liners & lifter bar assy. mounted in the subject areas as cited above for trublefree operation of the shell / mill.

REPLACEMENT OF FEED SPOUTE & FEED CHUTE:

- The damaged feed spoute & feed chute were replaced with new fabricated one.

PREVENTIVE MAINTENANCE

- Preventive maintenance in main pinion bearing, main trunion bearing (Inlet & out let) , geared coupling, main gear box, main motor, MST Agitator, screen Feed Pump ,weigh feeder gear box & weigh feeder carried out followed by greasing, oil replacement, all base bolt tightening, MST blade repairing , idler replacement .

BALL MILL ‘B’ TAG NO. :   20-27.010 ‘B’

REPLACEMENT OF FEED SPOUTE & FEED CHUTE:

- The damaged feed spoute & feed chute were replaced with new fabricated one.

- The roof structure & columns of MST, feed chute structures were replaced with new beam & gratings.

REPLACEMENT OF TROMMEL SCREEN, PRODUCT HOPPER (LOWER PORTION

& UPPER PORTION)

- Damaged trammel screen repaired with new wire mesh.

- Lower portion & upper portion of the product hopper replaced with new fabricated one.

PREVENTIVE MAINTENANCE

- Preventive maintenance in main pinion bearing, main trunion bearing (Inlet & out let) , geared coupling, main gear box, main motor, MST Agitator, screen Feed Pump ,weigh feeder gear box & weigh feeder carried out followed by greasing, oil replacement, all base bolt tightening, MST blade repairing , idler replacement .

BALL MILL ‘C’ TAG NO. :  20-27.010 ‘C’

SHELL LINER

Ball Mill shell liner inspection done and bolt tightened.

PREVENTIVE MAINTENANCE

Preventive maintenance in main pinion bearing, main trunion bearing (Inlet & out let) , geared coupling, main gear box, main motor, MST Agitator, screen Feed Pump ,weigh feeder gear box & weigh feeder carried out followed by greasing, oil replacement, all base bolt tightening, MST blade repairing , idler replacement .

BALL MILL ‘D’ TAG NO. : 20-27.010 ‘D’

SHELL & LINER

Ball Mill shell liner inspection done and bolt tightened.

REPLACEMENT OF FEED SPOUTE & FEED CHUTE :

- The damaged feed spoute & feed chute were replaced with new fabricated one.

- The roof structure & columns of MST, feed chute structures replaced with new beam & gratings.

REPLACEMENT OF MAIN PINION BEARIKNG

- The old pinion assembly was removed.

- Repaired pinion with new bearing assembly installed.

- All alignment work such as main pinion to girth gear, main pinion to gear box & main gear box to main motor done.

PREVENTIVE MAINTENANCE

Preventive maintenance in main pinion bearing, main trunion bearing (Inlet & out let) , geared coupling, main gear box, main motor, MST Agitator, screen Feed Pump ,weigh feeder gear box & weigh feeder carried out followed by greasing, oil replacement, all base bolt tightening, MST blade repairing , idler replacement .

SST AGITATOR BLADE REPLACEMENT, SST TANK REPAIRING & SST GEAR BOX OVERHAULING:

SST AGITATOR TAG NO. :   20-05.30

SLURRY SURGE TANK TAG NO. :   20-09.30

- Manhole opened for inspection.

- Necessary scaffolding made for replacement of damaged agitator blade.

- Old / Damaged blades were removed.

- Agitator bracket strengthening done.

- New blade fitted on agitator shaft.

- The damaged portion on the tank was repaired by patch working.

- Damaged baffle plates & ribs replaced with new one.

- All base bolts & coupling bolts checked & tightened.

- Old oil replaced.

- Motor was handed over to electrical department for overhauling purpose.

- Motor boxed up followed by leveling & alignment.

Scaffolding is under Progress for replacement of SST Agitator Blades in Ball Mill Section.

BELT FILTER SECTION

BELT FILTER TAG NO. :  20-22.210 ‘A’ / ‘G’

REPLACEMENT OF SEAL STRIP IN BELT FILTER - ‘E’

- Lowered down the vacuum box.

- Wear belt removed.

- Removed of seal strip by opening of bolts.

- Cleaning the vacuum box and the place where seal strip stands.

- Fixing of buta seal on the vacuum box.

- Installation of new seal strip carried out followed by leveling, installation of wear belt & seal water connection.

- Took up the vacuum box into the position & the gap adjusted between the mother belt & wear belt .

REPLACEMENT OF CURBING IN BELT FILTER - ‘C’

- Filter cloth was removed.

- Cake wash & 4th wash distribution box, flap dam stand were removed.

- Old curbing removed by cutting & surface preparation were made for fixing of new curbing.

- New curbing fixed by SC – 4000 adhesive.

- Cake wash & 4th wash distribution box, flap dam stand were installed in position .

- Filter cloth was installed & cloth tracking done.

Replacement of Curbing in Belt Filter – ‘C’ is going on.

MODIFICATION OF BLOWER BASE IN FILTER BELT - ‘E’

- Electric motor was removed from position.

- Impeller & shaft assy. Of the blower was removed.

- Casing removed.

- Stool assy. Removed.

- Old / corroded blower base removed by chipping through hilty.

- New / fabricated base positioned & leveled.

- Grouting done.

- Stool, casing, motor were re positioned followed by leveling & alignment.

MICELLANEOUS:

- All hoses like cloudy, product, return, 3rd wash & 4th wash in B/F – A, B, C, D, E & G were removed for cleaning & boxed up.

- All manifolds like product, return, 3rd wash & 4th wash in B/F – A, B, C, D, E & G were removed for cleaning & boxed up.

- Damaged filter dam rubbers replaced in B/F –A, D &E.

- The damaged cloudy pot receiver was taken out from its position; the damaged portion was repaired by super vinyl ester resin & boxed up.

FILTRATION SECTION

REVAMPING OF GYPSUM SLURRY TANK PLATFORM :

GYPSUM SLURRY TANK TAG NO. :  20-09.290

- Old chq. Plates were replaced with new gratings.

- Cleaning & painting of structure were carried out.

- Strengthening & extension of existing structure done.

REPLACEMENT OF SHEET & LINERS OF KNIFE EDGE GATE VALVES IN FILTER FEED PUMP SUCTION LINE.

FILTER FEED PUMP TAG NO. :  20-01.131 / 142

- Defective valves were dismantled for overhauling.

- Inspection was carried out on each part of the valves.

- Damaged sheet & Liners were replaced.

- Suction nozzles were cleaned & subject valves were boxed up.

OVERHAULING OF GYPSUM PUMP

GYPSUM SLURRY PUMP TAG  NO. :  20-01.292

Suction & discharge line were opened.

- Casing, liner, impeller, stuffing box & bearing cylinder were removed.

- New bearing cylinder assy. Fitted.

- Pump was boxed up followed by fitting of suction & discharge line.

- Alignment of Pump to gear box, Gear box to fluid coupling & Fluid coupling to motor done.

Overhauling Of Gypsum Pump Tag No : 20-01.292 is going on

MICELLANEOUS:

- Preventive maintenance of Filter Feed Pump, Product Acid Pump, Return acid Pump, 3rd wash, 4th wash & cake wash pumps were carried out.

- Inspections of the pump internals were carried out by complete dismantling of the pump.

- Damaged / wear out internals were replaced & boxed up.

- Lubricants checked.

- Alignment & coupling done.

- Gear box of Filtrate seal tank agitator & Gypsum slurry tank agitator were overhauled by replacing the damaged input gear with matching pinion assy.

CONCENTRATION SECTION

REVAMPING OF FLASH CHAMBER & BAROMETRIC CONDENSER IN EVAPORATOR – ‘C’

FLASH CHAMBER TAG NO. : 20 -16.310 ‘C’

- Shell & top dome repaired by patch work & rubber lined.

- Shell was completely brick lined.

BAROMETRIC CONDENSER TAG NO.: 20-11.320 ‘C’

- Bottom dish repaired by patch work & rubber lined.

- Bottom dish was brick lined.

REVAMPING OF FLOURINE SCRUBBER OF EVAPORATOR – ‘C’

FLOURINE SCRUBBER TAG NO. : 20 -10.310 ‘C’

- Shell & top / bottom cone of fluorine scrubber repaired by patch work & rubber lined.

- Shell was completely brick lined.

- Fluorine scrubber taken into line by connecting with interconnecting duct.

REPLACEMENT OF HEAT EXCHANGER IN EVAPORATOR ‘A’

HEAT  EXCHANGER TAG NO. : 20 -11.310 ‘C’

- Choked graphite heat exchanger of evaporator ‘A’ replaced with new one.

HYDROJET CLEANING:

- Tubes in the Heat exchanger ‘B’, ‘C’, ‘D’, ‘E’, ‘F’ & ‘G’ cleaned by hydro jet .

REVAMPING OF ENTRAINMENT SEPARATOR IN EVAPORATOR - ‘G’

ENTRAINMENT SEPARATOR TAG NO. : 20 -23.310 ‘G’

- Top cone of entrainment separator repaired by patch work & rubber lining done.

- Entrainment separator outlet duct to barometric condenser repaired by patch work & rubber lining done.

REVAMPING OF COOLING TOWER:

COOLING TOWER TAG NO. : 20 -18.610

- Complete revamping of cooling tower shell (Shell No. : 02, 05 & 06) like replacement of damaged louver sheets, louver diagonal, V-Bars, SS Grids etc. carried out .

- Damaged water Distribution deck of cooling tower shell (Shell No. : 6, 7 & 8) replaced.

- Damaged water distribution valve of cooling tower shell (Shell No. : 5, 7 & 8) replaced.

Damaged fifth (05) no. shell of PAP- cooling tower

REVAMPING OF COLD WELL PUMPS:

COLD WELL PUMP TAG NO. : 20 -01.621-27

- Complete overhauling of P-621, 622, 624,625 & 626 done followed by bearing replacement, gland replacement, alignment & coupling.

- Discharge NRV of P-621 replaced with new / repaired one.

Overhauling of cold well pump (pump tag no. : 20 -01.622) is going on.

REVAMPING OF HOT WELL PUMPS:

HOT WELL PUMP TAG NO. : 20 -01.611-17

- Complete overhauling of P-615 & 617 done followed by bearing replacement, gland replacement, alignment & coupling.

- Discharge NRV of P-611, P -612, P-616 were overhauled & reinstalled in position.

- Discharge valve ( 750 NB – Butterfly Valve) of P-612 was over hauled & reinstalled in position

ACID STORAGE AREA

- P-494 & P-495 discharge headers dismantled, dechoked & boxed up.

- P-495,P-497,P-494,P-496 & P-498 suction header dismantled, dechoked & boxed up .

- Tank 411 & 412 outlet over flow lines dismantled, dechoked & boxed up.

- Weak acid distribution box down comer line to tank – 411 & 412 opened, cleaned & boxed up.

Sulphuric Acid Plant 1

Preface:

Plant was stopped for replacement of mal functioning boiler bypass damper.

Along with this job, part of FAT shell brick lining repair job was taken up below the dome. During breaking of the damaged bricks, it was observed that there is slippage in the self supporting dome grid of the tower.

On 22.11.2012, it was decided to dismantle the dome and shell brick lining up to dome and apply new brick lining and dome.

Turbo Blower:

- All 3 actuators and MSSV dismantled, overhauled and calibration done.

- All the vanes of Blower suction IGV removed, bearings replaced and fitted back.

- Oil sump drained, cleaned and oil charged back after cleaning.

- Both the oil coolers cleaned by hydro jet cleaning.

- Bearings of the Blower were opened, cleaned and boxed up after checking the clearances.

  - Bearing clearance on DE side is 0.40

  - Bearing Clearance on NDE side is 0.45

  - Axial Thrust is 0.44

Sulphur Furnace:

- Brick lining including castable portion of the furnace neck is completely removed.

- Shell plates up to 50% diameter and 4 Mtrs. Long cut and removed. New plates fabricated, erected and welded.

- New brick lining with insulating and fire resistant castable was done on the complete furnace neck portion.

- After completion, the brick lining was dried out with a 72 hours cycle at 550 Deg.C

Brick lining repairing activities in sulphur Furnace

- Secondary Air dampers were overhauled.

- Both the fabric expansion joints were replaced with new fabric.

Boiler, Economizer and Super Heaters:

- Boiler bypass damper replaced with new damper as it is completely damaged.

- Complete cleaning of boiler, economizer and super heaters done, hydro test carried out in presence of AD (F&B)

- Thickness survey of all the tubes of Boiler, economizer and super heaters done.

- Boiler outlet and converter inlet dampers serviced.

- Various valves were replaced.

- All 5 safety valves were overhauled, tested and fitted back in position.

- Start up vent damper was made free and a new pneumatic actuator fixed for operation.

- Boiler sight glasses were replaced with new sight glasses.

Converter & Heat Exchanger and gas ducts:

- Catalyst from all the beds removed, screened and charged back into the beds.

- 11 nos. of Catalyst holding trays of 3rd bed were replaced with new trays of SS 304.

- Damaged central drum portion of the 3rd bed repaired by means of patch welding around the duct.

- Aluminizing of the replaced portion done.

- Old damaged liner plate was removed and new SS 316L liner plate was provided inside the cold heat exchanger.

- FAT to chimney damper was replaced with new pneumatic operated damper.

- Economizer outlet damper was made free.

Acid Towers:

- Complete brick lining of FAT up to self supporting dome was dismantled.

Dismantling activities of FAT Tower

Cleaning of FAT tower 			 application of Rhepanol ORG lining

Activities of brick lining work and dome grid installation

- Activities of FAT tower - dome grid installation, cross partition rings saddles installation

- Thickness survey of the FAT shell was carried out up to dome height.

- Damaged shell plates and the plates with thickness less than 10 mm were replaced with new plates of 14 mm Thk.

- 120 mm long portion of gas inlet nozzle was replaced with new plate.

- New RF pads were provided around the gas inlet nozzle.

- Both the acid outlet nozzles were replaced with new nozzles and flanges.

- New brick lining on the bottom dish end, shell and dome of FAT was done after applying Rhepanol sheeting.

- All the candle filters (130 nos.) of IAT were replaced with new high mist elimination capacity candle filters for commissioning of HRS.

- IAT bottom dish end cracks on the edges were grinded and welded from outside.

- FAT outlet duct was repaired from inside by welding.

- IAT outlet duct was repaired from inside by welding.

- Platforms of FAT and IAT top domes were replaced with new structure and SS 304 hand railings.

- Damaged irrigation pipes of FAT were replaced as per availability of material.

- Damaged FAT dilution pipe (PTFE lined Pipe) was replaced with new pipe.

Acid Pump Tanks:

- Brick lining of 1440 side acid inlet nozzle was broken.

- Nozzle was repaired by providing new plates and new brick lining was done.

- Roofs of all the 3 pump tanks were repaired by providing new plates.

- Platforms were provided on all 3 pump tanks for safe working.

- Both the IAT acid coolers were opened and hydro jet cleaning was carried out.

- 8 PHEs of FAT & DT were interchanged.

- Product PHE was back flushed.

Acid Piping:

- Acid piping from the discharge of all the pumps to their respective coolers / PHEs was upgraded from Cast Iron to SS 316L.

- 1451 side U Seal of final absorption tower was upgraded from Cast Iron to ZeCor-Z.

- 1420, 1421 and 1450 U Seals of drying tower and final absorption tower were upgraded from Cast Iron to SS 316L.

- Fumes extraction piping was dismantled, cleaned and refitted.

Rotary Equipment:

- Overhauling of both the sulphur burners was carried out.

- Both the primary air fans were overhauled.

- Both the bleed air fans of self cleaning air filters were replaced with new fan assemblies.

- All 6 acid circulation pumps and one product acid pump were overhauled.

Common Steam Shutdown

- HP deaerator steam inlet line bypass valve repaired.

- SAP Train 1 turbine back pressure line isolation valve‘s equalization line leakage attended.

- SAP Train 1 export line spectacle blind steam leakage attended.

- SAP Train 1 and 2 export line root valve overhauling done.

- SAP Train1 Pre heating line first and second valve overhauling done.

- LPS2 isolation valve both upstream and downstream flange leakage on deaerator platform arrested by replacement of gaskets.

- CWP inlet steam isolation valve is replaced with new valve in SAP 1.

- CWP export steam isolation valve gland leakage arrested.

- LPS-2 steam control valve isolation valves (1504) gland leakage arrested.

- Turbine exhaust steam isolation valve gland leakage arrested in both the plants

| BAGGING PLANT |  |  |  |
| --- | --- | --- | --- |
| Sl NO | EQUIPMENT/AREA | JOBS COMPLETED | REMARKS |
| 1 | 108 Conveyor Drive | Replacement of Gear Box model BTN 200 with new Motor and drive allignment |  |
| 2 | 102 Conveyor Drive | Replacement of Gear Box model BTN 200 with new Motor and drive allignment |  |
| 3 | 130 Conveyor Drive | Motor & Gear Box model HTN 320 replacement and drive allignment |  |
| 4 | 112,113,&104 Conv | Conveyror belt 1000 mm width replacement with hot vulcanising | Total 400 Meter length |
| 5 | 202 & 132 A Conv | Conveyror belt 1400 mm width replacement with hot vulcanising | Total 150 Meter length |
| 6 | 101 Conv | New Motor & Oil seals of Gear box Replacement |  |
| 7 | Bearings | All the bearings of Conveyors checking/Replacement/Lubrication done | 04 nos 22222 EK, 02 nos 22220 EK, 04 nos 22215 EK, 02 nos 22220 EK bearings replaced |
| 8 | Slat Convs | All the bearings of slat conv checked/replaced as per requirement |  |
| 9 | Portable Convs | 02 nos of belt replaced i.e. 650 mm width belt |  |
| 10 | GEAR BOX | All Gear box Oil Replacement |  |

ENERGY CENTRE

ANNUAL TURNAROUND REPORT

TG  COOLING TOWER

A).TG CIRCULATING WATER PUMP

Make			:MATHER & PLATT

Type of pump		:30”/30” ALE-T DV

Capacity			:7750 m3/hr

Net head			:37.86 M

Drive			:Electric Motor

REPLACEMENT OF ROTOR ASSEMBLY IN TG CT PUMP A&C AND   INSPECTION OF PUMPS

PROBLEM

- During shut down in the year 2011 it was observed that the impeller vanes of Pumps with CS impeller were not in good condition, erosion/corrosion were found on the impeller vanes.

- Cooling water pump ‘S’ was running with high vibration.

PLANNING

- It was planned to replace rotor assembly with new one (SS impeller).

- It was decided to do the balancing of the rotor.

ACTIVITY INVOLVED

1.De-coupled with Motor.2 Removal of Top casing and Rotor assembly.3 Cleaning of inside top and bottom casing.3 Cleaning of parting plane.4 Inspection of white metal lined journal bearings and Ball bearing.5 Replacement of Rotor assembly.6 Boxed-up with proper gasket.

EXECUTION OF JOB

This job was executed by M/S S.V.Industries (W.O No-252004121601) and alignment of the Pumps were done by IFFCO Technicians in the supervision of IFFCO  Engineer.

SPARES USED

- Rotor assembly complete in all respect (Two no.) for Pump A & C

- Deep groove ball Bearing(6315) three nos.(one for each pump).

OLD DAMAGED CS IMPELLER

INSPECTION OF OLD DAMAGED IMPELLER

INSTALLATION OF NEW(SS) IMPELLER

FITTING OF IMPELLER WORK UNDER PROGRESS

Alignment readings are given below

Pump “A”.

Radial			    Axial1			Axial2

(-0.08)                                          (-0.06)                                   (-0.08)

(0.00)----R------- (-0.04)          (0.0) -----A1------ (-0.05)    (-0.01) -----A2------ (0.0)

(0.03)                                              (0.01)                                             (0.02)

Pump “C”.

Radial			    Axial1			Axial2

(-0.03)                                        (+0.05)                                 (0.05)

(0.00)----R-------(-0.05)     (0.0)-----A1------(0.1)            (0.06)-----A2------(0.0)

(-0.08)                                           (0.02)                                             (0.02)

Pump “S”.

Radial			    Axial1			Axial2

(0.04)                                        (-0.02)                                  (-0.03)

(0.00)----R-------(0.04)       (0.0)-----A1------(0.1)            (0.1)-----A2------(0.0)

(0.01)                                            (0.04)                                           (0.05)

B) TG COOLING TOWER (MAKE: PAHARPUR COOLING TOWER LTD.) SUMP & BASIN                          CLEANING

Type		:Induced draft

No of cell		:10 (Ten)

Model no		:6615-4.0-10

Capacity		:33000m3/hr.

HW temp.		:43 deg.centigrade

CW temp.		:35 deg.centigrade

WB temp.		:31 deg.centigrade

PROBLEM

Due to ingress of fly ash and dust from neighboring plants, cooling water parameter such as Turbidity, Phosphate was running high. To maintain these parameters frequent blow down was required.

PLANNING

It was planned to cleaning of sludge, debris which was expected to settle down from the sump & basin.

ACTION TAKEN

W.O no-6600/252004131822 placed on M/S Jyoti Enterprises to carryout the cleaning job of sump & basin.

EXECUTION OF JOB

This job was executed by Jyoti enterprises in the supervision of IFFCO Technician.

CLEANING ACTIVITIES UNDER PROGRESS

CLEANING ACTIVITIES UNDER PROGRESS

AFTER CLEANING

C) TG COOLING WATER PUMP’S SUCTION STRAINER REPLACEMENT

PROBLEM

During shut down it was observed that suction strainer of cooling water pumps are in damaged condition.

PLANNING

It was planned to replace the strainers. Installed strainers were made up of MS rod. It was decided to replace the corroded strainer with GI graiting and SS support.

ACTION TAKEN

Material were issued from the store.

EXECUTION OF JOB

This job was executed departmentally in the supervision of IFFCO Engineer.

CORRODED SUCTION STRAINER OF COOLING WATER PUMP

SUCTION STRAINER FABRICATED FROM GI GRAITING AND SS SUPPORT

D) OVERHAULING OF DISTRIBUTION  VALVES FOR TG CT

PROBLEM

During revamping of cooling tower it was observed that cells are not isolating completely.

PLANNING & ACTION TAKEN

It was planned to replace the damaged internal of the valves. Purchase order were placed on M/s Paharpur cooling towers ltd (OEM) for valves  internals(eight set).

SPARES USED

(1) Valves stem with guide key (2) Valve Disc (3) washer (4) Castle nut (5) Gasket (6) Seal (7) Grease nipple (8) Locking bar (9) Cotter pin (10) ‘O’ ring (11) Lock plate (12) Operating bar with key and set screw.

EXECUTION OF JOB

This job was executed by M/S S.V.Industries (W.O No-252004121601) and alignment of the Pumps were done by IFFCO Technicians in the supervision of IFFCO  Engineer.

OVERHAULING OF VALVE UNDER PROGRESS

BOXING UP OF THE VALVE UNDER PROGRESS

TG BUILDING

A). TG CONDENSER

Type			:Cell & Tube type Surface Condenser

No of tubes		:7000

M.O.C. of tubes		:SS 304

CONDENSOR TUBES CLEANING

PROBLEM

In the running plant it was observed that vacuum and temp. in the condenser were rising.

PLANNING

It was anticipated that ash and dust ingresses in the cooling tower from neighboring plants was deposited in the tubes. It was planned to clean the ash and dust which was expected to deposit in the tubes.

ACTION TAKEN

W.O no-6600/252004130356 was placed on M/S. 5 S Engineering company to carryout the condenser cleaning job.

EXECUTION OF JOB

This job was executed by M/S. 5 S Engineering company in the supervision of IFFCO Engineer

BEFORE CLEANING OF CONDENSER TUBES

BEFORE CLEANING OF CONDENSER TUBES

CLEANING OF CONDENSER TUBES UNDER PROGRESS

CLEANING OF CONDENSER TUBES UNDER PROGRESS

INSPECTION OF CLEANING JOB

C) STEAM SYSTEM

1) INSTALLATION OF 600 MM NB ISOLATION VALVE IN HP STEAM HEADER

PROBLEM

Previously no isolation valve was in the scheme of HP steam header at TG end for the maintenance of steam line up to SAP and maintenance of three no safety valves.

PLANNING

It was planned to install isolation valve in HP steam header and procurement action taken for 600 NB valve.

Valve Type	: Pr.Seal type Gate valve

Size		: 24”(600 mm NB)

Rating		: 1500 #

Valve body	: WC9

Make		: KSB

ACTIVITIES INVOLVED

1) Cutting of pipe according to valve size. 2) Edge preparation for pipe. 3) Fitt-up of valve. 4) Root welding. 5) Radiography. 6) Final welding. 7) UT test. 8) Stress relieving of the joints.

EXECUTION OF JOB

This job was executed by M/S Royal Enterprises (BPA no-252004132595) in the supervision of IFFCO Engineer.

EDGE PREPARATION OF THE LINE

PREPARED EDGE OF THE LINE

WELDING OF THE JOINT   &  INSTALLED 600 MM NB VALVE

2) HP STEAM HEADER (UT TEST OF JOINTS)

Seven joints of HP steam header were inspected and UT test carried out.

ACTIVITIES INVOLVED

  - Removal of insulation. 2) Cleaning of joints by buffing.

CLEANING OF JOINT BY BUFFING

UT TEST UNDER PROGRESS

INSPECTION OF THE JOINT

3) INSTALLATION OF VENT CONTROL VALVE IN HP STEAM  HEADER

Process steam distribution is done by Energy Centre.Source of steam is waste heat recovery boiler from SAP plant(350 TPH) and from AFBC Boiler(220 TPH).Due to plant load variation in power as well as process steam,some time HP steam header pr. getting disturbed.To maintain HP steam header pr.,it was suggested to provide vent control valve in HP steam header.

MATERIAL USED

Control Valve

Valve Type	: PCV(Pr.Control valve)

Size		: 6”(150 mm NB)

Rating		: 1500 #

Tag No	: PV 1501

Make		: KOSO Fluid Control

End		: Butt Weld

Isolation Valve

Valve Type	: Gate

Size		: 4”(600 mm NB)

Rating		: 1500 #

MOC		: WC9

Make		: KSB

End		: Butt Weld

Qty		: 02 Nos.

Pipe(SMLS)

Size		:100 mm NB as per ASTM A 335 Gr. P11 IBR approved

Sch		:160

End		:Butt Weld

MAJOR ACTIVITIES

- Cutting in 600 mm NB,140 Sch,P11 steam header for weldolet fit-up (600 NB x 100 NB).

- Weldolet fitt-up and Root welding of the joint.

- 4” pipe & elbow fit-up with weldolet and Root welding of the joint.

- Gate Valve (4”,1500 #,Make-KSB) fit-up with spool piece and Root welding of the joint.

- Pr. Control valve fit-up and Root welding of the joint.

- Radiography of all the joints done.

- Post welding, stress relieving done for all the joints.

EXECUTION OF JOB

This job was executed by M/S Royal Enterprises (BPA no-252004132595) in the supervision of IFFCO Engineer.

EDGE PREPARATION FOR WELDOLET FITTING

INSTALLATION OF PR.CONTROL VALVE

4) OVERHAULING OF DEFERENT SIZES SAFETY VALVES AND GATE VALVE

| Sl.no. | Valve no/ location | Size/Rating | Job Carried out | Spare(if any) |
| --- | --- | --- | --- | --- |
| 1. | 4530.101/TG-I GSC | 200 NB/800# | V/V dismantalled,cleaning,lapping,blue matching done then boxed-up and installed in its position |  |
| 2. | 4530.101/TG-II GSC | 200 NB/800# | V/V dismantalled,cleaning,lapping,blue matching done then boxed-up and installed in its position |  |
| 3. | HP to LP isolation valve | 200 NB/1500# | V/V dismantalled,cleaning,lapping,blue matching done then boxed-up and installed in its position | 1.Pr.Seal ring,2.Gland packing. |
| 4. | HP to MP isolation valve | 200 NB/1500# | V/V dismantalled,cleaning,lapping,blue matching done then boxed-up and installed in its position | 1.Pr.Seal ring,2.Gland packing. |
| 5. | MSSV(main steam stop valve for TG-I) | 300 NB/1500# | V/V dismantalled,cleaning,lapping,blue matching done then boxed-up and installed in its position | 1.Pr.Seal ring,2.Gland packing. |
| 6. | Isolation valve for TG-I PRDS(02 No) | 150 NB/1500# | V/V dismantalled,cleaning,lapping,blue matching done then boxed-up and installed in its position | 1.Pr.Seal ring,2.Gland packing. |
| 7. | Isolation valve in HP header(Boiler end) | 450 NB/1500# | V/V dismantalled,cleaning,lapping,blue matching done then boxed-up and installed in its position | 1.Pr.Seal ring,2.Gland packing. |
| 8. | Pr.Safety valve(LP steam header) 03 No | 200 NB/300# | V/V dismantalled,cleaning,lapping,blue matching done then boxed-up and installed in its position |  |
| 9. | Pr.Safety valve(LP steam header) 01 No | 200 NB/150# | V/V dismantalled,cleaning,lapping,blue matching done then boxed-up and installed in its position |  |

SAFETY VALVES O/H JOB UNDER PROGRESS

SAFETY VALVES READY FOR INSTALLATION

AFBC BOILER

AFBC Boiler had gone under shutdown from 11.04.2013, One day for cooling of boilers was taken and jobs were carried out up till 19.04.2013.

The jobs that were under taken during plants common shutdown are mentioned below:

| Sl. No. | AFBC BOILER / Jobs Under taken. |
| --- | --- |
| 1. | Overhauling of Main steam stop valves and main steam line NRV. |
| 2. | Overhauling of Steam drum and main steam line safety valves & other important valves. |
| 3. | Replacement of Valves. |
| 4. | Inspection & Repair of Dearator. |
| 5. | Replacement of 2nd Pressure control valve of Dearator. |
| 6. | Installation of flow meter in D.M water line. |
| 7. | Cleaning & Repair of Ash silo & Vent filter and overhauling of ash un loader 1 &2. |
| 8. | P.A .Fan 2 B alignment. |
| 9. | Boiler Feed Pump – “A” alignment. |
| 10. | Boiler Feed water Pump – “C” pump replacement. |
| 11. | Inspection & Servicing of Coal conveyor bearings/Gear Box. |
| 12. | Coal Bunker Sheeting structure improvement and G.I. sheeting. |
| 13. | Cleaning of furnace & inspection of pressure parts. |
| 14. | Repair & Replacement of P.A lines. |
| 15. | Boiler Bank ash drain line inspection / repair work. |
| 16. | H.P. Dosing Tank replacement work. |
| 17. | Sample cooler of both boiler, cooling water line to be replaced from MS to SS -304. |
| 18. | Other miscellaneous jobs. |

AFBC BOILER

1. Overhauling of Main Steam Stop Valves & NRV of main steam line of Boiler # OR/805 & OR/806.

Observations:

a) It was observed during that the steam was passing from Main steam stop valves & NRV of both the boilers at the time of normal operation.

b) At the time of hydro test of one boiler with other in running condition water was passing in main steam line i.e. hydro test pressure of 112.5Kg/Cm2 was not able to be held for long time as required as per IBR.

Action taken:

Lapping of both boilers main Steam Stop valve, NRV was done.

Result:

After lapping the valves were checked and the performance is found satisfactory.

NRV OVERHAULING UNDER PROGRESS        MSSV OVERHAULING UNDER PROGRESS

2. Overhauling of Steam Drum safety valves and main steam line safety valves of Boiler # OR/805 & OR/806 & other important valves.

Observations:

The overhauling of important valves such as safety valves of steam drum, main steam line was due and needed to be done keeping plant safety in mind.

Action taken:

Lapping of both boilers safety valves was done.

At the start of boiler # OR/805 the safety valves were set to the popping pressure mentioned below using floating pressure method:

1. Safety valve of steam drum (towards TG) – set to a popping pressure of 75 Kg/Cm2.

2. Safety valve of steam drum (towards Blr # OR/806) – set to a popping pressure of 76.1 Kg/Cm2.

3. Safety valve of main steam line was set to a popping pressure of 66.7 Kg/Cm2

At the start of boiler # OR/806 the safety valves were set to the popping pressure mentioned

below using online safety valve setting method (valtest):

1. Safety valve of steam drum (towards TG) – set to a popping pressure of 75.1 Kg/Cm2.

2. Safety valve of main steam line was set to a popping pressure of 66.43 Kg/Cm2

In addition to these valves other important valves whose overhauling was under taken is mentioned below:

1. Manual vent valve of both boilers (02 nos.)

2. Feed water line 30% & 100 % isolation valves of both boilers (10 nos).

Result:

After overhauling all the valves were checked and the performance is found satisfactory.

3. Replacement of valves of Boiler # OR/805 & OR/806.

Observations:

All the valves listed below were found to be damaged and needed replacement.

A. Attemprator line valve at DCF floor - 1 ½” inch.

B. Dearator Attemprator line valve -1” inch.

C. Boiler-1, main steam line 2nd pressure gauge 1st valve - 1” inch.

D. Boiler-1, 1st drain both valves- 1” inch.

E. Boiler-1, 3rd drain 1st valve- 1” inch.

F. Boiler-2, 2nd drain 1st valve- 1” inch.

G. MSSV by pass valve- 1” inch.

H. Boiler-1 CBD line valve to be replaced - 1” inch.

I. Boiler 1 & 2 – IBD line valve - 1 ½” inch

Action taken:

Total in all 19 gate valves replaced – 16 nos. 1” inch 1500 PSI, 03 nos. 1 ½” inch 1500 PSI.

Result:

Performance of newly replaced valves is found satisfactory.

4. Inspection and repair of Dearator:

Observations:

a) Sparger tank pipe supports were found broken.

b) Saturated water drain pipe inside the Deaerator was broken from welding (100 NB ASTM A 106). This was causing the cold water to mix with saturated water resulting in hammering of Dearator.

Action taken:

a) Sparger tank was positioned properly & Sparger tank pipe supports were welded,

b) Pipe was replaced and properly welded. 
c) Thorough cleaning of Deaerator was done

Result:

Hammering in Deaerator has stopped.

Photos of Dearator

Photos Showing Damaged Sparger tank supports & broken saturated water drain pipe

Photos showing repaired sparger tank support & rectified saturated water drain pipe

5. Replacement of 2nd pressure control valve of Dearator:

Observations:

2nd pressure control valve installed in Deaerator line was flange type and was in damaged condition thereby was causing leakage of steam from valve body.

Valve details:

Size: 150 NB,

Pressure Rating: 300 PSI, WCB. Flanged raised faced

Action taken:

Valve replaced from flange type to butt weld with higher pressure rating and MOC

Size: 150 NB,

Pressure Rating: 600 PSI, WC9.

Result:

Valve performance found to be satisfactory.

6. Installation of Flow meter in D.M. water line at Deaerator inlet:

Observations:

Suggestion for installation of flow meter in D.M water line at Deaerator inlet was given and was very much needed for the purpose of efficiency calculation of boiler.

Action taken:

Flow meter in D.M water line at Deaerator inlet was installed.

Result:

The exact quantity of D.M. Water used is now known to us the flow meter is showing actual water consumption.

7. Cleaning of Ash Silo, Replacement of Vent filter Bags & Overhauling of Ash un-loader # 1 & 2

Observations:

a) It was observed that during normal boiler operation heavy ash leakage was there due to leakages from bends at silo top.

b) Choked and damaged vent filter bags had caused infiltration of air vent.

c) Due to continuous running of ash un-loader most of the rotary parts had worn out causing frequent breakdown of the un-loaders

Action taken:

a) Damaged ash conveying bends at the top of silo were replaced.

b) All 72 vent filter bags were replaced with new bags.

c) All damaged parts were replaced such as Drive sprocket, trunion wheels, orifice feeder, adjusting sprockets.

d) All ash un-loaders and vent filter were painted.

e) Ash silo top cleaning was done.

f) Ash unloader-2 isolation valve maintenance done.

Result:

Ash emission from the top of ash silo has reduced and ash un-loaders are working satisfactorily.

Attachment: Photos of Ash Un-loader & vent filter repair work

Photographs showing overhauling of Ash un-loaders, vent filter after bag replacement and silo top cleaning.

8. P.A. Fan - 2B alignment

Observations:

a) It was observed that during normal boiler operation PA fan -2B motor vibration was quite high in horizontal and axial direction was high (Velocity in the range of 8 mm/sec).

b) On checking it was found that the bearing of the motor needed replacement.

c) Bearings of fan on inspection were found in good condition.

Action taken:

For the reason mentioned motor was handed over to electrical department both fan side bearings overhauling was done. After receiving of motor fan and motor alignment was done

Result:

a) Alignment values are as given below:

0                                                                             0.0

0.0 3                                               0.02                 - 0.02                                                   - 0.03

0.02                                                                          0.01

Axial Values 	                  Radial Values

9. Boiler feed Pump “A” replacement

Observations:

a) It was observed that during normal boiler operation discharge pressure of the pump had dropped from 84 kg/cm2 to 72 kg/cm2.

Action taken:

New Pump with mechanical seal was installed and aligned with motor.

Result:

a) After new pump installation alignment of pump was done the values are as stated below

0                                                                             0

-0.03                                                 0.02                       -0.01                                       - 0 .02

0.02                                                                         - 0.01

Axial Values 	                  Radial Values

b) Vibration values were in maximum range of 4.0 - 4.5 mm/sec .

10. Boiler feed Pump “C” alignment

Observations:

a) It was observed that during normal boiler operation Boiler feed pump “C” - motor servicing needed to be undertaken.

b) On checking it was found that the bearing of the motor needed replacement.

c) Bearings of pump and pump on inspection were found in good condition.

Action taken:

For the reason mentioned motor was handed over to electrical department both pump side bearings (drive & non –drive overhauling was done). After receiving of motor pump and motor alignment was done.

Result:

a) Alignment values are as given below:

0                                                                             0.0

0.0 2                                                0.02                 - 0.01                                               0.0

-0.04                                                                          -0.02

Axial Values 	                  Radial Values

11. Maintenance of Conveyor belts.

Observations:

With common shutdown it was possible to do cleaning of gear boxes and pulley bearings, chute repair of conveyors C-4, C-5, C-6,C-7 & RBFD.

Action taken:

a) All gear boxes overhauling was done (04 nos.).

b) All take-up, bend pulley, head pulley and tail pulley bearing cleaning & re greasing was done.

c) RBFD conveyor gear box damaged oil seal (42X62X8 MM) was replaced.

d) Chute repair of C-5, C-6 conveyor done.

e) Vibro feeder structure repair at C-5 conveyor done.

f) Greasing of C-7 trolley wheel done.

g) RBFD conveyor tail end pulley bearing and Plummer block replacement done.

h) C-5 conveyor tail end (coal tunnel) cleaning was done

Result:

Conveyor belts are running OK.

Attachment: Photos of Conveyor repair

Photos showing: Cleaning of coal tunnel, repaired conveyor discharge chute, greasing of pulley, bearings & trolley wheels.

12. Coal Bunker sheeting structure improvement work.

Observations:

1. It was observed that half of the coal bunker sheeting structure was badly damaged and needed replacement.

2. Asbestos sheeting found broken at this half of the bunker.

Action taken:

1. Old scrap support structure of half of the coal bunker was removed and new support structure provided.

2. In the damaged area instead of asbestos sheeting more reliable G.I. Sheeting was done.

Photos of replacement of damaged support & G.I. Sheeting work under progress.

13. Cleaning of furnace.

Observations:

a) Cleaning of furnace of both boilers was required.

b) Replacement of damaged bubble cap in boiler # OR/806 (01 nos.) was required.

c) Cracks were found in wind box of boiler # OR/805 & OR/806.

d) Refractory was found damaged at various places in furnace of boiler # OR/805 & OR/806.

Action taken:

a) Cleaning of furnace done.

b) Replacement of damaged bubble cap was done.

c) Welding of cracks found in wind box done.

d) Damaged refractory replacement done in both the boilers.

Result:

Both boilers are running satisfactorily.

14. Repair of P.A. lines.

Observations:

a) It was observed that during normal boiler operation lots of leakages in primary air lines and “T” pieces of Boiler # OR/805, OR/806 which are listed below

B- OR/806

Bed  		     Line

- 1st chute leakage, 1st line, 4th & 6th cross piece.

- 2, 5, & 6th line T-piece, 3rd & 4th cross piece top.

- 6th line chute.

- 1 line T-Piece.

- 6th line chute.

B- OR/805

Bed  		     Line

- 3rd line T-Piece to be replaced.

- 1 & 3rd Chute leakage, 2nd line T-Piece, 4th line spool-Piece.

- 6th line chute leakage

Action taken:

Leakages from P.A lines arrested.

Result:

P.A.lines are operating satisfactorily without leakage.

15. Boiler bank ash drain line inspection & repair work.

Observations:

It was observed that ash leakage was there from boiler # OR/805 bank ash drain line.

Action taken:

Leakage attended by welding.

Result:

Running without any leakages in the line.

16. H.P. Dosing tank replacement.

Observations:

The existing dosing tank was of mild steel and was rubber lined. The thickness of dosing tank had reduced with rubber lining also damaged below stated problems were faced:

1. Corrosion in tank was seen.

2. With failed rubber lining was causing frequent choking of dosing pump suction line.

Action taken:

Existing tank was replaced with pre fabricated SS-304 tank.

Result:

Performance of the tank is satisfactory.

17. Sample cooler inlet & outlet cooling water tubing to be replaced from M.S to SS - 304

Observations:

It was observed that there were frequent leakages from inlet & outlet cooling water tubing of mild steel in both boilers sample cooler.

Action taken:

Both inlet & outlet cooling water tubing of mild steel replaced with SS-304 tubing

Result:

No leakages found

18. Other miscellaneous jobs:

In addition to above mentioned jobs few other jobs which as per requirement were taken and

completed these are mentioned below:

1. Tapping for new compressor discharge line taken from existing plant air receiver tank line.

2. Chimney inspection.

3. Gland leakage arrested from fire hydrant valve near air receiver tank.

4. BLR-1 & 2 ESP 3rd field hopper fluidizing air line provided near to hopper.

5. BLR-1 2nd & 3rd bed ash drain line bellow leakage arrested.

6. BLR-1 boiler bank ash drain line fluidizing airline provided.

7. Thickness measurement of main steam line loop in AFBC boiler, plant air & Instrument air line

etc was carried-out.

8. Inst air line leakage arrested at both boilers APH bypass area.

9. Motorized dampers of primary air fans taken in to line.

10. Permanent instrument air line connection provided at ash unloader-2 isolation valve.

UTILITY & OFFSITE DEPARTMENT

- FILTER WATER SYSTEM

  - Both 6" dia. & 4" dia. damaged recirculation line with valve has been replaced & modified near filter water pond.

  - 700 NB dia  filter water supply line leakage arrested near TG switch yard by providing patch plate.

- DM PLANT & AIR COMPRESSORS

- 12" dia CS Corroded/ leaky Neutralization Pit Pump Discharge line  has been replaced with

upgraded MOC of SS316 L from DM Plant to PAP Ball Mill of approx. length of 630 mtr.

- 6" NB CS Instrument Air Header has been replaced with upgraded MOC of SS304from Compressor House to AFBC Boiler of approx. length of 650 mtr.

- 6" NB corroded CS instrument air inlet loop to dryer/receiver has been replaced with MOC SS 304 pipe of length 12 mtr.

C.  SAP COOLING TOWER.

1.  Both side of SAP Cooling Tower Returned Water re-circulation Distribution header with

riser pipes has been successfully relocated/ commissioned in a modified route to decrease load & increase the life of Cooling Tower.

- All  07 nos. of 150 mm dia. Blowdown Valves overhauled by dismantling,  cleaning, disc

lapping, replacement of corroded fasteners with gasket & then    reassembling.

- Inspection / Overhauling done for all 04 nos. Cooling water recirculation     pump of capacity of 6670 m3/hr whose observations are described below. Brushable ceramic coating applied on affected zone to prevent corrosions    and   pitting from inside casing of all 4 nos. of pump casings.

PUMP-A :- Casing opened  then  all parts such as impeller, neck   ring,  throat bush, journal bearing ,ball bearing , oil wiper rings are cleaned  and checked, found driving side gland sleeve worn out and neck ring crack. Same are replaced with new one& then new gland packing & oil replaced. Both side journal bearing checked, found bearing scouring so replaced with new one & then clearances set. Top casing inside coating applied.

Alignment readings are as follows.

PUMP-B :- Casing opened  then  all parts such as impeller, neck ring,  throat bush, journal bearing , ball bearing & oil wiper rings are cleaned  and  checked , found both side gland sleeve badly worn out .Hence completely new rotor assembly , gland packing , oil and both side journal bearing replaced & then clearances set . Thrust bearing replaced with new one. Top casing inside coating applied as found partially corrosive.

Alignment done and readings are as follows.

Pump C :- Casing opened then  all parts such as impeller, neck ring,  throat bush, journal bearing ,ball bearing & oil wiper rings are cleaned and checked found  ok .Hence boxed up with replacing new gland packing & oil. Top casing inside coating applied to protect against corrosion. Alignment readings are as follows.

Pump-S:- Casing opened  then  all parts such as impeller, neck   ring,  throat bush, journal bearing ,ball bearing & oil wiper rings are cleaned & checked .Found   thrust bearing is worn out & NDE side latern ring crack .Hence replaced with new one& then new  gland  packing , oil replaced. Both side journal bearing checked found DE side bearing scouring so replaced with new one & then clearances set. Top casing inside coating applied to protect against corrosion.

Alignment   readings are as follows.

E.  AMMONIA TRANSFER LINE (8” DIA) TAPPING

17.  8” NB LTCS ammonia  transfer line has been hooked up & commissioned in a constant   elevation of 5.5 mtr height with a  modified route  from TP7 to back side of U & O Substation of  approx. length of 1.3 KM.

INSTRUMENTATION

DAP  TRAIN # A

LIST OF JOBS UNDERTAKEN DURING ANNUAL SHUTDOWN - 2013

- Overhauling and calibration of control valves

- FSOV 124 &FSOV127 Slurry main & recycle.

- FV-104(Vap. NH3  to Granu.).

- HV-111 (Steam flushing to slurry recycle.

- FV-106&FV106-1(Sul. Acid to PN).

- FV-107&FV-107-1(Pre. To PN)

- FV-103(54% P2O5 to PN)

- FV-105(28% P2O5  to PN)

- FV-603(Weak acid to pre)

- FV-602(Wash liq.to PN)

- FV-618(Weak acid to pri. tank)

- FV-628(Wash liq to pri. tank)

- FV-707(TG liq to pri. tank)

- HV-102(MP steam to PN)

- FV-606(Pri. To Pre.)

- FV-638(h2so4 to primary)

- FV-763(Weak acid to TG)

- FV-764(Wash liq. To TG)

- FV-729(Pond water to TG)

- LV-714(TG vap. level)

- LV-721 (Ammon. Vap level)

- FV-717(LP Steam to pre heater)

- PV-716-6(ammo.vap condensate)

- TV-755(Pre heater outlet to condensate)

- FV-200(FO to chamber)

- FY-50 (Pan Feeder Gate)

- FO Main & bypass

- PV-210 (Steam atomizing)

- Replacement of control valves

- TG Main & Bypass,FV101 (Vap. ammon. To PN),PV-759(Liq. ammon.)

- Cleaning and calibration of flow meters

- FT-127(21 pump) & FT-124(22 pump),FT-104,FT-101

- Jobs carried out in the Control Room

- DCS all cards, connecters and HMI cleaning done. UPS checking and maintenance done

- Other major jobs

- All JB maintenance

- Pre, Primary, PN,TG dip tube inspection.

DAP  TRAIN # B - INSTRUMENTATION

LIST OF JOBS UNDERTAKEN DURING ANNUAL SHUTDOWN - 2013

- Overhauling and calibration of control valves

1.       FSOV 124 &FSOV127 Slurry main & recycle.

2.       FV-104(Vap. NH3  to Granu.)

3.       HV-111 (Steam flushing to slurry recycle)

4.       FV-106&FV106-1(Sul. Acid to PN)

5.       FV-107&FV-107-1(Pre. To PN)

6.       FV-103(54% P2O5 to PN)

7.       FV-105(28% P2O5  to PN)

8.       FV-603(Weak acid to pre)

9.       FV-602(Wash liq.to PN)

10.   FV-618(Weak acid to pri. tank)

11.   FV-628(Wash liq to pri. tank)

12.   FV-707(TG liq to pri. tank)

13.   HV-102(MP steam to PN)

14.   FV-606(Pri. To Pre.)

15.   FV-638(h2so4 to primary)

16.   FV-764(Wash liq. To TG)

17.   FV-729(Pond water to TG)

18.   LV-714(TG vap. level)

19.   LV-721 (Ammon. Vap level)

20.   FV-717(LP Steam to pre heater)

21.   PV-716-6(ammo.vap condensate)

22.   TV-755(Pre heater outlet to condensate)

23.   FV-200(FO to chamber)

24.   FY-50 (Pan Feeder Gate)

25. FO Main & bypass

26. PV-210 (Steam atomizing)

- Replacement of control valves

- TG Main & Bypass,FV101,

- Cleaning and calibration of flow meters.

- FT-127(21 pump) & FT-124(22 pump), FT-104,FT-101

- Jobs carried out in the Control Room

- DCS all cards, connecters and HMI cleaning done. UPS checking and maintenance done

- Other major jobs

- All JB maintenance,

- Pre, Primary, PN,TG dip tube inspection

DAP  TRAIN # C  - INSTRUMENTATION

LIST OF JOBS UNDERTAKEN DURING ANNUAL SHUTDOWN - 2013

- Overhauling and calibration of control valves

1.       FSOV 124 &FSOV127 Slurry main & recycle.

2.       FV-104(Vap. NH3  to Granu.)

3.       HV-111 (Steam flushing to slurry recycle)

4.       FV-106&FV106-1(Sul. Acid to PN)

5.       FV-107&FV-107-1(Pre. To PN)

6.       FV-103(54% P2O5 to PN)

7.       FV-105(28% P2O5  to PN)

8.       FV-603(Weak acid to pre)

9.       FV-602(Wash liq.to PN)

10.   FV-618(Weak acid to pri. tank)

11.   FV-628(Wash liq to pri. tank)

12.   FV-707(TG liq to pri. tank)

13.   HV-102(MP steam to PN)

14.   FV-606(Pri. To Pre.)

15.   FV-638(h2so4 to primary)

16.   FV-763(Weak acid to TG)

17.   FV-764(Wash liq. To TG)

18.   FV-729(Pond water to TG)

19.   LV-714(TG vap. level)

20.   LV-721 (Ammon. Vap level)

21.   FV-717(LP Steam to pre heater)

22.   PV-716-6(ammo.vap condensate)

23.   TV-755(Pre heater outlet to condensate)

24.   FV-200(FO to chamber)

25.   FY-50 (Pan Feeder Gate)

26. FO Main & bypass

27. PV-210 (Steam atomizing)

- Replacement of control valves

- TG Main & Bypass,FV101

- Cleaning and calibration of flow meters

- FT-127(21 pump) & FT-124(22 pump), FT-104,FT-101

- Jobs carried out in the Control Room

- DCS all cards, connecters and HMI cleaning done.UPS checking and maintenance done

- Other major jobs

- All JB maintenance,

- Pre, Primary, PN,TG dip tube inspection, Potash & Urea weigh feeder commissioning.

PAP- INSTRUMENTATION

LIST OF JOBS UNDERTAKEN DURING ANNUAL SHUTDOWN - 2013

1. Maintenance of  Control Valves

(i) FY-1005 A,C,D,E,G overhauling and stroke checking done.

(ii)LY-1000-1A,B,C,D,E,F stroke checking and calibration done.

(iii)FY-200 A,B,C,D  overhauling and stroke checking  done.

(iv) FY-807 A,B,C,D,E  overhauling, stroke checking and calibration done.

(v) FY-807 F,G stroke checking and calibration done.

(vi) PY-829 A,B,C,D,E,F,G stroke checking & calibration done.

(vii) LY-818-1 B,F,G overhauling, stroke checking & calibration done.

(viii) LY-818-1 A,C,D,E stroke checking & calibration done.

(ix) LY-818-2 B,F,G  overhauling, stroke checking & calibration done.

(x) LY-818-2 A,C,D,E stroke checking & calibration done.

(xi) LY-823 E,F overhauling, stroke checking & calibration done.

(xii) LY-823 A,B,C,D,G  stroke checking & calibration done.

(xiii) FY-824 B,E,F,G overhauling, stroke checking & calibration done.

(xiv) FY-824 A,C,D  stroke checking & calibration done.

(xv) HV-845 A-G & FY-807-2 A-G (ON/OFF valves ) operation checking done.

(xvi) LY-711, TY-712 stroke checking & calibration done.

2. Replacement of Control Valves

(i)FY-1005F replaced with spare one.

(ii) FY-807 2B (Belt Filter condenser water ON-OFF valve) replaced with a new one.

3. Flowmetres

(i)FIT-1005 A, C, D,E,F,G flow heads descaled  and checked.

(ii)FIT-1004 A,B,C,D,E,F,G  all transmitter calibrated.

(iii)FIT-200 A,B,C,D  flow heads descaled and checked.

(iv) FIT-809 E, FIT-809-2E, FIT-815 E, FIT-815-2E flow heads descaled and checked.

4.Other jobs

a)Temperature

(i)TIT-1006 A,B,C,D,E,F,G ,TIT-1010 A,B,C,D,E,F,G and TIT-601,539,603  all transmitters checked with decade box and  calibrated.

(ii) )TIT-1006 A,B,C,D,E,F,G ,TIT-1010 A,B,C,D,E,F,G and TIT-601,539,603 all thermowell ,RTD removed and checked.

(iii)TIT-1006 F,G and TIT-1010G RTD changed.

(iv)TIT-1010 A,F,G ,TIT-738 new thermowell installed.

b) Pressure

(i)PIT-1008 A,B,C,D,E,F ,PIT-1527,PDIT-1519 all transmitters calibrated.

(ii)PIT-1007 C,F,G transmitter impulse line dechocking and calibration done.

c) Level

(i)LIT-1000 A,B,C,F,G  ,LIT-1501 ,LIT-115 A,B,C,D all transmitters checking and calibration done.

(ii) LIT-115 A,B,C,D all transmitters checking and calibration done.

(iii) LIT-842 A,B,C,D,E,F,G  all transmitters checking and calibration done.

(iv) LIT-812 A,B,C,D,E,F,G  all transmitters checking and calibration done.

(v) LIT-818-2 A,B,C,D,E,F,G  all transmitters checking and calibration done.

(vi) LIT-818-1 A,B,C,D,E,F,G  all transmitters checking and calibration done.

(vii) LIT-823 A,B,C,D,E,F,G  all transmitters checking & calibration done.

d) Miscellaneous

(i)CIT-1003 A,B,C,D,E,F,G  sensor cleaning and calibration with standard solution.

(ii) Reactor Agitators pressure and flow switches  checking and calibration done.

(iii) Evap.  A,B,C,D,E,F condensate pot changed.

(iv) All weighfeeders cleaning, checking, Idler arrangement adjustment and calibration done by service Engineer from Schenck Process.

(v) Conveyor 104  load cell replaced and it’s calibration done.

(vi) Ball mill area all pressure switches calibration done & faulty switches replaced with new one.

(vii) Ball mill area 02 nos. JB’s replaced with a new one.

(viii) Ball mill area all gate valve hand switch JB’s maintenance done. Faulty hand switches replaced with new ones.

(ix) FIT – 225, 226, 227 flow transmitters relocated to ground floor.

(x) FFT area all gate valves maintenance & operation checking done.

(viii) Filtration C,D,E  level transmitter shifting job undertaken.

(viii) Gypsum pump 291,292,293 all switches maintenance & calibration done.

( ix) Gypsum pump Miller unit JB maintenance done.

e. Jobs carried out in the Control Room

Following DCS related jobs also carried out

1.Yokogawa DCS all cards, connecters and HMI cleaning done.

2.B/M PLC all cards,connecters and HMI cleaning and maintenance done.

3.GE FANUC PLC all cards checked and two nos. of digital input cards changed

.

4.UPS checking and maintenance done.Three nos. of batteries also changed.

SAP- INSTRUMENTATION

LIST OF JOBS UNDERTAKEN DURING ANNUAL SHUTDOWN - 2013

- Overhauling and Calibration of following control valves is carried out

| S.No. | Tag No. | Area |
| --- | --- | --- |
| 1 | 10AV1420-1 | SAP-1 |
| 2 | 10AV1450-1 | SAP-1 |
| 3 | 10AV1440-1 | SAP-1 |
| 4 | 10LV1440 | SAP-1 |
| 5 | 10LV1450 | SAP-1 |
| 6 | 10AV1440-2 | SAP-1 |
| 7 | 10AV1450-2 | SAP-1 |
| 8 | 10LV0104 | SAP-1 |
| 9 | 10LV1301D | SAP-1 |
| 10 | 10LV1301 | SAP-1 |
| 11 | 10TV1308 | SAP-1 |
| 12 | 10TV1326 | SAP-1 |
| 13 | 10TV1506 | SAP-1 |
| 14 | 10PV1304 | SAP-1 |
| 15 | 10LV0105 | SAP-1 |

- Cleaning and Calibration of following flow meters  is carried out

| S.No. | Tag No. | Area |
| --- | --- | --- |
| 1 | 10FT 1201 | SAP-1 |
| 2 | 10FT 1206 | SAP-1 |
| 3 | 10FT 1301 | SAP-1 |
| 4 | 10FT 1302 | SAP-1 |
| 5 | 10FT 1303 | SAP-1 |
| 6 | 10FT 1304 | SAP-1 |
| 7 | 10FT 1305 | SAP-1 |
| 8 | 10FT 1306 | SAP-1 |
| 9 | 10FT 1401 | SAP-1 |
| 10 | 10FT 1560 | SAP-1 |
| 11 | 10FT 1460 | SAP-1 |

- Overhauling and Calibration of following control valves is carried out- SAP 2

| S.No. | Tag No. | Area |
| --- | --- | --- |
| 1 | 10AV2420-1 | SAP-2 |
| 2 | 10AV2450-1 | SAP-2 |
| 3 | 10AV2440-1 | SAP-2 |
| 4 | 10LV2440 | SAP-2 |
| 5 | 10LV2450 | SAP-2 |
| 6 | 10AV2440-2 | SAP-2 |
| 7 | 10AV2450-2 | SAP-2 |
| 8 | 10LV0204 | SAP-2 |
| 9 | 10LV2301D | SAP-2 |
| 10 | 10LV2301 | SAP-2 |
| 11 | 10TV2308 | SAP-2 |
| 12 | 10TV2326 | SAP-2 |
| 13 | 10TV2506 | SAP-2 |
| 14 | 10PV2304 | SAP-2 |
| 15 | 10LV0105A | SAP-2 |

- Cleaning and Calibration of following flow meters  is carried out – SAP 2

| S.No. | Tag No. | Area |
| --- | --- | --- |
| 1 | 10FT 2201 | SAP-2 |
| 2 | 10FT 2206 | SAP-2 |
| 3 | 10FT 2301 | SAP-2 |
| 4 | 10FT 2302 | SAP-2 |
| 5 | 10FT 2303 | SAP-2 |
| 6 | 10FT 2304 | SAP-2 |
| 7 | 10FT 2305 | SAP-2 |
| 8 | 10FT 2306 | SAP-2 |
| 9 | 10FT 2401 | SAP-2 |
| 10 | 10FT 2560 | SAP-2 |
| 11 | 10FT 2460 | SAP-2 |

E. Overhauling and Calibration of following control valves is carried out-COMMON

| S.No. | Tag No. | Area |
| --- | --- | --- |
| 1 | 10LV1536-A | Common |
| 2 | 10LV1536-B | Common |
| 3 | 10TV1510A | Common |
| 4 | 10LV0108 | Common |
| 5 | 10TV1554 | Common |
| 6 | 10PV2602A | Common |
| 7 | 10PV2602B | Common |
| 8 | 10PV1504 | Common |
| 9 | 10PV1392 | Common |
| 10 | 10PV1555 | Common |
| 11 | 10LV0429 | Common |
| 12 | 10AV0427 | Common |
| 13 | 10FT 101A-IS | Common |
| 14 | 10FT 101C-IS | Common |
| 15 | 10FT 1402 | Common |
| 16 | 10FT 1403 | Common |

- Jobs carried out in Control Room

| Cleaning of DCS |  |  |
| --- | --- | --- |
| S.No. | Panel No. | Area |
| 1 | 100 | SAP-1 |
| 2 | 101 | SAP-1 |
| 3 | 102 | SAP-1 |
| 4 | 103 | SAP-1 |
| 5 | 104 | SAP-1 |
| 6 | 400 | SAP-1 |
| 7 | 200 | SAP-2 |
| 8 | 201 | SAP-2 |
| 9 | 202 | SAP-2 |
| 10 | 203 | SAP-2 |
| 11 | 204 | SAP-2 |
| 12 | 401 | SAP-2 |
| 13 | 300 | Common |
| 14 | 301 | Common |
| 15 | 302 | Common |
| 16 | 303 | Common |
| 17 | 304 | Common |
| 18 | 305 | Common |
| 19 | 402 | Common |

| Cleaning of HMIs |  |  |
| --- | --- | --- |
| S.No. | HIS No. | Area |
| 1 | 157 | Control Room |
| 2 | 158 | Control Room |
| 3 | 159 | Control Room |
| 4 | 160 | Control Room |
| 5 | 161 | Control Room |
| 6 | 162 | DCS Room |
| 7 | 163 | DCS Room |
| 8 | 164 | DCS Room |

| Cleaning of Consoles |  |  |
| --- | --- | --- |
| S.No. | Console No. | Area |
| 1 | 71 | Control Room |
| 2 | 81 | Control Room |
| 3 | 57 | Control Room |
| 4 | 58 | Control Room |
| 5 | 59 | Control Room |
| 6 | 60 | Control Room |
| 7 | 82 | Control Room |
| 8 | 72 | Control Room |

| Cleaning of UPS |  |  |  |  |
| --- | --- | --- | --- | --- |
| S.No. | UPS No. |  | Area |  |
| 1 | UPS-1 |  | UPS Room |  |
| 2 | UPS-2 |  | UPS Room |  |
| Other Jobs |  |  |  |  |
| S.No. | Job Description |  | Area |  |
| 1 | Repacement of 34 Nos. Batteries in UPS-1 |  | UPS Room |  |
| 2 | Replacement of Left Processor Card CP451 in FCS101 |  | SAP-1 Cabinet No. 100 |  |
| 3 | Replacement of Left Processor Card CP451 in FCS103 |  | Common Cabinet No. 300 |  |
| 4 | Installation of Annunciator Panel in Common Area |  | Control Room |  |
| Other Jobs |  |  |  |
| S.No. | Job Description | Area |  |
| 1 | Signals from drives in new Substation are taken in DCS | SAP-1 & 2 |  |
| 2 | Ultrasonic flowmeter in sulphur line FT1201 got replaced | SAP-1 |  |
| 3 | Ultrasonic flowmeter in sulphur line FT2206 got replaced | SAP-2 |  |
| 4 | Vibration probes in turbine and blower are interchanged for probe safety | SAP-1 & 2 |  |
| 5 | Air Filer SOVs maintenance has been done | SAP-1 & 2 |  |
| 6 | Stack Analyzer maintenance has been done | SAP-1 & 2 |  |
| 7 | Start-up vent damper pneumatic actuator got replaced | SAP-1 & 2 |  |
| 8 | SH-1 TCV2506 servicing has been done | SAP-2 |  |

AFBC Boiler- INSTRUMENTATION

LIST OF JOBS UNDERTAKEN DURING ANNUAL SHUTDOWN - 2013

- Replacement of Valve Body of the Control Valve Assembly, Tag No - 50 PIC 005

- Gland Leakage attended of the Control Valve having Tag No- 50 PIC 003

- DM water line Temperature sensor (RTD-PT 100, 3 Wire) & Transmitter, Tag No- 50 TI 001 installation done & 4. taken in line.

- BFW Pump A 1/2" SS Tubing work Completed for Pump Bearing (Suction, Discharge sides) Cooling Purposes.

- Boiler A PA Fan 1B  Damper Actuator (Tag No- 50 HIC 409A) Positioner Changed with a new one.

- Boiler A ESP - 1st Field Air Conveying Valve (Tag No- 50 XV 561A) replaced with a new one.

- Overhauling & Servicing of all FD Fan Damper Actuators/Power Cylinders (Tag No- 50 HIC 402A, 50 HIC 403A) were done

- Overhauling & Servicing of all ID Fan Damper Actuators/Power Cylinders (Tag No- 50 HIC 301A, 50 HIC 302A) were done.

- Overhauling & Servicing of all PA Fan Damper Actuators/Power Cylinders (Tag No- 50 HIC 408A, 50 HIC 409A) were done.

- Overhauling of all Windbox Power Cylinders ( Tag No- 50 HIC 416A, 50 HIC 417A, 50 HIC 418A, 50 HIC 419A, 50 420A) were done.

- Overhauling & Servicing  of all Ash Intake Valve Power Cylinders (Tag No- 50 XV 553A, 50 XV 554A, 50 XV 555A) were done.

- A new Temperaure Transmitter (Tag No- 50 TI 205A) has been replaced in Boiler A.

- Calibration of the said Transmitters has been done: Tag No- 50 PI 005, 50 PI 003, 50 LI 001, 50 LI 002, 50 FI 006.

- Old Ash Silo Vent Filter System taken in line. All SS tubing work for the SOVs were done. The damaged sequence controller has been replaced with a new one.

- Old Ash Silo ash unloaders ash intake valve SS tubing work completed. Separate Instrument air connections are provided for each unloaders.

- Bed Height Measuring U-Tube inside Furnace found damaged in 1st, 3rd, 4th beds. Those were replaced with new U-Tubes.

- Furnace Bed Temperature Measuring Thermocouples found damaged in 1st & 5th bed (Tag No- 50 TI501A, 50 TI 509A). Those were replaced with new ones.

- 1/2'' nipple with Isolation Valve,  mechanical tapping work at individual air conveying line of ash conveying system was completed for the installation of air back pressure Transmitters.

- DCS all cards, connecters and HMI cleaning done.

- UPS & batteries Cleaning done

ENERGY CENTER – INSTRUMENTATION

LIST OF JOBS UNDERTAKEN DURING ANNUAL SHUTDOWN - 2013

- Jobs done for control valve:

- Overhauling of gland steam control valve 2PCV4510 done.

- PCV-2631 of TG 2 PRDS valve positioner replacement and overhauling done.

- PCV-906 MP steam to DAP valve overhauling done.

- PCV 1507 MP steam vent valve overhauling done.

- PCV 1513 LP steam vent valve actuator overhauling done.

- I/P for TCV 2632 replaced.

- Positioner for PCV 1514 replaced.

- Regulators for PCV1513, PCV 1514, FV 906 and PCV 909 changed.

- New installation:

- Installation of HP steam vent valve PCV 1501 was done.

- Control Room related Jobs:

- TG DCS Controller sa083102 and sa083202 replaced and all controllers were restarted.

- DM plant and Ammonia DCS all cards, connecters and HMI cleaning done.

- TG, DM Plant, & Ammonia UPS Cleaning done & TG UPS-1 Batteries replaced with new one.

- Other Major Job:

- Instrument cable relocation done for 12 nos. feeders in DM plant electrical substation.

- All motorized operated valves of TG-1 & TG-2 were taken into line in DCS.

- Replacement of all terminal blocks in TG-1 GEN CON JBs 1 to 6.

BAGGING – INSTRUMENTATION

LIST OF JOBS UNDERTAKEN DURING ANNUAL SHUTDOWN - 2013

- Jobs carried out in the Control Room

- In the Bagging control room new UPS has been installed & also taken in the line

- Inside control room 07 nos of bagging machine panel & PLC panel air cleaning & terminal tightness has been done.

- In Weigh Bridge, From Pit type To Pitless, 02 nos of new 60 mt electronic road weighbridge has been installed & also taken in the line.

- Other Major jobs carried out

- 24 nos of bagging weigh hopper overhauling done. For that

a). 96 Hopper door flange bearing

b). 48 nos of roller bearing

c). 84 mtr of seal rubber

d). 07 nos of hopper door cylinder

e). 26 nos of air flow valve  used.

- In Bird beak area 48 nos of bag grip rubber used

- In control J.B   18 nos of Push button, 09 nos of Indication lamp , 3 nos of E.S used

- 96 nos of machine's junction box air cleaning, terminal tightness

ELECTRICAL

A.	DAP Area

| 1 | RETROFITTING OF BREAKERS |
| --- | --- |
| 1.1 | 3 Nos of 4000Amps incomer breakers and 2 nos of 2500A out going breakers (Make-schneider ) were replaced in the PCC-4 and PCC-5. 2 Nos of 4000Amps incomer breakers and 3 nos of 2500A out going breakers (Make-L&T ) were replaced in the PCC-4 and PCC-5. Problems faced and Improvement – GE Breakers power contact assembly failure rate became very high due to overheating of jaw contacts resulting in to Flashovers and equipment down. After replacement same has been eliminated and Reliability is increased. |
| 2.0 | 33 KV SWITCH GEAR MAINTENANCE |
| 2.1 | 33KV Both Brkr. chambers Cleaning, Tightness Checking, Control Checking etc done. |
| 3.0 | 6.6KV SWITCH GEAR MAINTENANCE SECTION –A |
| 3.1 | 6.6KV Bus Section-A Brkr. chambers Cleaning, Tightness Checking, Control Checking etc done. |
| 3.2 | 6.6KV Bus Section-A all Brkr. trolley Cleaning, mechanism inspection, close/trip checking etc. |
| 4.0 | 6.6KV SWITCH GEAR MAINTENANCE SECTION –B |
| 4.1 | 6.6KV Bus Section-B Brkr. chambers Cleaning, Tightness Checking, Control Checking etc. |
| 4.2 | 6.6KV Bus Section-B all Brkr. trolley Cleaning, mechanism inspection, close/trip checking etc. |
| 5.0 | 6.6KV SWITCH GEAR BUSCOUPLERS |
| 5.1 | 6.6KV Bus Coupler Breaker. chambers Cleaning, Tightness Checking, Control Checking etc. |
| 5.2 | 6.6KV Bus Coupler Breaker. trolley Cleaning, mechanism inspection, close/trip checking etc. |
| 6.0 | PCC Maintenance. |
| 6.1 | PCC-4 Bus Section-A Busbar Cleaning, Tightness Checking, Control Checking etc. |
| 6.2 | PCC-4 Bus Section-B Busbar Cleaning, Tightness Checking, Control Checking etc. |
| 6.3 | PCC-4 Bus Section-C Busbar Cleaning, Tightness Checking, Control Checking etc. |
| 6.4 | PCC-4 Bus Section-D Busbar Cleaning, Tightness Checking, Control Checking etc. |
| 6.5 | PCC-4 Bus Couplers Busbar Cleaning, Tightness Checking, Control Checking etc. |
| 6.6 | PCC-4 all O/G feeder Cleaning, mechanism inspection, close/trip checking etc. |
| 6.7 | PCC-4 Bus Section-A Busbar Cleaning, Tightness Checking, Control Checking etc. |
| 6.8 | PCC-4 Bus Section-B Busbar Cleaning, Tightness Checking, Control Checking etc. |
| 6.9 | PCC-4 Bus Section-C Busbar Cleaning, Tightness Checking, Control Checking etc. |
| 6.10 | PCC-4 Bus Section-D Busbar Cleaning, Tightness Checking, Control Checking etc. |
| 6.11 | PCC-4 Bus Couplers Busbar Cleaning, Tightness Checking, Control Checking etc. |
| 6.12 | PCC-4&5 I/C & O/G BKRS maintenance, Cleaning, mechanism inspection, close/trip checking etc done by M/s GE. |
| 6.14 | PCC-4 all O/G feeder Cleaning, mechanism inspection, close/trip checking etc. |
| 7.0 | MCC Maintenance for TR#A, TR#B, and TR#C |
| 7.1 | All MCCs out surface, rubber mat cleaning done. |
| 7.2 | Busbar Cleaning, Busbar bolt Tightness carried out. |
| 7.3 | Breakers mechanism and control checking done. |
| 7.4 | All Feeder Cleaning, Tightness Checking, Control & Logic Checking |
| 8.0 | Chain mill MCC Maintenance for TR#A, B And C MCCs |
| 8.1 | All MCCs out surface, rubber mat cleaning done. |
| 8.2 | Busbar Cleaning, Busbar bolt Tightness carried out. |
| 8.3 | Breakers mechanism and control checking done. |
| 8.4 | All Feeder Cleaning, Tightness Checking, Control & Logic Checking |
| 9.0 | PDBs and LDB Maintenance |
| 9.1 | Maintenance of All the PDBs and LDBs of DAP and Bagging is done. |
| 10.0 | MCC Maintenance -- MCC 34,35 36 37 &38(Bagging) |
| 10.1 | All MCCs outer surface, rubber mat cleaning done. |
| 10.2 | Busbar Cleaning, Busbar bolt Tightness carried out. |
| 10.3 | Breakers mechanism and control checking done. |
| 10.4 | All Feeder Cleaning, Tightness Checking, Control & Logic Checking |
| 12.0 | Transformers Maintenance. |
| 12.1 | Complete over Hauling of 6.6 Kv/415v, 2 MVA transformers TR#24,26,27,29 &30 carried out by M/s Voltamp transformers Ltd. |
| 13.0 | Relay Testing and calibration |
| 13.1 | 08 nos7SJ600 relays installed in 6.6 kV panels were tested for functionality. |
| 14.0 | Breaker Maintenance |
| 14.1 | 20nos LT Siemens breaker servicing done. |
| 15.0 | Emergency Power supply |
| 15.1 | The new MLDB Testing and commission done. |
| 16.0 | Battery & CHARGER INSTALLATION |
| 16.1 | 02 nos 50 amp battery charger Installed & testing and commissioning done the same. |
| 16.2 | 01set battery installed ,testing &commissioning done & taken in line. |
| 17.0 | Maintenance of Motors |
| 17.1 | TR#B- Granulator, Dust and Fumes, and Drier ex. Fan over hauling done. |
| 17.2 | TR#C- Granulator, Drier, Dust and Fumes, and Drier ex. Fan over haulling done. |
| 17.3 | LT Motors- All TR#A,B&C, chain mill motors Overhauling done. |
| 17.4 | LT Motors- All TR#B&C, elevator motors overhaulling done. |
| 17.5 | LT Motors- All TR#A,B&C, Fines,RM,DDC ,20series,40,50,60,80,90 series motors motors overhaulling done. |
| 17.6 | All Bagging motors maintenance is carried out at site. |
| 18.0 | Installation of Zero speed switches |
| 18.1 | In All trains Zero speed switches maintenance carried out and taken in to line. |
| 19.0 | Conveyor safety equipment maintenance |
| 19.1 | All PH conveyors damaged Pull chord is replaced, switches replaced/ maintenance done. |
| 19.2 | ZSS lined up. |
| 19.3 | Conveyor hooters lined up. |

B.	Energy Center

| Sl.No | Equipment | Job Description | Jobs Carried out by |
| --- | --- | --- | --- |
| 1 | 33 kV | 33KV Bus Section-B Brkr. chambers Cleaning, Tightness Checking, Control Checking etc. All the Space heaters ckecked. 2 Nos of space heaters were newly installed in TG#2 I/C Breaker backside. | Departmentally |
| 2 |  | 33KV Bus Section-A Brkr. chambers Cleaning, Tightness Checking, Control Checking etc. All the Space heaters ckecked. 2 Nos of space heaters were newly installed in TG#2 I/C Breaker backside. | Departmentally |
| 4 | 6.6 kV | 6.6KV Bus Section-A Brkr. chambers Cleaning, Tightness Checking, and Control Checking. All the space heater checked and 5 nos of faulty space heaters were replaced with new one. | Departmentally |
| 5 | MCC | TG#2 MCC maintenance done, busbar cleaning, Control tightness checking done and normalized. | Departmentally |
| 6 | Emergency Supply | Emergency supply for TG#1 &2 and MLDB scheme checked from U/O | Departmentally |
| 7 | MOV | TG#1 & 2 Auma valves Overhauling done. | Auma Service Engr |
| 8 | Battery Charger | NEW 220V Battery charger for TG#1 & 2 commissioning done. New 110V battery charger commissioning done for switchyard | Universal Service Engr |
| 9 | MOV | All LIMITORQUE MOVs in TG#1 & 2 in total 17 nos Overhauling done | Limitorque Service Engr |
| 10 | TR-39 | TR#39 2MVA transformer Overhauling done | M/S Volt AMP |
| 11 | TR-40 | TR#40 2MVA transformer Overhauling done | M/S Volt AMP |
| 12 | VCB Breaker, Make- Siemens | 33KV/6.6KV Siemens Breaker maintenance | M/S Siemens |
| 13 | ACB Breaker, Make- L&T | All the MCC incomers ofTG#1,TG#2,SAP cooling tower ,TG cooling tower ACB breaker maintenance done | M/S L&T |
| 14 | Protection Relays | Relays testing done for 6.6KV motor feeders. Scheme checked for TG#1,TG#2 new PCC. | M/s Power system consultants |
| 15 | PLC | PLC job for LMS system done for various feeders at AFBC boiler,U/O and E/C | Departmentally & Rockwell service Engr |
| 16 | TG#1 | TG#1 Overhauling job done | M/S ALSTOM |
| 17 | 80MVA Transformer | TG#1 80MVA Transformer maintenance done | M/S Volt AMP |
| 18 | Spaceheater | Spaceheaters for 33KV and 6.6KV feeders cable laid from new panel to all feeders and taken in line. | Departmentally |
| 19 | Capacitor banks | Capacitor banks cleaning done | Departmentally |
| 20 | Battery charger | TG#1,TG#2,Switchyard,switchgear HBL make Battery chargers maintenance done | HBL service Engr |
| 21 | ACB Breaker, Make- GE | GE ACB Breaker maintenance of PCC Breakers including spare feeder | GE Service Engr |

C.	Utility and Ammonia

| Sl. | Type Of Jobs Carried Out/Performed | Job performed By |
| --- | --- | --- |
| 1 | Preventive Maintenance of 33 KV switchgear at Utility & Ammonia Bus Section-B | Departmentally |
|  | Dedusting, Busbar tightness checking, sealing of panels, spaceheater checking, Breaker healthyness checking, Testing of closing ,tripping & interlocking Ckt. |  |
| 2 | Preventive Maintenance of 33 KV switchgear at Utility & Ammonia Bus Section-A | Departmentally |
|  | Dedusting, Busbar tightness checking, sealing of panels, spaceheater checking, Breaker healthyness checking, Testing of closing ,tripping & interlocking Ckt. |  |
| 3 | Preventive Maintenance of 6.6 KV switchgear at Utility Bus Section-B | Departmentally |
|  | Dedusting, Busbar tightness checking, sealing of panels, spaceheater checking, Breaker healthyness checking, Testing of closing ,tripping & interlocking Ckt. |  |
| 4 | Preventive Maintenance of 6.6 KV switchgear at Utility Bus Section-A | Departmentally |
|  | Dedusting, Busbar tightness checking, sealing of panels, spaceheater checking, Breaker healthyness checking, Testing of closing ,tripping & interlocking Ckt. |  |
| 5 | Preventive Maintenance of 415 Volt PCC at Utility . De-dusting, Bus bar tightness checking and breaker healthyness checking etc. | Departmentally |
| 6 | Dedusting, checking of Charger & battery bank, checking of relay & alarm contacts for UTILITY and AMMONIA S/S. | External Agency (HBL)&Departmentally both |
| 7 | Thorough Over hauling,Checking, cleaning and testing of SIEMENS make LT AIR CIRCUIT BREAKER | External agency(Siemens) |
| 8 | Thorough Over hauling,Checking, cleaning and testing of L&T makeAIR CIRCUIT BREAKER | External agency(L&T) |
| 9 | Thorough Over hauling,Checking, cleaning and testing of SIEMENS make 6.6 KV vacuum circuit breaker (ER Trafo breaker)and 4 nos. spare vacuum contactor feeder. | External agency(Siemens) |
| 10 | Retrofitting, commissioning and testing of L&T make ACB, rating 4000A CN-CS for PCC Incomer-B and Bus coupler -BCat Utility S/S | External agency(L&T) |
| 11 | Testing of selected relays installed in the 6.6 KV switchgear panel , PCC and emergency MCC panel. Thorough scheme checking of new emergency MCC. | External agency(Power System) |
| 12 | Commissioning of new Emergency MCC . All power and control cable shifting from existing MCC-2A , termination, feeder testing, DOR etc. at Utility. | Departmentally |
| 13 | Preventive Maintenance of MCCs ( Siemens Compressor MCC, MCC-2B, Old DM plant MCC, Raw water MCC, and Conv.MCC at Utility . De-dusting, Bus bar tightness checking, all power cable/lead, control connection tightness checking and motor feeders healthyness checking etc. | Departmentally |
| 14 | O/H of DM Water Transfer Pump Motor 101A, 110KW,1500RPM | Departmentally |
| 15 | O/H of Air Compressor Motor 102A, 150KW,1500RPM | Departmentally |

D.	SAP

| Sl. | Jobs are Carried Out | Jobs Carried Out By |
| --- | --- | --- |
| 1 | Maintenance of 33 KV switchgear |  |
|  | Dedusting,Busbar tightness checking,sealing of panels,spaceheater checking,Breaker healthyness checking,Testing of closing, tripping & interlocking Ckt. Preventive maintenance of Breaker | Departmentally |
| 2 | Maintenance of PCC |  |
|  | Dedusting,Busbar tightness checking,checking of cluster contacts & fixed contacts of ACB.Sealing of panels,spaceheater checking,Breaker healthyness checking,Testing of closing,tripping & interlocking Ckt. | Departmentally |
|  | Overhauling ,realignment of ACB in breaker compartment & Retrofitting of Incomer & Out going to MCC Breakers | GE & L&T TEAM |
| 3 | Maintenance of MCC#10A, MCC#10B, MCC#10C, MCC#10D, MCC#10E,MCC#10F, MCC#11, MCC#12, L&T MCC |  |
|  | Dedusting,Busbar tightness checking,sealing of panels,spaceheater checking,checking of all switchgear componets installed.Testing of closing,tripping Ckt. | Departmentally |
| 4 | Maintenance of Transformer (TR # 13,14,15,16) |  |
|  | Major overhouling of transformers for Trf#13 & Trf#15 are caaried out. Inspection of HT & LT chamber, checking of bushing, arrest of oil leakage, sealing of terminal box & marshalling box, relay & alarm contacts checking, checking of Temp. Indicator. Replacement of broken hinges & damaged connectors inside Marshalling box. | Departmentally/ External egency |
|  | Busduct Cleaning & repair/replacement of damaged MS sheet to be done. | External Agency |
| 5 | Maintenance of Charger & DCDB panel. |  |
|  | Dedusting,checking of Charger & battery bank,checking of relay & alarm contacts. | Departmentally |
| 6 | Maintenance of VFD Panel. |  |
|  | Dedusting,tightness checking of Power ckt.,checking& cleaning of VFD cooling fan, All parameters & control ckt. checking. | Departmentally |
| 7 | Additional Busbar arrangement for chargeing INCOMER -2 of the new MCC #11& MCC#12 | External Agency/Deptt |
| 8 | Maintenance of MOVs |  |
|  | Checking of operation & limit switches of Train-2 all actuators . Train-1 IGV faulty card is replaced & commissioned. | Departmentally & External Agency |
| 9 | HT Motor Overhauling BFW 101S ,101B . |  |
|  | overhauling,cleaning of cooling ducts. | Departmentally & External Agency |

E.	Boiler and CHP

| Sl. | Type Of Maintenance Jobs Carried Out |
| --- | --- |
| 1 | Installation, Testing of PLC |
|  | Laying of Cables between PLC panel & Individual switchgear |
|  | Glanding Termination of Cables at both end |
|  | Fixing of contactors for contact multiplication |
| 2 | 6.6KV Switchgear |
|  | 6.6KV Bus Section-A Brkr. chambers Cleaning, Tightness Checking, Control Checking etc. |
|  | 6.6KV Bus Section-A all Brkr. trolley Cleaning, mechanism inspection, close/trip checking etc. |
|  | 6.6KV Bus Section-B Brkr. chambers Cleaning, Tightness Checking, Control Checking etc. |
|  | 6.6KV Bus Section-B all Brkr. trolley Cleaning, mechanism inspection, close/trip checking etc. |
|  | 6.6KV Bus Coupler Brk. chambers Cleaning, Tightness Checking, Control Checking etc. |
|  | 6.6KV Bus Coupler Brk. trolley Cleaning, mechanism inspection, close/trip checking etc. |
| 3 | Boiler PCC |
|  | PCC Bus Section-A Busbar Cleaning, Tightness Checking, Control Checking etc. |
|  | PCC Bus Section-B Busbar Cleaning, Tightness Checking, Control Checking etc. |
|  | PCC Bus Section-C Busbar Cleaning, Tightness Checking, Control Checking etc. |
|  | PCC Bus Section-D Busbar Cleaning, Tightness Checking, Control Checking etc. |
|  | PCC Bus Couplers Busbar Cleaning, Tightness Checking, Control Checking etc. |
|  | PCC I/C-A,B,C,D Cleaning, mechanism inspection, close/trip checking etc. |
|  | PCC all O/G feeder Cleaning, mechanism inspection, close/trip checking etc. |
| 4 | Boiler MCC |
|  | Busbar Cleaning, Tightness Checking, Control Checking etc. |
|  | All Feeder Cleaning, Tightness Checking, Control & Logic Checking etc. |
|  | Current readings of PA fans shall be given at DCS |
| 5 | New L&T Emergency MCC : |
|  | Busbar Cleaning, Tightness Checking, Control Checking etc. |
|  | All Feeder Cleaning, Tightness Checking, Control & Logic Checking etc. |
| 6 | New MLDB at Boiler |
|  | Installation of new MLDB at Boiler S/S |
|  | Laying & Termination of I/C-A cable at PCC 2F3 and taking in to line |
|  | Laying & Termination of I/C-B cable through 60kva transformer |
|  | Laying & Termination of I/C-B cable through 100kva transformer |
|  | Charging of MLDB after testing. |
|  | Laing of cable for 24V 1ph. Powersupply according to the scheme |
|  | Laing of cable for 240V 1ph. Power supply according to the scheme |
|  | Installation of new Junction box & FRP Scckets as per scheme |
|  | Termination of cable at both end and taking in to line |
|  | Shifting existing cables from old panel to the new MLDB |
| 7 | New MLDB at CHP |
|  | Installation of new MLDB at CHP S/S |
|  | Laying of Cables for I/C-A of MLDB, glanding & termination |
|  | Laying of Cables for I/C-B of MLDB, glanding & termination |
|  | Charging of MLDB after testing. |
|  | Laing of cable for 24V 1ph. Power supply according to the scheme |
|  | Laing of cable for 240V 1ph. Power supply according to the scheme |
|  | Shifting existing cables from old panel to the new MLDB |
| 8 | New MCC for Motorized Actuator of Dampers at Boiler-1 &2 |
|  | Installation of New MCC for Motorized Actuator of Dampers at Boiler-1 &2 |
|  | Laying of 3.5Cx300mm2 AL Cable for I/C from PCC 1F2, glanding & termination |
|  | Laying of Power & Control cable ID-2A Damper Motorized Actuator & fixing of LCS, glanding & termination. |
|  | Laying of Power & Control cable ID-2B Damper Motorized Actuator & fixing of LCS, glanding & termination. |
|  | Laying of Power & Control cable FD-2A Damper Motorized Actuator & fixing of LCS, glanding & termination. |
|  | Laying of Power & Control cable FD-2B Damper Motorized Actuator & fixing of LCS, glanding & termination. |
|  | Laying of Power & Control cable PA-2A Damper Motorized Actuator & fixing of LCS, glanding & termination. |
|  | Laying of Power & Control cable PA-2B Damper Motorized Actuator & fixing of LCS, glanding & termination. |
|  | Laying of Power & Control cable PA-1A Damper Motorized Actuator & fixing of LCS, glanding & termination. |
|  | Laying of Power & Control cable PA-1B Damper Motorized Actuator & fixing of LCS, glanding & termination. |
|  | Laying of Power & Control cable CBD Boiler-2 Motorized Actuator & fixing of LCS, glanding & termination. |
|  | Laying of Power & Control cable IBD Boiler-2 Motorized Actuator & fixing of LCS, glanding & termination. |
|  | Laying of Power & Control cable IBD Boiler-1 Motorized Actuator & fixing of LCS, glanding & termination. |
| 9 | Overhauling of H.T. & L.T. Motors :- |
|  | Removing, Overhauling & fixing back of ID-1A Motor |
|  | Removing, Overhauling & fixing back of ID-1B Motor |
|  | Removing, Overhauling & fixing back of FD-1A Motor |
|  | Removing, Overhauling & fixing back of FD-1B Motor |
|  | Removing, Overhauling & fixing back of PA-1A Motor |
|  | Removing, Overhauling & fixing back of PA-1B Motor |
|  | Removing, Overhauling & fixing back of ID-2A Motor |
|  | Removing, Overhauling & fixing back of ID-2B Motor |
|  | Removing, Overhauling & fixing back of FD-2A Motor |
|  | Removing, Overhauling & fixing back of FD-2B Motor |
|  | Removing, Overhauling & fixing back of PA-2A Motor |
|  | Removing, Overhauling & fixing back of PA-2B Motor |
|  | Removing, Overhauling & fixing back of BFW-A Motor |
|  | Removing, Overhauling & fixing back of BFW-B Motor |
|  | Removing, Overhauling & fixing back of BFW-C Motor |
|  | Replacement of C-4 Conveyor Motor of Boiler |
|  | Replacement of C-5 Conveyor Motor of Boiler |
|  | Replacement of C-6 Conveyor Motor of Boiler |
|  | Replacement of C-7 Conveyor Motor of Boiler |
|  | Replacement of RF Trolly Motor of Boiler |
|  | Replacement of RBFD Motor of Boiler |
|  | Replacement of NBC-6 Conveyor Motor of Boiler |
|  | Replacement of NBC-5 Conveyor Motor of Boiler |
|  | Checking by installation of a 110KW ABB motor in place of SIEMENS motor for any one of PA fan |
| 10 | ESP Boiler-1 &2 :- |
|  | Cleaning & Maintenance of Boiler-1 ESP support insulators & shaft insulators, Installation of new sp. Heatrs in isolator box. |
|  | Cleaning & Maintenance of Boiler-2 ESP support insulators & shaft insulators, Installation of new sp. Heaters in isolator box. |
| 11 | Battery Charger & Battery Banks :- |
|  | Cleaning of 110V Battery Charger, Its Battery Bank at Boiler & CHP & checking of sp. Gravity. |
| 12 | ESP Control room :- |
|  | Cleaning of all six controller panels of Boiler-1&2 ESP |
|  | Cleaning of both MCC panels of Boiler-1&2 ESP |
| 13 | Substation, MCC Room & Control Room :- |
|  | Cleaning of DCF panels |
| 14 | Motorized Actuators of Boiler :- |
|  | Complete maintenance of Boiler-1 MSSV-A actuator (Rotork make) |
|  | Complete maintenance of Boiler-1 MSSV-B actuator (Rotork make) |
|  | Complete maintenance of Boiler-1 Feed Water 30% I/L actuator (Rotork make) |
|  | Complete maintenance of Boiler-1 Feed Water 30% O/L actuator (Rotork make) |
|  | Complete maintenance of Boiler-1 Feed Water 100% I/L actuator (Rotork make) |
|  | Complete maintenance of Boiler-1 Feed Water 100% O/L actuator (Rotork make) |
|  | Complete maintenance of Boiler-1 Spray Control Valve I/L actuator (Rotork make) |
|  | Complete maintenance of Boiler-1 Spray Control Valve O/L actuator (Rotork make) |
|  | Complete maintenance of Boiler-2 MSSV-A actuator (Rotork make) |
|  | Complete maintenance of Boiler-2 MSSV-B actuator (Rotork make) |
|  | Complete maintenance of Boiler-2 Feed Water 30% I/L actuator (Rotork make) |
|  | Complete maintenance of Boiler-2 Feed Water 30% O/L actuator (Rotork make) |
|  | Complete maintenance of Boiler-2 Feed Water 100% I/L actuator (Rotork make) |
|  | Complete maintenance of Boiler-2 Feed Water 100% O/L actuator (Rotork make) |
|  | Complete maintenance of Boiler-2 Spray Control Valve I/L actuator (Rotork make) |
|  | Complete maintenance of Boiler-2 Spray Control Valve O/L actuator (Rotork make) |
|  | Complete maintenance of SAP-1 Main Steam Vent Valve actuator (Rotork make) |
|  | Complete maintenance of SAP-2 Main Steam Vent Valve actuator (Rotork make) |
|  | Commissioning of CBD-1 Actuator for Boiler-1(Rotork Make) |
|  | Commissioning of CBD-2 Actuator for Boiler-2(Rotork Make) |
|  | Commissioning of CBD-2 Actuator for Boiler-2(Rotork Make) |
|  | Complete maintenance of Boiler-1 Main Steam Vent Valve actuator (Auma make) |
|  | Complete maintenance of Boiler-2 Main Steam Vent Valve actuator (Auma make) |
|  | Commissioning of Damper Actuator for Boiler-2 FD-2A (Auma Make) |
|  | Commissioning of Damper Actuator for Boiler-2 ID-2A (Auma Make) |
|  | Commissioning of Damper Actuator for Boiler-2 ID-2B (Auma Make) |
|  | Commissioning of Damper Actuator for Boiler-2 PA-2A (Auma Make) |
|  | Commissioning of Damper Actuator for Boiler-2 PA-2B (Auma Make) |
|  | Commissioning of Damper Actuator for Boiler-1 PA-1A (Auma Make) |
|  | Commissioning of Damper Actuator for Boiler-1 PA-1B (Auma Make) |

F.	Bagging

| 1.0 | Maintenance of MCC-34,MCC-35, MCC-36, MCC-37, MCC-38,MCC-39, PH MCC |
| --- | --- |
|  | Job Includes: Dedusting, Busbar tightness checking, sealing of panels, spaceheater checking, Module healthyness checking.Interlocking of control ckt checking |
| 2.0 | MAINTENANCE OF PDB-01no, MLDB-02 NOS, |
|  | Dedusting, Busbar tightness checking, sealing of panels.SFU healthyness checking. |
| 3.0 | LT Motor Overhauling .(Annexure of motor list attached) |
|  | Dismantling from site, shifting to W/Shop, overhauling, shifting back to site, Termination & DOR checking. |
|  | 70 A,B,C conveyors( 18.5 KW) – 03 nos 101,102,104 conveyors( 18.5 kw)-- 03 nos 107,108 conveyors (30 kw ) – 02 nos 130,132 conveyors ( 75 kw) – 02 nos. 201,202 conveyors ( 22kw) – 02 nos 203,204 conveyors ( 22 kw)-- 02 no |
| 4. | Pull chord switch, Belt sway switch & zero speed switch maintenance of conveyors. |
|  | 101,102,104,107,108,111A,113A,130,132,201,202,203,204.& Portable conveyors. |
| 5. | MAINTENANCE OF TRIPPER & TRIPPER PANNEL.203 204 Conveyors |
|  | Dedusting, Busbar tightness checking, sealing of panels.SFU healthyness checking. |

G.	PAP

| SL.NO. | SWITCH GEAR/PMCC/MCC |
| --- | --- |
| 1 | B/M-A,B,C,D PLC PANELS |
|  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking, SFU healthiness checking, Testing of interlocking Ckt. Were done. |
| 2 | B/M-D MCC & NEW EM.MCC |
|  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking, Breaker healthiness checking, Testing of closing, tripping & interlocking Ckt. Were done. |
| 3 | 6.6 KV SEC-A, S/S-6 |
|  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking, VCB ad VC healthiness checking, Testing of closing, tripping & interlocking Ckt. Were done. |
| 4 | 6.6 KV SEC-B, S/S-6 |
|  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking, VCB and VC healthiness checking, Testing of closing, tripping & interlocking Ckt. Were done. |
| 5 | 33 KV SEC-A & MCC-20 |
|  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking, Breaker healthiness checking, Testing of closing, tripping & interlocking Ckt. Were done. |
| 6 | 33 KV SEC-B & MCC-21 |
|  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking,Breaker healthiness checking, Testing of closing, tripping & interlocking Ckt. Were done. |
| 7 | A/S MCC & MCC-23 |
|  | De-dusting, Busbar tightness checking, Sealing of panels, Space heater checking, Breaker healthiness checking, Testing of closing, tripping & interlocking Ckt. Were done |
| 8 | SIEMENS PANEL (OCHP) |
|  | De-dusting, Busbar tightness checking, Sealing of panels, Space heater checking, Breaker healthiness checking, Testing of closing, tripping & interlocking Ckt. Were done. |
| 9 | VCB CLEANING AT S/S-5 |
|  | De-dusting, Breaker healthiness checking, Testing of closing & tripping Ckt. Were done. |
| 10 | VCB CLEANING AT S/S-6 |
|  | De-dusting, Breaker healthiness checking, Testing of closing & tripping Ckt. Were done. |
| 11 | Motors Over hauling |
|  | 20-01-310C Evaporator circulation pump 20-05-114 Reactor agitator-04 20-01-624 Cold well pump 20-01-625 Cold well pump 20-01-617 Hot well pump 20-01-383 Cooling water transfer pump 20-01-291 Gypsum pump 20-05-120 Reactor agitator 20-05-130 Reactor agitator 20-05-030 SST agitator 20-22-210A Belt filter-A 20-22-210B Belt filter-B 20-22-210C Belt filter-C 20-22-210D Belt filter-D 20-22-210E Belt filter-E 20-22-210F Belt filter-F 20-01-022A Screen feed pump 201-M-104 M-104 conveyer 20-01-415 Evaporator feed pump |

H.	Port and Conveyor

| 1.0 | 6.6KV SWITCH GEAR MAINTENANCE |
| --- | --- |
| 1.1 | 6.6KV Bus Section-A Brkr. chambers Cleaning, Tightness Checking, Control Checking etc done. |
| 1.2 | 6.6KV Bus Section-A all Brkr. trolley Cleaning, mechanism inspection, close/trip checking etc. |
| 2.0 | 6.6KV SWITCH GEAR BUSCOUPLERS |
| 2.1 | 6.6KV Bus Coupler Breaker chambers Cleaning, Tightness Checking, Control Checking etc. |
| 2.2 | 6.6KV Bus Coupler Breaker trolley Cleaning, mechanism inspection, close/trip checking etc. |
| 3.0 | MCC Maintenance – Un loader -1,2, Lighting and main MCC. |
| 3.1 | All MCCs out surface, rubber mat cleaning done. |
| 3.2 | Busbar Cleaning, Busbar bolt Tightness carried out. |
| 3.3 | Breakers mechanism and control checking done. |
| 3.4 | All Feeder Cleaning, Tightness Checking, Control & Logic Checking done. |
| 4.0 | Unloader Drive Maintenance. |
| 4.1 | All surface, rubber mat cleaning done. |
| 4.2 | Busbar Cleaning, Busbar bolt Tightness carried out. |
| 4.3 | Breakers mechanism and control checking done. |
| 4.4 | All Drives Feeder Cleaning, Tightness, and control Checking done |
| 5.0 | PDBs and LDB Maintenance |
| 5.1 | Maintenance of All the PDBs and LDBs is done. |
| 6.0 | Transformers Maintenance. |
| 6.1 | Cleaning of 6.6/0.415 KV Transformer done. |
| 7.0 | Maintenance of Motors |
| 7.1 | R1 and R2 motor cleaning and Fan cleaning done. |
| 7.2 | All Un loader DC motors, Carbun brush checking and replacement done. |
| 8.0 | Cable Reeling Drum maintenance |
| 8.1 | Drum rollers greasing and maintenance done. |
| 9.0 | Conveyor safety equipment maintenance |
| 9.1 | All conveyors damaged Pull chord is replaced, switches replaced/ maintenance done. |
| 9.2 | Conveyor hooters checking done |
| 10.0 | Installation of 630A Load break switch for Screw Unloader |