PREFACE

The annual plant turnaround for the year 2014 was taken form 28 th March 2015, for carrying out preventive maintenance of static and rotary equipments, statutory IBR inspection, Preventive maintenance of Electrical  and instrument systems, Civil related jobs and for attending jobs which were pending for shut down.

After ensuring the availability of all the required material for shutdown and awarding contracts for various shut down jobs. It was decided to stop the plants as per the following.

Plant			            	Stopped on 				Started on

DAP Train A 			:	28/03/2015				17/04/2015

DAP Train B 			: 	28/03/2015				19/04/2015

DAP Train C 			: 	28/03/2015				17/04/2015

PAP 				: 	28/03/2015				16/04/2015

SAP Train 1			: 	05/03/2015				08/06/2015

SAP Train 2			: 	28/03/2015				18/04/2015

Energy center		: 	29/03/2015				14/04/2015

AFBC Boiler  	1		: 	29/03/2015				12/04/2015

AFBC Boiler  	1		:	28/03/2015				16/04/2015

The Turnaround was carried out smoothly due to meticulous planning of all activities like planning of man power, material and other resources. Due to exemplary efforts put in by all personnel at all levels, turnaround jobs could be completed in the scheduled period.

Safety was one of the major aspects, which was given top most priority during the execution of various jobs. Necessary training for safe working in the plant was given to the manpower employed by all contractors and strict vigilance was kept by fire and safety section during execution of shut down works. All The jobs were carried out considering all safety aspects and the use of safety equipments was ensured during execution of jobs.

The shutdown report contains plant wise and section wise details of jobs carried out.

INDEX

- DAP							:	4	-   	45

TRAIN A, B & C

ELECTRICAL

INSTRUMENTATION

- PHOSPHORIC ACID PLANT 			:	46	 -   	96

PHOSPHORIC ACID PLANT

ELECTRICAL

INSTRUMENTATION

- SULPHURIC ACID PLANT				:	97	 -       195

SULPHURIC ACID PLANT

ELECTRICAL

INSTRUMENTATION

- OFFSITES AND UTILITY				:	196	 -        217

DM PLANT

ELECTRICAL

INSTRUMENTATION

- SGPG							:	218     -        324

ENERGY CENTER

ELECTRICAL

INSTRUMENTATION

AFBC BOILER

ELECTRICAL

INSTRUMENTATION

- GENERAL ENGINEERING				:	325	  -       330

- CIVIL							:	331	  -       334

- BAGGING PLANT					:	335	 -	340

DAP TR A

| Dust & Fumes Fan | motor |  | Motor overhauled |
| --- | --- | --- | --- |
|  | impeller | cleaned | Impeller sand blasting & balancing |
|  | casing | cleaned | Casing repaired, rubber lining |
|  | Discharge bellow | cleaned | New bellow fixed. |
| Dryer exhaust fan | Motor |  | Motor overhauled |
|  | Impeller | cleaned | Impeller sand blasting & balancing |
|  | Casing | cleaned | Casing repaired, rubber lining |
|  | Discharge bellow |  | New bellow fixed |
| Pre scrubber Tank | Tank | Tank inside cleaned. | No work |
|  | Tower | Tower top/bottom /down comer cleaning & de-scaling done, all nozzles cleaned. | No work |
|  | Separator | Separator top portion, conical portion and down comer line cleaning, de-scaling done, all nozzles cleaned. | No work |
| Primary Scrubber Tank | Tank | Inside cleaning & de-scaling done. | No work |
|  | Agitator |  |  |
|  | Dryer seperator | Its conical portion, down comer line cleaning done. De-scaling job completed, all nozzles cleaned. | No work |
|  | Dryer venturi | Venturi side cleaning done and its down comer line cleaning done, all nozzles cleaned. Ring header cleaned. | Bellow replaced. |
|  | Dryer duct | Outlet duct cleaning done | No work |
|  | Dust & Fumes separator | Cleaned & de-scalled, all nozzles cleaned. | Around 3 meters Shell plate replaced. |
|  | Dust & Fumes venturi | Ring header cleaned. All nozzles cleaned, shell de-scalling & cleaned. | No work |
|  | Dust & Fumes duct | Outlet duct cleaning done | In let duct 2 bellows replaced. |
| Tail Gas Scrubber | tank | Inside cleaning done and stack grizzly cleaning done | No work |
|  | TG common duct | Inside cleaned. All nozzles cleaned. | Joint DP test & welding done. |
|  | TG nozzles header | cleaned | No work |
| Primary elevator | Boot area | Boot cleaned | no work |
|  | Immediate discharge | Cleaned. Over size screen outlet cleaned. | Immediate discharge patched up. |
|  | Drive unit | Drive unit platform cleaning done. | Motor Over hauled. Gear box oil seal replaced, fluid coupling replaced. |
|  | De-dusting | cleaned | No work |
|  | Buckets | No work | No work |
| Secondary elevator | Boot area | Boot cleaned | Boot door repaired and side door replaced. |
|  | Drive unit | Drive unit area cleaned | Motor Over hauled |
|  | De-dusting |  |  |
|  | buckets | Bucket cleaned & water washing done. | Damaged Bucket replaced. |
|  | discharge | Discharge cleaned. | No work |
| Product screen elevator | Boot area | Cleaned | Door repaired. |
|  | Drive unit | cleaned. | Motor over hauled. |
|  | discharge | cleaned | No work |
|  | bucket |  | Damaged Bucket replaced. |
|  | Screen outlet & hopper | Cleaned. | No work. |
| Prod Elevator | Drive unit | Cleaned. | Motor over hauled . |
|  | discharge | Cleaned | No work |
|  | Buckets |  | Damaged Bucket replaced. |
| Granulator | Drive unit | Cleaned & its Platform cleaned | Motor over hauled. Pinion replaced & its Structure strengthening done. |
|  | Rubber panel | Cleaned & Water washing done | 4 panels replaced. |
|  | Slurry header | cleaned | No work. |
|  | sparger |  | Gap made uniform. |
| Dryer | Drive unit | Area Cleaned | Motor over hauled. |
|  | Inside | Deduct cleaning done. Inside cleaned & water washing done (flights) . | Discharge damaged grizzle bar 6 number replaced. |
| Preneutraliser | Tank inside | Cleaned | Pesting & chipping( civil) |
|  | Ammonia spargers | cleaned | No work |
|  | Duct | Cleaned & water washed | Only 5% shell patched up rest left as it is. |
|  | Sulfuric acid line |  | Damaged portion replaced. |
| Fines Conveyor | Deck area | Cleaning done | Canopy cut at tail end portion. |
|  | idller | Idler area cleaning done | Damaged structure & frame repaired. |
|  | Hot air line |  | No work |
|  | Counter weight | Cleaning done | No work |
|  | Discharge | Cleaned | No work |
| 70 CONVEYOR | Floor and structure | Cleaning and water washing done | Painting done. |
|  | Belt |  | Belt replaced. |
|  | Tailend deck | cleaned | Painting done. |
| RM CONVEYOR | Belt & Grizzly | Hopper grizzly cleaning done | Belt replaced & Grizzly repaired. |
|  | Tail end | Cleaning done | No work |
|  | motor | Motor area cleaning done | Motor over hauled. |
| Combustion chamber | Diffuser box | Inside oil and clinker removed | No work |
|  | inside | Cleaned done | Brick lining pesting & chipping ( civil) |
|  | gun |  | cleaned |
|  | dampers | Cleaning is done | Made free. |
| DDC | belt |  | replaced |
|  | Inlet & out let chute | cleaned | No work |
|  | idlers | cleaned | No work |
|  | floor | cleaned | Floor grating repaired. |
| Chain mills | motor | Area cleaned | 12-A1 motor replaced |
|  | rotor |  | 11A2 & 14A2 replaced |
|  | Balancing line |  | Provided. |
| 81 pump & 82 pump. |  | Suction & discharge cleaned | Suction modified, base modified( civil),motor over hauled. |
| 41 & 42 pumps |  | Suction & discharge cleaned | No work |
| 51 ,52,53 pumps |  | Suction & discharge line cleaned. | Only 52 pump motor replaced. |
| 61,62 & 63 pumps |  | Suction & discharge line cleaned | Discharge NRV replaced. |
| 21 & 22 pumps |  | Suction & discharge line cleaned | No work |

DAP TR-A(Mech): 28.03.2015 TO 16.04.2015

01. GRANULATOR

- Support roller bearing clearance checking & lubrication.

- Granulator alignment, skewing of support roller done.

- Pinion to girth gear root clearance, back lash & blue matching done.

- Torque tube inspection, lubrication done

- Leveling, alignment of drive side, Two nos EPDM panel Replaced.

- Torque tube coupling replaced.

02. DRYER

- Support roller bearing clearance checking & lubrication.

- Dryer alignment, skewing of support roller done.

- Pinion to girth gear root clearance, back lash & blue matching done.

- Girth gear inspection & health check up.

- Torque tube inspection, lubrication done, Leveling , alignment of drive side.

- Drive pinion replaced.

03. CHAINMILL

- All chainmill liner inspection & overhauling done.

- Chainmill inlet & discharge chute repairing & replacement done.

04. ELEVATOR

- All elevator chain link, pin, bucket inspected & damaged buckets were replaced.

- All elevator head shaft bearing insp/lubrication done.

- The counter weight box was aligned properly with respect to guide channels and was welded properly.

- The tail shaft assembly and CI block was replaced and aligned.

05. FINES CONVEYOR

- Head pulley & foundation frame replaced.

- All pulley bearing insp/lubrication done

- Carrying & return idler with frame replaced.

- Coupling bolt insp/replaced.

- G.B. oil replacement done.

6.    Conveyor Belt replacement done.

7.   Plain Tail pulley replaced in place of Wing pulley.

06. SCRUBBER AREA JOB:

- Dust & Fumes separator full shell plate course replaced with new plate.

- Prescrubber shell patch work done.

- PN to Pre duct fabrication & erection.

- TG scrubber metal lining inspection & welding done.

07.  CHAMBER

- Comb chamber shell assembly with wind box patch work done.

08.  RM CONVEYOR

- Conveyor structure strengthening done.

- Feeding hopper & grizzly replacement done.

09.  70 CONVEYOR

- Gearbox inspection & overhauling done

- All bearing s of pulley insp/lubrication done.

- Gear coupling inspection/lubrication done.

- Idlers with frame replacement as per requirement

10.  DDC CONVEYOR

- Structure strengthening done.

- DDC conveyor structure revamped.

- Gearbox oil replacement & coupling bolt with bearing inspection /lubrication done.

- Conveyor Belt replaced.

11.  FANS

- All fan bearing inspection & lubrication done.

- Casing repairing with rubber lining done.

- Dust & Fumes  and Dryer exhaust fan casing rubber lining done.

12. SCREENS

- All oversize & product screen mesh repairing/replacement done.

- Tensioning rail & optimizer tensioning kit replaced in Oversize & product screens.

13. STEAM AIR HEATER

1. Steam air heater coil cleaning done .

DAP TR B

| Fumes Fan | motor |  |  | Motor opened and sent to work shop and fixed. | Motor overhauled at workshop. |
| --- | --- | --- | --- | --- | --- |
|  | impeller |  |  | Impeller opened, sand blasting and balancing job done. |  |
|  | casing | Casing inside thoroughly cleaned. FAN inlet duct also cleaned. |  | Rubber lining job done. |  |
|  | Damper |  |  | New Damper fixed, |  |
| Dryer exhaust fan | Motor |  |  | Motor opened and sent to work shop and fixed. | Motor overhauled at workshop. |
|  | Impeller |  |  | Impeller opened, sand blasting and balancing job done, |  |
|  | Casing | Casing inside thoroughly cleaned. FAN inlet duct also cleaned. |  | Rubber lining job done. |  |
|  | Damper |  |  | New Damper fixed, |  |
| Dust fan |  | Dust duct cleaning done towards fan side. |  | New fan impeller and casing installed. Discharge chute also fabricated to fix with old discharge chute. | New motor of capacity 0.4 mw installed. |
| Pre scrubber Tank | Tank | Tank inside, pumps suction and agitator blade completely descaled. |  | 42 pump casing leak arrested. | Agitator motor job taken. |
|  | Tower | Tower top/bottom /down comer cleaning & de scaling done |  |  |  |
|  | Separator | Separator top portion, conical portion and down comer line cleaning, de scaling done |  |  |  |
| Primary Scrubber Tank | Tank | Tank inside, pumps suction and agitator blade completely descaled. |  | Tank manhole boxed up. | Agitator Motor to be provided |
|  | Agitator |  |  | Agitator platform strengthening job done. |  |
|  | Dryer separator | Its conical portion, down comer line de-scaled. Seperator header line cleaned |  | Separator inside patch up and rubber line job done |  |
|  | Dryer venturi | Venture side cleaning done and its down comer line cleaning done. Ring header cleaned. |  | Venture side umbrella positioned. Bellow replaced. Ring header boxed up |  |
|  | Dryer duct | Outlet duct cleaning done |  |  |  |
|  | Fumes Separator | Cleaning done. Separator nozzle header line cleaned. |  |  |  |
|  | 50 series | Discharge line cleaned. |  | . |  |
|  | Fumes venturi | Cleaning done. Separator nozzle header line cleaned. Ring header cleaned |  | Venture damaged nozzle connecting pipes replaced. |  |
|  | Fumes duct | Outlet duct cleaning done |  | Top doors boxed up |  |
|  | Dust duct | Inlet and outlet cleaned |  | Inlet duct bellow replaced |  |
| Tail Gas Scrubber | Separator tank | Inside cleaning done and stack grizzly cleaning done |  | stack door boxed up. |  |
|  | TG common duct | Inside cleaning done. All fan outlet duct area cleaning done. |  | SS plate joint DP check and corresponding welding job done. |  |
|  | 60 series | Suction and discharge line cleaning done |  | Lines boxed up. 61 & 63 NRV replacement not done. | No job taken. |
|  | TG nozzles header | Lower nozzles cleaned |  |  | Main /bypass valve servicing done |
| Primary elevator | Boot area | Boot area cleaned |  | New CI block fixed. Repaired door fixed. |  |
|  | Discharge | Cleaning done. Over size screen outlet cleaning to be done. |  | Only one plate of 2.5’’*2.5’’ replaced at immediate and oversize inlets( all four) replaced. |  |
|  | Drive unit | Drive unit platform cleaning done. |  |  |  |
|  | Motor |  |  |  | Motor overhauled. |
|  | De-dusting | Hood cleaned. |  | New erected line fixed. |  |
|  | Buckets |  |  | No job taken. |  |
| Secondary elevator | Boot area | Boot area cleaned |  | C.I block replacement done. New door fixed. |  |
|  | Drive unit | Drive unit area cleaned |  |  | Motor overhauled. |
|  | Dedusting |  |  | Line connected |  |
|  | buckets | Bucket water washing done. |  |  |  |
|  | Discharge | Discharge cleaned . |  |  |  |
|  | Dedusting |  |  | De-dusting line Refixed. |  |
| Product screen elevator | Boot area | Cleaning done |  | Side and boot door fixed (new one) |  |
|  | Drive unit | Area cleaning done. |  |  | Motor overhauled . |
|  | Discharge | Immediate discharge cleaned |  | New discharge line as like train C installed. |  |
|  | Bucket |  |  |  |  |
|  | dedusting |  |  | Line fixed |  |
|  | Screen outlet & hopper | Cleaning done. |  | 6 nos product screen mesh replaced. |  |
| Prod Elevator | Drive unit | Area cleaning done |  | Bearing greasing done. Coupling & gearbox oil filled. | Motor overhauled |
|  | discharge | Cleaning done |  | De-dusting re fixed. |  |
|  | Dedusting |  |  | Line erection job started. |  |
|  | Buckets |  |  |  |  |
| Granulator | Drive unit | Platform cleaned | Lube oil tank emptied and filters cleaned. Motor opened for overhauling and refixed |  | Motor overhauled . |
|  | Rubber pannel | Water washing done | 14 pannels fixed and new strip replaced. |  |  |
|  | Slurry header | cleaned | Header line with it’s new beam replaced. |  |  |
|  | Sparger |  | New fabricated sparger fixed. |  |  |
|  | Lube oil pumps |  |  |  |  |
|  | 21,22 main and recycle,Slurry actuator and valve body |  | Removed, servicing done and fixed. Slurry line elbow repairing done. |  |  |
| Dryer | Drive unit | Cleaning done, dryer outer shell cleaned by steam flushing | Motor opened for overhauling and re-fixed |  | Motor overhauled |
|  | Spring plate |  | 4 spring plate changed. |  |  |
|  | Inside | Deduct cleaning done. Inside water washing done (flights) |  |  |  |
|  | Support roller |  | Roller alignment done, tyre support ring replaced. |  |  |
|  | Lube oil pumps |  | Filters cleaned. Gearbox oil replaced. |  |  |
| Pre neutraliser | Tank inside | Cleaning done Damaged Brick linning repaired | Manhole boxed up. |  |  |
|  | Ammonia spargers |  | Nozzle direction 1, 4, 5 changed. Missing mouthpiece re-fixed. |  |  |
|  | Agitator |  |  |  |  |
|  | Slurry pump |  | 22 suction valve is opened and checked and re-fixed. |  |  |
|  | Sulfuric acid blow leg |  |  |  |  |
| Fines Conveyor | Deck area | Cleaning done | Chain mill hopper 13,14 new one fixed. 11 no hopper plate fixed. |  |  |
|  | Motor |  |  |  | Motor overhauled |
|  | idler | Idler area cleaning done | New belt positioned. Vulcanization done. |  |  |
|  | Counter weight | Cleaning done. | Counter weight Tr c side bearing changed and positioned |  |  |
|  | Tail end | Cleaning done | Tail pulley replaced. |  |  |
|  | Discharge | Cleaned |  |  |  |
| 70 CONVEYOR | Floor and structure | Cleaning and water washing done | Painting done. Structure angle fixed. |  |  |
|  | Belt |  | Belt replaced. |  |  |
|  | Motor |  |  |  | Motor overhauled |
|  | Tail end deck | cleaned |  |  |  |
| DDC |  | Floor cleaned. | Belt replacement done. |  | Motor overhauled |
| RM CONVEYOR | Grizzly | Hopper grizzly cleaning done. | New Grizzly provided. Head pulley hood area modified |  | Motor fixed. Termination and DOR checked. |
|  | Tail end | Cleaning in progress | Idler frame repaired and hopper repaired. |  |  |
|  | Motor | Motor area cleaned |  |  | Motor overhauled |
| Combustion chamber | Diffuser box | Inside oil and clinker removed. Damage of shell | Damaged pipe Replacement done (new one fixed). Gun fixed. |  |  |
|  | Inside | Clinker and damaged brick lining cleaned | Brick lining job done by civil dept. |  |  |
|  | gun |  | Gun fixed after fabrication |  |  |
|  | dampers | Cleaning done. | Comb & Quench damper opened and fixed . |  | Actuator to be fixed for damper operation (inst maint). |
| 11 No chain mill |  | cleaned | Hopper plate replaced, welding done |  |  |
| 12 No chain mill |  | cleaned | Hopper plate replaced |  |  |
| 13 no chain mill |  | cleaned | New hopper replaced. |  | New Motors provided |
| 14 no chain mill |  | cleaned | New hopper replaced. |  | New Motors provided |
| Ammonia vaporizer |  |  | Opened and hydro testing done and re-fixed. |  |  |
| Tail gas Vaporiser |  |  | Safety relief valves opened for servicing & fixed |  |  |
| Pre Heater |  |  | TT flange replaced. Pre heater Opened and hydro testing done and re-fixed. |  | Instrument PT to be fixed |
| F. O. System |  |  | Filter cleaning pending |  |  |
| Coating System |  |  | Strainer cleaned, coating nozzles cleaned. |  |  |
| Over size screens |  |  |  |  | Vibrators servicing done. |
| Product size screens |  |  | 6 nos Damage mesh replaced |  | Vibrators servicing done. |
| Steam Air Heater |  | Co2 blasting done. |  |  |  |
| All PRV |  |  | Opened and servicing done. |  |  |
| All LTs |  |  |  |  | Servicing done by instrument depts |
| All flow heads |  |  |  |  | Servicing done by instrument depts |
| All control valves |  |  |  |  | Servicing done by instrument depts |
| Acid pumps | 80 and 90 series | Inlet and outlet cleaned. | Pump base modification done |  | Motor overhauled |
| Acid lines | W/A to PN,Pre and pri | W/A to PN ,Pre and Pri line cleaned. |  |  |  |
|  | S/A to PN | S/A to PN line cleaned. |  |  |  |
|  | Pre to PN | Pre to PN line cleaned |  |  |  |
|  | Pri scrubber to pre scrubber line | Pri scrubber to pre scrubber line cleaned. |  |  |  |
| House keeping | All floor | All floor cleaned and structure up to screen floor cleaned. Ground floor cleaned. Wet section floor and drains cleaned. |  |  |  |

DAP TR-B(Mech)

01. GRANULATOR:

Support roller bearing clearance checking & lubrication.

Granulator alignment, skewing of support roller done.

Pinion to girth gear root clearance, back lash & blue matching done.

Torque tube inspection, lubrication done

Leveling , alignment of drive side.

Slurry header support pipe replaced.

Granulator Ammonia sparger replaced.

14 nos EPDM panel replaced.

02. DRYER:

Support roller bearing clearance checking & lubrication.

Dryer alignment, skewing of support roller done.

Pinion to girth gear root clearance, back lash & blue matching done.

Girth gear spring plate 4 nos replaced.

Thrust rinding ring wear ring replaced.

Torque tube inspection, lubrication done, Leveling , alignment of drive side.

03. CHAINMILL:

All chainmill liner inspection & overhauling done.

Chainmill inlet & discharge chute repairing & replacement done.

04. ELEVATOR:

- All elevator chain link, pin, bucket inspected & damaged buckets replaced.

- All elevator head shaft bearing insp/lubrication done.

- The counter weight box was aligned properly with respect to guide channels and was welded properly.

- The tail shaft assembly and CI block was replaced and aligned.

- Product screen elevator inlet chute (21,22,23 & 24) modified.

05. FINES CONVEYOR:

- Head pulley & foundation frame replaced.

- All pulley bearing insp/lubrication done

- Carrying & return idler with frame replaced.

- Coupling bolt insp/replaced.

- G.B. oil replacement done.

- Conveyor Belt replacement done.

- Plain Tail pulley replaced in place of Wing pulley.

06. SCRUBBER AREA JOB:

- Dust & Fumes separator full shell plate course replaced with new plate.

- Prescrubber shell patch work done.

- PN to Pre duct fabrication & erection.

4.TG scrubber metal lining inspection & welding done.

07.  CHAMBER

1.Comb chamber shell assembly with wind box patch work done.

+

08.  RM CONVEYOR

- Conveyor structure strengthening done.

- Feeding hopper & grizzly replacement done.

09.  70 CONVEYOR

- Gearbox inspection & overhauling done

- All bearing s of pullies insp/lubrication done.

- Gear coupling inspection/lubrication done.

- Idlers with frame replacement as per requirement

10.  DDC CONVEYOR

- Structure strengthening done, DDC conveyor structure revamped.

- Gearbox oil replacement & coupling bolt  with bearing inspection /lubrication done.

- Conveyor Belt replaced.

11.  FANS

- All fan bearing inspection & lubrication done.

- Casing repairing with rubber lining done.

- Dust & Fumes and Dryer exhaust fan casing rubber lining done.

- New Dust fan erected & commissioned.

12. SCREENS

- All oversize & product screen mesh repairing/replacement done.

- Tensioning rail & optimizer tensioning kit replaced in Oversize & product screens.

- Over size screen inlet chute replaced by new one.

13. STEAM AIR HEATER

1. Steam air heater coil cleaning done .

DAP TRAIN-C

Annual shut down activity of DAP Train-C in the year 2015 was started on 29.03.15 and completed on 16.04.15 During this period many activities related to process and equipment overhauling, cleaning jobs done. The equipment wise major jobs are as per the followings.

- Granulator

- Dryer

- D&F Exhaust Fan

- Dryer Exhaust Fan

- Scrubbers

- Pre neutralizer

- Ammonia Section

- Quench Air Fan

- Steam Air Heater

- Coating System

- Combustion chamber

- Primary Elevator

- Secondary Elevator

- Product screen Elevator

- Product Elevator

- Oversize Screen

- Product Screen

- Dryer Discharge Conveyor(DDC)

- 70 conveyor

- RM Conveyor

- Chain mill

- Cyclones

- Fines Conveyor

- Vibro feeder

Granulator:

- Granulator inside all fourteen (14) nos damaged rubber panels replaced.

- Granulator inside ammonia sparger below crack welding done.

- Torque tube coupling alignment and lubrication done.

- It’s both lube oil filters cleaned.

- Granulator motor replaced.

- Granulator inside washed and cleaned.

Dryer:

- Dryer spring plate 1 no replaced.

- Torque tube coupling alignment and lubrication done.

- Pinion to girth gear alignment done.

- Gear box input oil seal replaced.

- All thrust and support roller bearing greasing done.

- Lube oil filters and water cooler cleaned.

- Its discharge grizzly 6 nos. missing bars welded.

- 10 nos. bended lifters straighten.

D& F Exhaust Fan:

- Casing damaged portion patching and rubber lining done.

- Impeller inspection, sand blasting & balancing done.

- Fan impeller & motor alignment done.

- Impeller Water flushing line cleaned.

- D & F exhaust fan suction damper replaced.

- Motor replaced.

- Both bearing replaced.

- Fan’s suction & discharge duct are cleaned.

- Motor base painting done.

Dryer Exhaust Fan:

- Casing damaged portion patching and rubber lining done.

- Impeller inspection, sand blasting & balancing done.

- Fan impeller & motor alignment done.

- Impeller Water flushing line cleaned.

- Fan suction damper replaced.

- Fan’s suction & discharge duct are cleaned.

- Motor base painting done.

Scrubbers:

- All scrubbers’ venturi and separator side, it’s down comer line its nozzles header line cleaned.

- All scrubber’s venturi and separator inner shell descaled.

- All pumps suction & discharge line cleaned.

- Weak acid line to primary scrubber tank cleaned.

- Line from Primary scrubber tank to Pre scrubber tank cleaned.

- TG scrubber Top demister cleaned.

- TG common duct cleaned .Pump common discharge line & Nozzles header line cleaned.

- TG scrubber liquor main & bypass line control valve inspected and cleaned.

- D&F exh.fan and dryer exh.fan discharge duct damaged rubber lining replaced.

- TG Common duct inside SS plate joint DP test and welding done.

- FRP duct cleaned.

- 41, 42 pumps discharge circulation line up to FRP duct cleaned.

- Weak acid line to pre scrubber tank cleaned.

- Pre scrubber separator top damaged rubber lining replaced.

Pre neutralizer (PN):

- PN tank inside, top roof cleaned.

- PN Tank inside ammonia sparger damaged mouth piece welded.

Ammonia Section:

Ammonia Vaporizer:

- Pressure safety valve of inlet line and top shell servicing done. Tube pressure testing done

TG Vaporizer:-

- Tube bundle replaced.

- Pressure safety valve of inlet line and top shell servicing done.

Ammonia Pre heater:

- Ammonia pre heater replaced.

Quench Air Fan:

- Fan rotor servicing & bearing greasing done.

Steam/Air heater:

- Steam Air heater coil’s external surface dry ice blast cleaning done.

- Pressure safety valve of steam inlet line servicing done.

- DAP battery limit area 10” LP steam pipe replaced  normal 14” pipe with control valve

Coating Oil System:

1.  Surface coating oil pump suction strainer cleaned.

2.  All spray nozzles cleaned.

3. Mixing tank cleaned.

Combustion Chamber:

- Chamber inside clinker cleaned.

- Chamber inside damaged plate patching done.

- Chamber inside brick lining & refractory plastering done.

- Air Register & Gun replaced.

- Wind holes nozzles provided in Combustion chamber.

- All  FO pump suction and discharge filters cleaned.

Primary Elevator:

- Motor and fluid coupling replaced.

- Gear box input oil seal replaced.

3.   Buckets and chain link inspection done. Damaged & missing bolts replaced.

4.  Bottom both sides C. I .block with guide channel replaced.

5. Gear box oil replaced.

Secondary Elevator:

- Motor replaced.

- Buckets and chain link inspection done. Damaged & missing bolts replaced.

- Gear box oil replaced.

Product Screen Elevator:

- Motor replaced.

- Bottom both sides C. I .block with guide channel replaced.

- Gear box oil replaced.

- Buckets and chain link inspection done. Damaged & missing bolts replaced.

- Chain length shortened.

Product Elevator:

- Motor replaced.

- Buckets and chain link inspection done. Damaged & missing bolts replaced.

- Gear box oil replaced.

- Chain length shortened.

Oversize Screen:-11, 12, 13, 14

- O/S screen inlet, outlet, hopper cleaned.

- All O/S screen meshes replaced.

Product size screen:-21, 22, 23, 24

- P/S screen inlet, outlet, hopper cleaned.

- All P/S screen meshes replaced.

Dryer Discharge Conveyor (DDC):

- DDC belt replaced.

- Damaged Skirt rubber replaced.

- Motor replaced.

- Damaged Carrying idlers replaced.

- Head pulley lagging done.

- Tail pulley replaced.

70-Conveyor:

- 70-Conveyor belt replaced.

- Motor replaced.

- Deck plate, tail pulley head pulley, snub pulley cleaned.

- Damaged Carrying idlers replaced.

- Head pulley lagging done.

- Counter weight adjustment done.

RM Conveyor:

- RM conveyor belt replaced.

- Motor replaced.

- Both coupling replaced.

Chain Mill:

- All chain mill inlet chutes cleaned.

- All chain mill rotors chain link replaced.

- All chain mill bearing replacement done.

- Chain mill inside & motor base cleaning done.

- 12 & 13 no chain mill inlet chute replaced.

- All Bearing fixed after greasing.

Cyclones:

- All cyclones plenum inlet, outlet duct, bottles, hopper, and discharge duct to fines conveyor cleaned.

- Trickle valve de-scaled and down comer line cleaned.

Fines Conveyor:

- Fines conveyor belt replaced.

- Motor replaced.

- Gear box overwhelming done.

- Head pulley, bend pulley, Take off pulley rubber lining done.

- Deck plate cleaned.

- Tail pulley replaced.

- Head end & Tail end bearing greasing done.

- Damaged Carrying idlers replaced.

- Damaged carrying idlers frame replaced.

- Both sides damaged skirt rubber replaced.

Vibro feeder:

- Vibro feeder both motors replaced.

- Vibro feeder plate descaling done.

Common jobs:

- New FO transfer line connected at the DAP plant battery limit area.

- Instrument air line from DAP plant battery limit point to Air receiver replaced.

Instrument jobs:-

- All control valve and its actuator servicing done.

- All dip tubes inspection done.

Electrical jobs:-

- Most of HT and LT motor servicing done.

Inspection Section jobs:-

- Inspection of steam air heater coil thickness was carried out by inspection section.

Planning Section jobs:-

- Painting of structures was carried out by planning section.

Process cleaning:-

  - Granulator and dryer inside washing done at the time of stoppage of plant.

2.   All the floors of the plant cleaned.

DAP TR-C(Mech): 28.03.2015 TO 16.04.2015

01. GRANULATOR

- Support roller bearing clearance checking & lubrication.

- Granulator alignment, skewing of support roller done.

- Pinion to girth gear root clearance, back lash & blue matching done.

- Torque tube inspection, lubrication done

- Leveling , alignment of drive side.

- Two nos EPDM panel Replaced.

02. DRYER

- Support roller bearing clearance checking & lubrication.

- Dryer alignment, skewing of support roller done.

- Pinion to girth gear root clearance, back lash & blue matching done.

- Girth gear inspection & health check up done & one girth gear spring plate replaced.

- Torque tube inspection, lubrication done

- Leveling , alignment of drive side.

03. CHAINMILL

- All chainmill liner inspection & overhauling done.

- Chainmill inlet & discharge chute repairing & replacement done.

04. ELEVATOR

- All elevator chain link, pin, bucket inspected & damaged buckets replaced.

- All elevator head shaft bearing insp/lubrication done.

- The counter weight box was aligned properly with respect to guide channels and was welded properly.

- The tail shaft assembly and CI block was replaced and aligned.

05. FINES CONVEYOR

- Head pulley & foundation frame replaced.

- All pulley bearing insp/lubrication done

- Carrying & return idler with frame replaced.

- Coupling bolt insp/replaced.

- G.B. oil replacement done.

- Conveyor Belt replacement done.

- Plain Tail pulley replaced in place of Wing pulley.

06. SCRUBBER AREA JOB:

- Dust & Fumes separator full shell plate course replaced with new plate.

- Prescrubber shell patch work done.

- PN to Pre duct fabrication & erection.

- TG scrubber metal lining inspection & welding done.

07.  CHAMBER

- Comb chamber shell assembly with wind box patch work done.

+

08.  RM CONVEYOR

- Conveyor structure strengthening done.

- Feeding hopper & grizzly replacement done.

09.  70 CONVEYOR

- Gearbox inspection & overhauling done

- All bearing s of pullies insp/lubrication done.

- Gear coupling inspection/lubrication done.

- Idlers with frame replacement as per requirement

10.  DDC CONVEYOR

- Structure strengthening done.

- DDC conveyor structure revamped.

- Gearbox oil replacement & coupling bolt  with bearing inspection /lubrication done.

- Conveyor Belt replaced.

11.  FANS

- All fan bearing inspection & lubrication done.

- Casing repairing with rubber lining done.

- Dust & Fumes  and Dryer exhaust fan casing rubber lining done.

12. SCREENS

- All oversize & product screen mesh repairing/replacement done.

- Tensioning rail & optimizer tensioning kit replaced in Oversize & product screens.

13. STEAM AIR HEATER

1. Steam air heater coil cleaning done .

14. TG Vaprouiser

TG vapouriser new tube bundle replaced

INSTRUMENTATION                                    JOBS CARRIED OUT IN DAP DURING ATR

Control valve’s maintenance (Globe Type) :-

- FV-759 ( Liquid ammonia main valve )

- FV-717 ( LP steam to pre heater inlet )

- FV- 755 ( Pre heater condensate outlet valve)

- FV-716.1 (Ammonia vap. Condensate outlet valve )

- FV-714 (TG vap. Inlet valve)

- FV-721 (Ammonia vap. Inlet valve)

- HV-102 (MP steam to PN )

- HV-111 ( MP steam slurry nozzel )

- HV-118 ( MP steam to granulator)

- FV-200 ( FO to chamber )

- FV-231 ( LP steam to chamber)

- LV-203 ( Steam air heater condensate outlet )

- PV-204 ( Steam air heater condensate vent )

- TV-202 ( Steam condensate to tank )

During the maintenance, following activities had carried out,

- Valve removed from line & sent to workshop.

- Completely dismantle the valve.

- Checking the healthiness of plug & sheet & where required it’s machining done in central workshop.

- Assembled the valve completely.

- Valve’s passing & leakage checked with 20 kg/cm2 pressure from dead weight tester.

- Calibrate the valve with MA source.

- All valve’s tubing straightened in proper way, unused tubes removed from field

- Control valve’s maintenance ( Butterfly Type ) :-

- FV-104 ( Vapor ammonia to granulator )

- FV-101 ( Vapor ammonia to PN )

- TG main valve

- TG bypass valve

During the maintenance, following activities had carried out,

- Valve removed from line & sent to workshop.

- Completely dismantle the valve.

- Checking the healthiness of flapper & teflon seat ring & where required it replaced.

- Assembled the valve completely.

- Valve’s body passing checked.

- Calibrate the valve with MA source.

- All valve’s tubing straightened in proper way, unused tubes removed from field

- Control valve’s maintenance ( Plug Type ) :-

- FV-106.1 ( Sulphuric acid to PN )

- FV-107 (Scrubber liq. To PN )

- FV- 107.1 (Scrubber liq. To PN )

- FV-103 ( Strong acid to PN )

- FV-105 ( Weak acid to PN )

- FV-707 ( TG liq to primary )

- FV-628 ( Wash liq to primary )

- FV-606 ( Primary to pre. )

- FV-638 ( Sulphuric acid to primary)

- FV-618 ( Weak acid to primary )

- FV-603 ( Weak acid to pre )

- FV-520 ( Wash liq. to PN )

- FV-764 ( Wash liq. to TG )

- FV-729 ( Pond water to TG )

- Slurry pump (21) main/recycle

- Slurry pump (22) main/recycle

During the maintenance, following activities had carried out,

- Valve removed from line.

- Actuator & positioner servicing.

- Checking of valve’s body passing & where required it attended.

- Assembled the valve completely.

- Calibrate the valve with MA source.

- All valve’s tubing straightened in proper way, unused tubes removed from field.

- All el-o-matic actuators ( Ball valve ) servicing done.

- Following scrubber flow heads removed from line, descaling & zero caliberation done.

- FT-630.1

- FT630.2

- FT-631.1

- FT-631.2

- FT-762

- FT-609.

- Slurry flow heads ( FT-124 & FT-127 ) descaling & zero caliberation done.

- All electromagnetic flow meter’s, flow head terminal box’s maintenance & pulse converter’s servicing done.

- All temperature transmitters & temperature elements ( RTD & thermocouple ) maintenance done & where required temperature element changed.

- All pressure transmitters maintenance & it’s impulse tube’s de chocking done.

- All level transmitters maintenance & it’s impulse tube’s de chocking done.

- All flow transmitters maintenance & it’s impulse tube’s de chocking done.

- Product storage conv.(70), load cell frame’s maintenance & it’s caliberation done.

- Oval wheel flow meter (FT-200), FO to chamber servicing done.

- BMS (chamber firing) panel’s maintenance done.

- Following Field JB maintenance & ferruling done.

- AJB-101/AJB-102/AJB-112/AJB-111/AJB-109/AJB-110/AJB-115/AJB-121/AJB-128/AJB-251/AJB-252/PJB-101

- At substation, HT drive’s JB (DO & DI)maintenance done.

- At substation, HT drive’s IT panel maintenance done.

- DCS, system cabinet, analog panel, DO panel , DI panel’s & operating station’s , proper cleaning & maintenance done.

Extra jobs in DAP Tr- A:-

- PT-104 (vap. Ammonia pressure to granulator), TT-104 (vap. Ammonia temperature to granulator), PT-120 ( Granulator lub oil pressure) & PT-219 ( Dryer lube oil pressure) cable re- routing done.

- AJB-109, AJB-110 & AJB-111 cable re-routing done.

- Scrubber flow meter ( FT- 630.1 & FT-631.2 ) re-location done.

Extra jobs in DAP Tr- B:-

- One faulty processor card ( CP 451 ) replaced with new one & it’s master/redundancy checked.

- One power JB lineup for electromagnetic flow meters.

Extra jobs in DAP Tr- C:-

- Damaged power JB ( PJB-103 ) replaced with new one.

DCS Maintenance

- Controlled shutdown for complete DCS and HMI stations had been taken under the supervision of service engineer from Yokogawa.

- All the HMIs and Engineering station CPUs were cleaned with blower and reinstalled.

- All the CPU cards, Power supply cards and I/O cards were removed from the back plane and cleaning done by the Yokogawa team and reinstalled.

- Backup of all configured machines have been taken.

- End Point Security system (Antivirus) has been installed in all HIS and Engg. Station.

Advantages of End Point Security System are:

- Since our network is secured, there is 0% breakdown & 100% availability in Network.so results in breakdown free Operation for operators.

- There is no time delay in any response /input given by operator.

- Good efficiency in operation results in minimizing down time of Equipment’s, results in less operational Cost & Maximizing Production.

- No Panic Situation caused in case of any emergency led by failure of HIS.

- The Downtime of the HIS will be very less comparatively when the HIS failure without any security.

- The Networked DCS system without ENDPOINT SECURITY have open communication and open access for everyone to use their Pen drive to collect plant datas or other confidential official datas. Whereas CS3000 Network with ENDPOINT SECURITY has a very Closed Communication & Full Locked Down so that no datas are stolen and very much secured.

- The use of Pen drives is a major source of Viruses, End Point Security will restrict the use of pen drives  & therefore our system will not get affected by viruses.

UPS Maintenance

- Controlled shutdown of UPS had been taken.

- General AMC checkups done by the Emerson engineer.

- UPS taken in line after completion of the AMC jobs.

EARTH PIT

- Old Earth Pit of DCS & UPS of each train are replaced with two New Earth Pits.

ELECTRICAL JOB DONE IN ATR 2015 IN DAP PLANT

|  | ELECTRICAL JOB DONE IN ATR 2015 IN DAP PLANT | Duration/ date | Agency/ Manpower |  |
| --- | --- | --- | --- | --- |
| 1.0 | 33 KV SWITCH GEAR MAINTENANCE |  |  |  |
| 1.1 | Bus section –A Dedusting, bus bar tightness checking, space heater checking and sealing of panels done. IR value of the bus Ph- E 2.5 G –ohm, Ph-Ph- 8 G –ohm | 01.04.2015 | Deptt. |  |
| 1.2 | Bus section –B Dedusting, bus bar tightness checking, space heater checking and sealing of panels done. IR value of the bus Ph- E 2.3 G –ohm, Ph-Ph- 8 G –ohm | 03.04.2015 | Deptt. |  |
| 2.0 | 6.6 KV SWITCH GEAR MAINTENANCE |  |  |  |
| 2.1 | Bus section –A Dedusting, bus bar tightness checking, space heater checking and sealing of panels done. IR value of the bus Ph- E 2.5 G –ohm, Ph-Ph- 10 G –ohm | 01.04.2015 | Deptt. |  |
| 2.2 | Bus section –B Dedusting, bus bar tightness checking, space heater checking and sealing of panels done. IR value of the bus Ph- E 2.3 G –ohm, Ph-Ph- 10 G –ohm | 05.04.2015 | Deptt. |  |
| 3.0 | PCC -4 MAINTENANCE |  |  |  |
| 3.1 | Dedusting, bus bar tightness checking, space heater checking and sealing of panels done. IR value of the bus Ph- E 600 M –ohm, Ph-Ph- >1000 M –ohm | 02.04.2015 | Deptt. |  |
| 4.0 | PCC -5 MAINTENANCE |  |  |  |
| 4.1 | Dedusting, bus bar tightness checking, space heater checking and sealing of panels done. IR value of the bus Ph- E 600 M –ohm, Ph-Ph- >1000 M –ohm | 07.04.2015 | Deptt. |  |
| 5.0 | RETROFITTING JOB |  |  |  |
| 5.1 | Retrofitting of MICOM RELAY 642 Differential relay done for transformer- 9 & 10 Materials used : 2 nos new of MICOM RELAY 642 Differential relay | 07.04.2015&09.04.2015 | Power system |  |
| 6.0 | RELAY TESTING |  |  |  |
| 6.1 | 7SJ ELECTRONIC Relay , Micom relay and other electromechanical relay testing done. Materials used : 1nos new relay have been used for replacement. | APR 2015 | POWER LINKER |  |
| 7.0 | MCC MAINTENANCE |  |  |  |
| 7.1 | CHAIN MILL MCC TRAIN-A Dedusting, busbar tightness checking, Modules of all outgoing motor feeders checking done. IR value Ph- E >1000 M –ohm, Ph-Ph- >1000 M –ohm | 31.03.2015 | Deptt. |  |
| 7.2 | CHAIN MILL MCC TRAIN-B Dedusting, busbar tightness checking, Modules of all outgoing motor feeders checking done. IR value Ph- E >1000 M –ohm, Ph-Ph- >1000 M –ohm | 30.03.2015 | Deptt. |  |
| 7.3 | CHAIN MILL MCC TRAIN-C Dedusting, busbar tightness checking, Modules of all outgoing motor feeders checking done. IR value Ph- E 1000 M –ohm, Ph-Ph- >1000 M –ohm | 01.04.2015 | Deptt. |  |
| 7.4 | MCC- Train-A Dedusting, busbar tightness checking, Modules of all outgoing motor feeders checking done. IR value Ph- E 500 M –ohm, Ph-Ph- >1000 M –ohm | 02.04.2015 | Deptt. |  |
| 7.5 | MCC- Train-B Dedusting, busbar tightness checking, Modules of all outgoing motor feeders checking done. IR value Ph- E 500 M –ohm, Ph-Ph- >1000 M –ohm | 04.04.2015 | Deptt. |  |
| 7.6 | MCC- Train-C Dedusting, busbar tightness checking, Modules of all outgoing motor feeders checking done. IR value Ph- E 400 M –ohm, Ph-Ph- >1000 M –ohm | 03.04.2015 | Deptt. |  |
| 8.0 | 6.6 KV MOTOR OVERHAULING |  |  |  |
| 8.1 | Dust & Fumes motor for train A,B & C | APR 2015 | Deptt. |  |
| 8.2 | Dryer ex. Fan for train A,B & C | APR 2015 | Deptt. |  |
| 8.3 | Granulator motor for train A,B & C | APR 2015 | Deptt. |  |
| 8.4 | Dryer motor for train A & B |  |  |  |
| 8.5 | Dust Fan motor for train B, 6.6 KV, 400 KW ABB MAKE New Motor installed and commissioned | 15.04.2015 | Deptt. |  |
| 9.0 | 415 V MOTOR OVERHAULING |  |  |  |
| 9.1 | 07 Nos. chain mill motors of train A ,B & C | APR 2015 | Deptt. |  |
| 9.2 | Dryer Inching drive motor for train B | APR 2015 | Deptt. |  |
| 9.3 | DDC, RM Conveyor & Fines, 70A/B/C conveyor motors | APR 2015 | Deptt. |  |
| 9.4 | All elevators motors of train A ,B & C | APR 2015 |  |  |
| 9.4 | 21A, 52B, 62C , 81 & 82 A & Vibrofeeder motors | APR 2015 | Deptt. |  |
| 10.0 | Transformer maintenance |  |  |  |
|  | Transformer 25 , 28,29, 30 31 , 9 & 10- maintenance done . Busduct cleaned, HT & LT terminal checked, checking of marshalling box, silica gel & replacement of radiator etc job done. Materials used : Transformer #9- 01 no radiator ( new ) & breather ( new ), Transformer#10- 04 nos. Radiatos ( new ) |  |  | Deptt./Voltamp |
| 11.0 | HT BREAKER SERVIVING |  |  | Siemens |
|  | 16 nos HT BREAKER/VCU servicing done |  |  |  |
| 12.0 | LT BREAKER SERVIVING |  |  | Siemens |
|  | 32 nos M/S SIEMENS MAKE LT ACB servicing done | APR 2015 |  | Siemens |
| 13.0 | DCDB MAINTENANCEH |  |  |  |
| 13.1 | General cleaning & maintenance done. | APR 2015 |  | Dept/M/S Universal |
| 14.0 | TEMPORARY CONNECTIONS : |  |  |  |
| 14.1 | Temporary connection given for lighting job, extension boards, handlamp , flood light , welding m/c etc. for train A,B & C | APR 2015 |  | Deptt |

Report on Annual Turn Around – 2015 activities

Annual shut down activity of Phosphoric Acid Plant in the year 2015 was started on 28th March and completed on 15h April. During this period many activities related to process and equipment overhauling, cleaning jobs at different points were undertaken. The area wise major process activities are depicted below.

- Reactor.

- Slurry Surge Tank

- Fume scrubber and Pre scrubber

- Cold well, Cooling Tower Mist eliminator and basin.

- Vac. Cooler Pre condenser seal tanks etc.

- Evaporator Area

- Belt Filter

- Ball Mill & Ball Mill area

- New Pump tank

- Vessel & Line Cleaning

- RPSS area

- Gypsum Tank

- Others

1. Reactor cleaning: As a part of Annual Turn Around 2015, Reactor was drained on 28/03/2015 & chemical washing was running till 7.00 PM on 29/03/2015 for degasification of fluorine compounds. Finally liquid draining was completed at 8.00AM on 30/03/2015.

After opening of manholes, it was observed that there is huge deposition of very hard scale on reactor walls. In some places, projection of scale material was even up to 1 meter in annular zone. No deposition was there on floor. Quantity of material in annular zone was approx. 700 MT. It was impossible to clean this deposit manually and safely within the time frame of Annual Turn Around 2015. Hence it was decided to get the job done with the help of one JCB machine. De scaling of both side walls of annular zone was done carefully with constant supervision and without any harm to brick lining. Care was taken to complete the activity in the safest manner. Entire scale material was removed through the agitator openings by net & rope (jhula). Baffle columns cleaning was done. Cleaning of flash chambers of vacuum cooler 110 & 113 was also done. Heavy hard scaling was observed on walls of vacuum cooler 110, same was removed from vessel. Approximately, 250 MT material was cleaned from all the vac. coolers. Out of seven damaged agitators, only one reactor agitator was replaced in annular section. Conditions of other agitators were not good. A pit formed at the bottom of agitator 120 where repairing was done again like previous year. Descaling on walls of VCST was done. Around 200 MT hard scaling was removed from VCST. Wall descaling and floor cleaning (Pebble) of VCFT was done manually. Around 150 MT material was removed from VCFT.  Agitator 142 of VCST was replaced with new one. Complete cleaning of adjustment & Filter feed tank was done. Around 150 MT material was removed from both tanks. Descaling was done for all four vacuum cooler outlet pipes and seal legs.

Reactor annular section cleaning with JCB

Scale removal from Reactor with crane

Pit formed under Agitator 120

Pit after repairing under Agitator 120

Reactor VCST wall cleaning

Descaling of reactor agitator

Reactor annular section after cleaning

VCST wall & Baffle column after cleaning

2. SST cleaning:  Deposition of Material (apprx. 200 MT) was found at the bottom. Same was cleaned to make access to the agitator. Damaged blades of the agitator were replaced, gear Box was checked & motor was overhauled. Damaged baffle plates were strengthened. Also patch up strengthening was carried out over thinned portions of the tank wall.

Cleaning inside SST

SST wall patch work

3. Fume scrubber cleaning: Deposited silica on Fumes scrubber inside floor & walls, inside Pre scrubber and its outlet U-duct were thoroughly cleaned. Fumes scrubber floor was found damaged at multiple places, metal work and rubber lining job was carried out. Cleaning was done in Fumes scrubber sump also. Approximately, 100 MT material was cleaned in this section.

Fume scrubber sump after cleaning

Fume scrubber inside before cleaning

- Cold well, basin, strainers & Mist Eliminator cleaning: Cold well basin was emptied out and found to be deposited with silica and foreign materials (mist eliminators, wooden pieces, V-bars etc.). After pushing same to Cold Well, basin was cleaned. Pay loader and Excavator were utilized for cleaning of the cold well. Strainers & Mist eliminators of all the cells were cleaned thoroughly. Damaged brick linings of basin walls of compartment no. 2 & 3 was repaired. Cooling Tower top deck was also thoroughly cleaned. Approximately, 300 MT materials were cleaned in this section.

Cold well basin after cleaning

Mist eliminator after cleaning

Cold well cleaning by Excavator

Cooling Tower deck cleaning

- Vac. Cooler Pre condenser seal tanks cleaning: Depositions inside Pre condenser seal tanks (both old and new) were also cleaned.  Approximately, 50 MT material was cleaned in this section.

- Evaporator Area: Heat Exchanger tube cleaning was done for evaporators B, C, D, E & F. Sieve trays of Barometric Condensers of all evaporators were cleaned. Entrainment separator and FSA seal tanks of all evaporators were opened and cleaned. Fluorine Scrubber man way of all evaporators were opened for inspection of spray nozzles. Blocked nozzles were cleaned & selective damaged nozzles were replaced. Evaporator B steam isolation valve was also replaced.

Heat Exchanger Tubes after cleaning

- Belt Filter cleaning: Inside the filter manifolds wherever scaling was observed, it was cleaned. Along with those Vac. Boxes, Filtrate hoses, Sluice headers, Cloth wash headers, Distributors, Receivers etc. were also cleaned.

- Ball Mill & Ball Mill area cleaning: Segregation and charging of balls were carried out for Ball Mill A & D during this shut down. MST of all Ball Mills were cleaned. Deposition of spillage rock in entire Ball Mill area was also cleaned. Approximately, 100 MT material was cleaned in this section.

Ball Mill- D ball segregation & charging

- New pump tank cleaning: New pump tank manhole was opened during the annual shut down and found to have deposition of gypsum. Tank was cleaned thoroughly. Manhole repairing was done also.

- Vessel & Line Cleaning: Cloth wash tank was cleaned. Filtrate seal tanks of all the Belt Filters were cleaned. All the control valves in Filtration area were cleaned. All the suction & discharge lines of Acid transfer pumps were cleaned thoroughly.

Line cleaning u/progress

Lines after cleaning

- RPSS area cleaning: Entire conveyor area spillage was cleaned.

- Gypsum Tank: Deposition inside Gypsum Tank has been cleaned and strengthening of its agitator has been done.

- 8th evaporator: For commissioning of 8th evaporator cooling water, steam, condensate and air connection was taken from corresponding header lines.

Isolation valve in Cold Well water header

Isolation valve in steam header

Annual Shut Down Report 
PAP-Mechanical Department

Asst. Manager (Mech.)

RPSS SECTION

Conveyor Tag No. : 20-29.103 ‘A’, 20-29.103 ‘B’, 20-29.103 ‘C’

- All carrying, Impact & return idlers were checked & made free for smooth pulling of the belt.

- Defective / Faulty Idlers were replaced.

- Drive side & non drive side i.e. snub pulley, bend pulley, take up pulley & tail pulley were                checked & made free / greasing done for smooth pulling of the belt.

- Faulty manual slide gate repaired followed by replacement of damaged sliding plates, greasing & diesel washing and made ready for operation.

- Gear Box oil replaced for conveyor 103 ‘A’, 103 B & 103 C .

- Gear Box & Fluid Coupling oil replaced for conveyor 103 A 103 ‘B’ & 103 ‘C’.

Conveyor Tag No. : 20-29.104 A

- All carrying, Impact & return idlers were checked & made free for smooth pulling of the belt.

- Defective / Faulty Idlers were replaced.

- Drive side & non drive side i.e. snub pulley, bend pulley, take up pulley & tail pulley were             checked & made free / greasing done for smooth pulling of the belt.

- Gear Box oil replaced.

- Rubber bush of Pin Bush Coupling / High speed coupling (Motor to Gear Box) replaced .



 Conveyor Tag No. : 20-29.104

- Elongation length ( Appx. : 15 mtr.) of 104 Belt was shortened by hot vulcanization process .

- All carrying, Impact & return idlers were checked & made free for smooth pulling of the belt.

- Defective / Faulty Idlers were replaced.

- Drive side & non drive side i.e. snub pulley, bend pulley, take up pulley & tail pulley were            checked & made free / greasing done for smooth pulling of the belt.

- Damaged skirt rubber (appx.24 mtr.)  Replaced and damaged skirt plate repaired.

- Gear Box & Fluid Coupling oil replaced.

Conveyor Tag No. : 20-29.105

- All carrying, Impact & return idlers were checked & made free for smooth pulling of the belt.

- Defective / Faulty Idlers were replaced.

- Drive side & non drive side i.e. snub pulley, bend pulley, take up pulley & tail pulley were              checked & made free / greasing done for smooth pulling of the belt.

- Damaged skirt rubber (appx. 12 mtr.) replaced.

- Gear Box oil replaced & greasing in gear coupling was carried out.

- Discharge chute repaired by patch working.

- Dust Protection cover rubber provided .

- Receiving chute was modified by reducing the opening for spillage control.

Conveyor Tag No. : 20-29.106 ‘B’

- All carrying, Impact & return idlers were checked & made free for smooth pulling of the belt.

- Defective / Faulty Idlers were replaced.

- Damaged skirt rubber (appx.12 mtr.)  Replaced and damaged skirt plate repaired.

- Gear Box oil replaced.

- Drive side & non drive side i.e. snub pulley, bend pulley, take up pulley & tail pulley were             checked & made free / greasing done for smooth pulling of the belt.

- Receiving chute modification was done to reduce spillage of rock.

- De dusting system ( bag filter ) completely dismantled . Bags were removed , cleaned by air and re installed in position .

- Damaged plates from the floor area were replaced.

Cleaning Job in progress

Final view after Cleaning Job

Conveyor Tag No. : 20-29.106 ‘A’

- All carrying, Impact & return idlers were checked & made free for smooth pulling of the belt.

- Defective / Faulty Idlers were replaced.

- Damaged skirt rubber (appx.12 mtr.)  Replaced

- Gear Box oil replaced.

- Drive side & non drive side i.e. snub pulley, bend pulley, take up pulley & tail pulley were              checked & made free / greasing done for smooth pulling of the belt.

- Discharge chute repaired by patch working.

- De dusting system ( bag filter ) completely dismantled . Bags were removed , cleaned by air 
and re installed in position .

- Damaged plates from the floor area were replaced .

Air cleaning of Filter Chamber

BALL MILL SECTION

SLURRY SURGE TANK TAG NO. :   20-09.30
          SST AGITATOR TAG NO. :   20-05.30
           SLURRY SURGE TANK STRENGTHENING / REPAIRING, AGITATOR BLADE 
           REPLACEMENT JOB:

- Manhole opened for inspection of SST wall thickness & agitator blade condition.

- Necessary scaffolding made for strengthening of SST shell and replacement of agitator blade.

- Strengthening of shell was carried out in the eroded portion of the wall by putting liner plate of 16 mm thick to suit at site.

- Strengthening / Repairing of baffle plates & ribs were carried out.

- Worn out agitator blades were replaced.

- Agitator bracket strengthening done.

- Agitator base structure strengthened.

- Motor was removed, gear box checked up.

- Motor fitted, Man way boxed up and the cut shell portion was fitted again .

Agitator blade replacement job in SST Tank

BALL MILL TAG NO:  20-27.010 A/B/C/D

MISCELLANEOUS SHUT DOWN MAINTENANCE JOBS

- Maintenance in main trunion bearing (Inlet & out let) ,  geared coupling, main gear box, MST Agitator gear box, screen Feed Pump,  Reactor Feed Pump, weigh feeder gear box, weigh feeder & fluid coupling were  carried out followed by greasing, oil replacement, all base bolt tightening, MST blade repairing, defective idler replacement works and defective components replacement

- All Ball Mill manholes were opened for ball segregation.

- Repairing of feed spout, packing, distance piece & hoppers was carried out .

- Trommel Screen of Ball Mill – ‘’C’’ was repaired.

- Screen hoppers of Ball Mill – ‘’B’’ & Ball Mill – ‘’D’’ were repaired & Damaged product hopper  
of Ball Mill – ‘’A’’ was repaired .

- Oil leakage from trunion bearing of Ball Mill ( A,B & C)  arrested .

REACTOR SECTION

- REVAMPING OF  FRP  FUMES DUCT IN REACTOR

Replacement / Repairing job in FRP Duct:

- The damaged / leaky part of the duct was repaired by super vinyl ester resin and associated materials to make the duct leak proof .

Dismantling of damaged FRP Fumes duct by EOT crane.

‘U’ duct removal & Pre-scrubber nozzle cleaning:

- The ‘U’ Duct was removed from its position.

- The duct was cleaned by water washing on the ground & boxed up at its position.

- Necessary scaffolding made in the pre-scrubber.

- All nozzles were dismantled, cleaned & fitted

.

U-Duct of Pre-scrubber boxed up after cleaning

- REVAMPING OF REACTOR AGITATORS :

Agitator Tag No. : 20-05.111, 142

- Complete assembly of reactor agitator was removed from the position followed by                                      gear box, motor, base frame and new agitator assembly was installed in the respective 
position, followed by leveling and alignment.

New Agitator installed in 111 Position

Agitator Tag No. : 20-05.112, 113,114,115 &116

- Complete assembly of reactor agitators were removed from the position followed by                                      gear box, motor, base frame.

- Agitator blades were inspected thoroughly. The damaged blades were repaired / strengthened by patch welding (25 mm thick. SS 904L Plates were patch welded according to damage portion of the agitator blades )

- Condition of Gear box oil was checked and existing oil replaced based on visual & physical inspection report.

- The damaged cover plates were changed along with supporting structure.

- Complete unit of agitator assembly was erected followed by leveling, alignment &                    commissioning activities.

Repair of Agitator Blades

Repair of Agitator Blades in progress

- OVERHAULING OF KNIFE EDGE GATE VALVE OF VACUUM COOLER                             CIRCULATION PUMP :

Knife Edge Gate Valve of Pump Tag No. : 20-01.110 & 20-01.113

- Two nos. of knife edge gate valves of size: 1050 NB were completely dismantled followed by inspection, bonnet removal, water washing, and liner & sheet removal.

- The damaged liner & sheet were removed.

- New liner & sheet fitted in the subject valves.

- The complete assemblies were boxed up.

Overhauling of Knife Edge gate Valve of Vacuum Cooler 110/113

- OVERHAULING OF VACUUM COOLER CIRCULATION PUMP :

Vacuum Cooler Circulation Pump Tag No. : 20.01.110 / 111 / 112 / 113

- The suction spool piece, reducer & bellow of size: 1050 NB in the subject pumps was removed.

- Necessary patch work in suction reducer, spool piece and casing was carried out.

- Bearing housing assembly was removed followed by removal of pulley, shaft & sleeve.

- Impeller along with complete bearing housing assembly fitted.

- New casing liner & stuffing box were fitted.

- New gland packing provided in all the pumps as cited above.

- Pulleys were installed & aligned.

- New power transmission ‘V’ belts (Belt No. : SPC 7100) provided & safety guard fitted.

- The subject pumps were handed over to operation.

Overhauling of Vacuum Cooler 110/111/112

OVERHAULING OF PRECONDENSOR PUMP

Pre-condenser Pump Tag No. : 
20-01.182 & 183

- The pump was completely dismantled.

- Through inspection was carried out in the rotor assembly of the pumps .

- New rotor assembly was provided in P-183.

- Damaged gland pickings were changed New Rubber bush in Pin Bush coupling of the subject pump provided.

- New casing gasket provided.

- The subject pump was handed over to operation.

- MIXING TEE REPLACEMENT:

Mixing Tee Tag No. : 20-05.409/410/415/416

- All Mixing Tee (total: 04nos.)  Were taken out for Inspection.

- Mixing Tee- 410 was found damaged, which was replaced with new one.

- Rest mixing tee assemblies were cleaned & re installed in position.

Mixing Tee Replacement

REMOVAL OF ALL VACUUM COOLER OUTLET (1500 MM) PIPE & SEAL LEG

- All the outlet pipes, Tee Piece and seal leg of tahe flash cooler (04 Nos.) were removed from position, necessary cleaning was carried out and then boxed up. (Picture attached below)

REMOVAL OF ALL VACUUM COOLER OUTLET (1500 MM) PIPE & SEAL LEG

REVAMPING OF FUME SCRUBBER FAN

- Old and new fume scrubber exhust fan inspected throughly and corrective action taken.

- Old fan was removed as there was deposition of silica found in the impeller and vibration observed during operation.

- Thus, the same was replaced with the ready assembled one, followed by motor erection, levelling & allignment .

FUME SCRUBBER FAN REMOVED FOR OVERHAULING

OVERHAULING OF FUME SCRUBBER FAN

CENTRAL COMPARTMENT AGITATOR FLOOR REPAIR

- A big pit was observed in 120 – central compartment agitator floor, which was located just below the agitator position .

- SS 904L Plate was provided and fixed in the pit position to suit the pit dimension and  filled by necessary mastic cements and then brick lined .

Hole in 120 Agitator Position

MISSCELLANEOUS SHUT DOWN MAINTENANCE JOB:

- Complete pre condenser vessel (111 & 112) was inspected thoroughly. Metal work was carried out inside the vessels at different location (roof & shell) as per inspection report and then rubber lining was done in the shell portion.

- Manholes & nozzles of precondensor vessels were opened and boxed up after necessary cleaning and repairing jobs.

- Fume scrubber chamber outlet pipes and nozzles were removed for cleaning purposes and then boxed up.

- Electric motor of agitator tag no.: 20-05.111, 112,113,114,115,116,172 &142 were removed for overhauling  purpose as per electrical requirement, reinstalled after overhauling & alignment done.

- All agitators top cover plate along with safety cover mesh were removed for proper ventilation                   inside reactor & as per operation requirement.

- The damaged cover plates of agitator tag no. : 20-05.116, 20-05.172 was replaced with new / repaired cover plates.

- Rest of the cover plates were reinstalled followed by rubber seal belt & safety cover mesh.

- All gear box filter element, oil level & quality of oil inspected, replaced with new as per               observation.

- Manholes of fume scrubber chamber, stack, pre-scrubber, pre-condenser, inter-condenser,                 PCST (Pre-condenser Seal Tank), CST (Condenser Seal Tank) was opened, inspected,                 cleaned & boxed up.

- Outlet elbow (1200 mm)  of 110 Flash Cooler vessel was removed and inside metal work done and then boxed up.

- Damaged outlet Pipe (1200 mm) of 112 Flash Cooler vessel was removed and New pipe erected on position.

FILTRATION SECTION

REPLACEMENT OF SHEET & LINERS OF KNIFE EDGE GATE VALVES                                            IN FILTER FEED PUMP SUCTION LINE.

FILTER FEED PUMP TAG NO. :  20-01.131 / 142

- All Suction line knife edge gate valve overhauled.

- Inspection was carried out on each part of the valves.

- Damaged sheet & Liners were replaced.

- Suction nozzles were cleaned & subject valves were boxed up.

OVERHAULING OF GYPSUM PUMP

GYPSUM SLURRY PUMP TAG NO. :  20-01.291/292/293

- Lubrication system of all gypsum pumps were checked, heat exchangers were cleaned  and corrective action taken .

- Gypsum Pump ( 20-01-293) Suction & Discharge valve opened and liner / seat replaced .

- Discharge Tee of Gypsum Pump ( 20-01-293) replaced .

MISSCELLANEOUS SHUT DOWN MAINTENANCE JOB:

- Arrangements made for draining of reactor.

- All the filters product & return flow head were opened for inspection and boxed up.

- All the filters cake wash manholes opened for inspection of Internals and then boxed up.

- All seal tank nozzles were opened for cleaning.

- Damaged Gypsum hopper was repaired.

- Process water isolation valves provided towards filter feed pump seal water line.

- Orifice meter was fixed on LP Steam line in-between SAP end to Cloth wash tank.

- Preventive maintenance of Filter Feed Pump, Product Acid Pump, and Return acid Pump, 3rd wash, 4th wash, cake wash, spillage sump pumps and booster pumps were carried out.

- Inspections of the pump internals were carried out by complete dismantling of the pump.

- Damaged / wear out internals were replaced & boxed up.

- Lubricants checked.

- Alignment & coupling done.

BELT FILTER SECTION

BELT FILTER TAG NO. :  20-22.210 ‘A’ / ‘G’

MICELLANEOUS SHUT DOWN MAINTENANCE JOBS

- Head Pulley of Belt Filter ‘’C’’ replaced .

- Replacement of Seal Strip of Belt Filter C was carried out.

- Damaged Portion of Fumes Duct was repaired by Super Vinyl Ester Resin.

- Belt Filter B,C,D,F & G pulley wash pipe & Pulley gap were minimized for better pulley washing

- All Belt Filters final wash buckled pipe changed.

- Sluice Header fume scrubber valve of Belt Filter ‘’F’’ was replaced and  Sluice Header pond water valve of Belt Filter ‘’G’’ was made free.

- All filter vacuum box lowered for inspection.

- All Filtrate hoses, manifolds & Filter feed distribution Y Piece of Filter ‘A’ to ‘G’ opened, cleaned & boxed up.

- All vapour lines, end blinds opened for inspection.

- All filter condenser manholes opened for the inspection of packing .

- Cloth wash header & cloth wash pipes dismantled for cleaning purposes.

- Distribution Tray of Belt Filter – A was repaired and leveled.

- Faulty Sluice water valves replaced.

- All head pulley & tail pulley bearing inspected & lubricated properly.

- Damaged Flap dam rubber of Filter A to F replaced.

EVAPORATOR SECTION

Top domes of all heat exchangers were removed

TUBE CLEANING OF HEAT EXCHANGER IN EVAPORATOR AREA
      HYDROJET CLEANING:

- Top domes of all heat exchangers were removed for heat exchanger cleaning .

- Tubes in the Heat exchanger ‘A’,‘B’, ‘C’, ‘D’, ‘E’, ‘F’ & ‘G’ cleaned by hydro jet cleaning .

EVAPORATOR CIRCULATION PUMP:

- Complete overhauling of P-310 “F” (Evaporation Circulation Pump) was carried out                               followed by bearing replacement, gland replacement, alignment & coupling.

REVAMPING OF COLD WELL PUMPS:

COLD WELL PUMP TAG NO.: 20 -01.622, 623,624, 625 & 626

- Complete overhauling of P-622, 623, 624, 625, & 626 was carried out followed by                           bearing replacement, gland replacement, alignment & coupling.

- P-626 discharge butterfly valve ( Size : 750 mm ) was replaced by new one .

- Discharge NRV of P-622 & P-624 were opened , overhauled & installed in position.

- All Cooling tower pumps suction strainers were opened, cleaned & boxed up.

Hydro jet cleaning of Heat Exchanger tubes

Complete overhauling of P-622

Cleaned cooling tower pumps suction strainers

REVAMPING OF HOT WELL PUMPS:

HOT  WELL PUMP TAG NO.: 20 -01-612

- Complete overhauling of P-612 was carried out followed by  bearing replacement, gland replacement, alignment & coupling

- Discharge NRV of P-611 & P-616 were opened, overhauled & installed in position.

ACID STORAGE AREA

- P-494 & P-495 (Evaporator Feed Pump) suction & discharge headers dismantled,                                   de-choked & boxed up. (Picture attached below)

Discharge Header of P-494/P-495

- P-496 & P-498 (Weak acid transfer Pump) suction headers dismantled, de-choked & boxed up.

Suction Headers of P-496/P-498

- Damaged manhole of New Pump Tank was replaced by fabricated new SS manhole. Further manhole potion was rubber lined & brick lined .

REVAMPING OF EVAPORATOR FLASH CHAMBER – ‘’F’’

- Vessel was opened, Inside metal work was carried out at different location of the vessel and rubber lining was carried out, then boxed up .

COOLING TOWER  AREA:

- Scaffolding was made inside all cells of Cooling tower & cleaned .

- Deposition on cooling tower fan blades ( 611-618)  were removed, blade angle checked and aligned.

- Cooling Tower top header flow control valve (3 – Road Side), (5 & 8 – Plant Side) were replaced with new valves.

MISSCELLANEOUS SHUT DOWN MAINTENANCE JOB:

- Evaporator ‘B’ LP steam isolation gate valve (500 mm dia.) replaced with new valve .

--------------------------------

PAP- INSTRUMENTATION

LIST OF JOBS UNDERTAKEN DURING ANNUAL SHUTDOWN - 2015

- All weigh feeders (A/B/C/D) inspection, cleaning & maintenance done.

- 20-FV-200 A/B/C/D maintenance, checking and calibration done with their respective Flow heads.

- 20-FV-200 B control valve changed with a new valve procured under capital budget.

- Ball Mill area old damaged hand-switch junction box (JB) of Ball Mill A & C replaced with a new junction box. Same was wired afresh with installation of new hand-switches for operation of MST gate valves.

- Ball Mill – A/B/C/D all switches, RTD’s checking and calibration done. Ball Mill C inlet side damaged tube and isolation valve replaced.

- Ball Mill A/B/C/D Siemens S7 PLC new hardware configuration of modules and CPU hardware separation done for individual Ball Mills. Earlier, 02 No of Ball Mills were running through a single CPU.

Advantage: Previously, two no. of Ball mills were being run by a single CPU. Due to any fault arising in CPU, two number of ball mills were forced to shutdown thereby causing production loss.

Post modification, in case if any problem arises in a CPU, then only one ball mill shall get stopped at a time thereby saving downtime of one Ball Mill.

- Ball Mill A/B/C/D Siemens S7 PLC maintenance, cleaning, laying of the new Ethernet cables from all ball mill CP cards to HMI stations done.

- Ball Mill A/B/CD Siemens PLC, new PROFIBUS cable laying and connector installation done.

- Ball Mill A/B/C/D programming & graphics modification done.

- Modification of the SCADA as per the new program and modification of all the graphics pages for all ball mills done. All alarms, trends, control and overview page defined for all ball mills, new interlock and sequence page has been added to the SCADA.

- Checking of the auto controlling from the SCADA screen for ball mill A,B,C & D done and found working properly.

- Checking of the auto sequence from the SCADA and the control desk for the all ball mills done and found working properly

Advantage: Modification in programming software & graphics shall help in troubleshooting and shall ease fault identification thereby reducing equipment downtime in case of any fault.

- Ball Mill A/B/C/D Panels & control desk maintenance & painting work done.

BEFORE				      AFTER

BEFORE						       AFTER

- 20-FV-409/415 (Sulfuric acid control valves) cleaning, maintenance calibration and stroke checking done.

- Sulfuric Acid flow FIT-409/410/415/416 zero checking done. Their calibration also checked and found ok.

- Reactor area all JB’s, RTD’s maintenance & checking done.

- Vacuum Cooler Circulator area FIT-716, FIT-722 & FIT-727 old damaged canopies replaced with new canopies, with transmitter relocation and new tubing. All nozzles and impulse tubes were de-choked.

- Circulator 111 discharge RTD TIT-741 thermowell found damaged. Same replaced with a spare one.

- FFT area FIT-527, FIT-523, FIT-519, FIT-515, FIT-539, FIT-540, FIT-541, FIT-542 old damaged canopies changed with new canopies.

- All Belt Filter area J.B. maintenance done.

- Belt Filter Condenser Water flow FIT-810-B orifice flange tapping problem attended.

- Belt Filter PY-829 A/B/C/D/E/F/G maintenance, stroke checking & calibration done.

- Belt Filter FY-807 A/B/C/D/E/F/G maintenance, stroke checking & calibration done

- Belt Filter HV-807-2 A/C/D/F/G operation checked and found ok.

- Belt Filter HV-807-2B & HV-807-2E (Condenser Water ON/OFF) replaced with spare valves.

- Belt Filter area all air tubing checked, modified and damaged tubes replaced with new ones.

- All control valves of Filtration Section (LY-818-1 B/C/D/F/G, LY-818-2 A/B/C/D/E/F/G, LY-823 A/B/C/D/E/F/G, FY-824 A/B/C/D/G) maintenance, stroke checking and calibration done.

- Filtration area Fourth wash control valve LY-818-1E replaced with a new valve procured under capital budget.

- Filtration area Fourth wash control valve LY-818-1A replaced with a new valve procured under capital budget.

.

- Filtration area cake wash outlet control valve FY-824-E replaced with a spare valve.

- Filtration area cake wash outlet control valve FY-824-F replaced with a spare valve.

- Filtration LIT-842 A/B/C/D/E/F/G, LIT-812 A/B/C/D/E/F/G, LIT-818-2 A/B/C/D/E/F/G, LIT-818-1 A/B/C/D/E/F/G all seal tank level transmitters proper mounting and calibration done.

- Filtration-F LIT 842F, LIT-812F, LIT-818-1F & LIT-818-2F transmitters relocated and taken in line.

- All flow meters of Filtration section checking & maintenance done.

- Filtration area FIT-809-C, FIT-809-2C, FIT-809F, FIT-809-2F flowheads removed from line. Their checking, cleaning, de-scaling and maintenance done.

- Orifice plate assembly installed for measurement of LP steam flow (FIT-865) to cake wash tanks.

- Filtration area all air tubing checked, modified and damaged air tubes replaced with new tubes.

- Gypsum pumps 01.291/01.292/01.293 all pressure switches maintenance and calibration done

- Gypsum pump 01.291/01.292/01.293 Miller unit hand-switch junction box (JB) replaced with a new one. Same was wired afresh with installation of new hand-switches for operation of Miller unit gate valves.

- FIT-1004 A/B/C/D/E/F/G all transmitters checking, maintenance & calibration done.

- Evaporator area steam control valves FY-1004 A/B/CD/E/F/G stroke checking & calibration done.

- Evaporator area acid feed valves FY-1005 A/B/C/D/E/F/G stroke checking & calibration done.

- Evaporator area TIT-1006 A/B/C/D/E/F/G & TIT-1010 A/B/C/D/E/F/G all RTD’s & thermowells removed for inspection & maintenance.

- TIT-1010B & TIT-1010F RTD’s found damaged and replaced with new RTDs.

- Evaporator area FIT-1005 A/B/C/D/E/F/G & FIT-1016 A/B/C/D/E/F/G checking & maintenance done.

- Evaporator area all instruments air tubing checked, modified and damaged tubes replaced with new tubing.

- Evaporator area FIT-1113 A-G all impulse tubes & nozzle de-chocking, damaged tubes replacement and transmitter checking & maintenance done.

- Evaporator area FIT-1004 D-G (LP Steam Flow) new condensate pot taken in line and leakages attended.

- Old CHP MCC GE-Fanuc make PLC old model CPU “IC200CPU001” upgraded and replaced with new “IC200CPU005E” CPU with necessary software changes. Same was cross checked, tested and found working satisfactorily.

OLD		 NEW

- One No. of HMI Engineering station for Old CHP MCC PLC with software hooked up with DCS for monitoring and Engineering purpose.

- Old CHP MCC PLC marshalling panels wiring modification and relocation job undertaken with TB replacement, cable ferruling, lugging & termination for the whole panel

- Complete DCS hook-up job of the newly installed MCC 20 & MCC 21 comprising of feeders of Rock Conveyors, Reactor agitators, SST & MST agitators at Electrical Substation-5 was undertaken and completed successfully. Job included old cables identification, tagging, removal, relocation, new cable laying as per requirement, entry into new MCC panel with complete ferruling, lugging, termination & loop testing for all feeders hooked up with DCS.

- DCS shutdown was taken and  following jobs were performed with M/s Yokogawa service Engineers:

  - All cabinets were cleaned.

  - FCS checking and Filter cleaning done.

  - All modules in the system cabinet were racked out for cleaning.

  - All terminal boards in the marshalling cabinet were cleaned, tightened.

  - All filters removed and filter cleaning done.

  - Data backup taken by service Engineer.

  - End Point Security system (Antivirus) has been installed in all HIS and Engg. Station.

Advantages of End Point Security System are:

- Since our network is secured, there is 0% breakdown & 100% availability in Network.so results in breakdown free Operation for operators.

- There is no time delay in any response /input given by operator.

- Good efficiency in operation results in minimizing down time of Equipment’s, results in less operational Cost & Maximizing Production.

- No Panic Situation caused in case of any emergency led by failure of HIS.

- The Downtime of the HIS will be very less comparatively when the HIS failure without any security.

- The Networked DCS system without ENDPOINT SECURITY have open communication and open access for everyone to use their Pen drive to collect plant datas or other confidential official datas. Whereas CS3000 Network with ENDPOINT SECURITY has a very Closed Communication & Full Locked Down so that no datas are stolen and very much secured.

- The use of Pen drives is a major source of Viruses, End Point Security will restrict the use of pen drives  & therefore our system will not get affected by viruses.

- UPS cleaning, servicing & maintenance along with battery bank checking & inspection done with service Engineer from M/s Emerson.

EARTH PITOld Earth Pit of DCS & UPS are replaced with two New Earth Pits.

SWGR, MCC S/D JOBS DONE DURING ATR # 2015

PAP (Electrical)

| SL.NO. | DATE | SWITCH GEAR/PMCC/MCC |  | DETAILS OF JOB CARRIED OUT |
| --- | --- | --- | --- | --- |
| 1 | 29/03/2015 | B/M-C,D PLC PANELS |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking, Isolators healthiness checking were done. |
| 2 | 30/03/2015 | B/M-A,B PLC PANELS |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking, Isolators healthiness checking were done. |
| 3 | 31/03/2015 | 6.6 KV SEC-A, S/S-6 |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking, Breaker healthiness checking, Testing of closing,tripping & interlocking Ckt were done. |
| 4 | 01/04/2015 | 33 KV & 6.6 KV SEC-A, S/S-5 |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking, Breaker healthiness checking, Testing of closing,tripping & interlocking Ckt were done. |
| 5 | 02/04/2015 | 6.6 KV SEC-B, S/S-6 |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking, Breaker healthiness checking, Testing of closing,tripping & interlocking Ckt were done. |
| 6 | 03/04/2015 | 33 KV & 6.6 KV SEC-B, S/S-5 |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking, Breaker healthiness checking, Testing of closing,tripping & interlocking Ckt were done. |
| 7 | 04/04/2015 | MCC-25 |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking, Breaker healthiness checking, Testing of closing,tripping & interlocking Ckt were done. |
| 8 | 05/04/2015 | 6.6 KV SEC-B, OLD CHP A/S MCC , SEC-A |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking,Breaker healthiness checking, Testing of closing,tripping & interlocking Ckt were done. |
| 9 | 06/04/2015 | 6.6 KV SEC-A, OLD CHP A/S MCC, SEC-B A/S Emergency MCC |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking,Breaker healthiness checking, Testing of closing,tripping & interlocking Ckt were done. |
| 10 | 07/04/2015 | SIEMENS MCC RPSS MCC MLDB,PDB |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking,Breaker healthiness checking, Testing of closing,tripping & interlocking Ckt were done. |
| 11 | 08/04/2015 | NEW Emergency MCC MCC-50 , 51 , 52 |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking,Breaker healthiness checking, Testing of closing,tripping & interlocking Ckt were done. |
| 12 | 10/04/2015 | MCC-22 , 23 |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking,Breaker healthiness checking, Testing of closing,tripping & interlocking Ckt were done. |
| 13 | 11/04/2015 | BUS COUPLER SECTION OF 6.6 KV (S/S-5,S/S-6, OLD CHP) A/S MCC , MCC-25 ,50 |  | Dedusting, Busbar tightness checking, Sealing of panels, Space heater checking,Breaker healthiness checking, Testing of closing,tripping & interlocking Ckt were done. |
| 14 | 12/04/2014 | CAPACITOR BANK-1 & 2 |  | Dedusting, Terminal tightness checking were done.IR Value was recorded and found OK. |
| 15 | 30/03/2015 TO 15/04/2015 |  | NEW L&T MCC | NEW L&T MCC installation done at S/S#5 in place of MCC-20, 21 & Seal Wtr Mcc & Trial run taken for individual feeders. |
| 16 | 13/04/2015 |  | Battery Banks S/S-5,6 & Old CHP | Dedusting, Terminal tightness checking were done.Voltage of each cells were recorded and found OK. |

MOTORS OVERHAULED DURING ATR # 2015

PAP (Electrical)

| SL.NO. | DATE | MOTOR TAG NO | MOTOR DESCRIPTION | REMARKS |
| --- | --- | --- | --- | --- |
| 1 | 30/03/2015 | 20-05-111 | Reactor Agitator-01 | Spare Motor Provided |
| 2 | 31/03/2015 | 20-05-142 | Reactor Agitator-09 | Spare Motor provided |
| 3 | 31/03/2015 | 20-01-310F | Evap Circulation pump | Spare Motor provided |
| 4 | 02/04/2015 | 20-01-381 | Cooling Wtr Tfr pump |  |
| 5 | 31/03/2015 | 20-01-293 | Gypsum pump |  |
| 6 | 07/04/2015 | 20-01-113 | Vac cooler circulation pump |  |
| 7 | 05/04/2015 | 20-01-110A | Fumes Scrubber Fan |  |
| 8 | 29/03/2015 | 20-05-030 | SST Agitator |  |
| 9 | 30/03/2015 | 20-01-140 | Filter feed pump |  |
| 10 | 04/04/2014 | 20-01-210B | Spillage sump pump(NEW) | Spare Motor provided |
| 11 | 05/04/2015 | 20-01-320G | Product pump |  |
| 12 | 01/04/2015 | 20-01-293-2 | 293 GB oil pump |  |
| 13 | 01/04/2015 | 20-01-293-3 | 293 FC oil pump |  |
| 14 | 04/04/2015 | 20-01-291-2 | 291 GB oil pump |  |
| 15 | 04/04/2015 | 20-01-291-3 | 291 FC oil pump |  |
| Note: | Sr. No. 1 To 7 | are HT Motors & |  |  |
|  | Sr. No. 8 To | 15 are LT Motors. |  |  |

# Sulphuric Acid Plant

In 2014-15 SAP 1 produced 7,39,490 MT of Sulphuric acid with a Capacity Utilization of 77.6%  and the On-stream factor of 75 %

While  SAP 1 produced 8,67,326 MT of Sulphuric acid with a Capacity Utilization of 80.2%  and the On-stream factor of 85 %

The Overall performance of Sulphuric Acid Plant was as given below:

- Capacity Utilization:		79.0%

- On-stream Factor:		79.6%

- OEE:				62.8%

The SAP-1 was stopped on 4th March for 90 days shutdown for IAT revamping and Sulphur Furnace replacement. SAP-2 was stopped on 28th March for 20 days as a part of complex turnaround.

The list of jobs planned during the Annual Turnaround is attached as Annexure I.

SAP-1 Highlights:

Major jobs summary

| Sr No |  | Job | Observation / Action remarks |
| --- | --- | --- | --- |
| Air Filter and Turbo-blower |  |  |  |
| 1 | Dynavanes and air filter elements replacement |  | Job under progress |
| 2 | Asbestos sheeting in front of filter casing to reduce dust load |  | Job dropped |
| 3 | Air filter dust blower overhauling |  | Both blowers replaced with new SS304 casing |
| 4 | Turbine complete overhauling, actuators servicing, trip block servicing. |  |  |
| 5 | Blower IGV servicing and vanes bearing replacement |  | Completed |
| 6 | Blower suction bellow replacement |  | Completed |
| 7 | Lube oil reservoir cleaning and oil complete replacement |  | Done |
| 8 | Air filter DP transmitter installation and indication in DCS |  | Not done |
| 9 | Air filter back washing system all solenoid valves servicing |  | Completed |
| Sulphur pump tank and Furnace |  |  |  |
| 1 | Train 1 Sulphur VPT replacement |  | VPT was replaced with new SS tank |
| 2 | Sulphur furnace replacement (original neck – 90 deg angle) |  | Old furnace brick lining was removed in-situ, furnace was cut and replaced with new shell & dish end in a single piece, brick lining was done in-situ. (old furnace removed) (new furnace erected) Furnace brick lining neck portion design is modified (modified neck – 45 deg angle) |
| 3 | Air register and wind box replacement |  | Done. Air register guide vanes will be adjusted during plant start up by Outotec’s engineer |
| 4 | Sulphur new sampling point provision |  | Yet to be done |
| 5 | Both primary air fans overhauling |  | Done |
| 6 | Both sulphur burners overhauling |  | Done |
| Waste Heat Boiler, Economizer, Superheaters |  |  |  |
| 1 | Waste heat boiler & steaming equipment tubes external cleaning by dry ice blasting (WHB flag coil before cleaning) (SH tubes before cleaning) |  | Considerable amount of deposit were not found on the SH-1, SH-2, Economizer and the WHB side manholes opened and cleaned in October 2014. On tubes not accessible with the manholes not opened in October, there was large amount of fouling. (WHB flag coil after cleaning) (SH tubes during cleaning) |
| 2 | WHB bypass duct replacement |  | Bypass duct was badly deformed. Horizontal bellow was deformed. Bypass damper was not damaged badly. (bypass damper shaft welding was broken) Bypass bellows design was changed by Thermal Systems. Bypass duct, all 3 bellows and damper were renewed. (new bypass duct bellows) Complete support structure was replaced |
| 3 | Waste heat boiler complete insulation replacement |  | Heat recovery is expected to improve |
| 4 | Boiler bottom plate replacement and re-brick lining |  | Boiler bottom plate was badly eroded |
| 5 | Boiler CBD line new control valve was installed |  | completed |
| 6 | Start up vent damper replaced |  | Completed |
| 7 | All safety relief valves calibrated |  | Done |
| 8 | Thickness measurement of economizer bends |  | Done |
| 9 | Several spring supports in the boiler water and steam piping are being replaced |  |  |
| 10 | Critical steam valves servicing done |  | Some valves have been serviced |
| 11 | CWP servicing, lube oil cooler cleaning, MOP and EOP servicing |  | Done |
| 12 | Safety relief valve installation on flash tank |  | Not done |
| 13 | De-super heater valve isolation valves replaced |  | Completed |
| 14 | SH-2 drain line replaced |  | Done |
| 15 | Boiler area structural painting done |  | Done |
| Converter, Heat Exchanger and Gas ducts |  |  |  |
| 1 | All catalyst bed screening |  | All converter beds screening done. The top up quantity is as follows: Bed I: RR type: 18 m3 Bed II: HV type: 5 m3 Bed III: HV type: 5 m3 Bed IV: Cs type : 6 m3 HV type: 6 m3 Pressure drop reduction to be observed after plant start up |
| 2 | Converter bed I catalyst support tray repair |  | 9 trays replaced |
| 3 | Converter bed III shell aluminum coating done |  | Converter bed III central drum gas division joint was found cracked. The crack was repaired and aluminization was done |
| 3 | Expansion bellows replacement |  | Converter inlet, SH-2 inlet and bypass, Second bed outlet, Economizer outlet and IAT return line bellows replacement Other bellows were in good condition. These were painted and restored. |
| 4 | Cold heat exchanger internal inspection and repair |  | CHE bottom plate repaired and SS liner complete replacement done CHE area below bottom plate was full of sludge due to gas leakage. The area was cleaned and brick lined. The sealing wall around heat exchanger foundation was removed. CHE tubes neutralization and hydro-jet cleaning was done, but could not de-choke all the tubes. The tube condition is very good. Hot heat exchanger inside checking and cleaning done |
| 5 | All gas dampers servicing done |  | Done |
| Acid Section and HRS |  |  |  |
| 1 | IAT re-brick lining |  | IAT all saddles removed, complete brick lining removed, shell and bottom dish-end repaired and re-brick lining done Shell to dish-end joint was opened on the south side for about 120° circumference Bottom dish end inner SS plate had bulged out at several locations, which was repaired Dilution water lance was badly damaged Acid outlet nozzle joints were corroded |
| 2 | IAT candle filters washing |  | All candle filters and the top cone was removed to facilitate the brick lining job. All the candle filters were washed. 6-7 candles cages were affected. 3 candles bottom plate were badly damaged. |
| 3 | IAT acid distributors replacement |  | IAT acid distributors are being replaced with new CorfreeA10 material. |
| 4 | IAT pump tank replacement |  | The old brick lined tank replaced with Zecor material tank |
| 5 | FAT candle filters washing |  | All candle filters of FAT were washed and reinstalled |
| 6 | FAT acid distributor replacement |  | FAT acid distributor is being replaced with new CorfreeA10 material |
| 7 | DT demister pad replacement |  | New demister pad was installed |
| 8 | DT internal brick lining inspection & repair |  | All saddles were removed for brick lining inspection Gas inlet nozzle brick lining was damaged, which was repaired. Acid outlet nozzles were also damaged, which was repaired Tower inlet brick lining was in good condition |
| 9 | DT acid distributor replacement |  | DT acid distributor damaged pipes were replaced with spare CI pipes. The material of construction of DT acid distributor remains unchanged |
| 10 | All acid tower inlet pieces replaced |  | Tower inlet piece had leaked in all towers. The CI pieces were replaced with metallic pipe |
| 11 | Acid pumps overhauling |  | All acid pumps were overhauled (DT pump impeller) |
| 12 | Acid PHEs acid to water and inlet to outlet interchange |  | Interchanged |
| 13 | IAT coolers water side hydro-jet cleaning done |  | Completed. Small amount of cooling tower fills were found blocking the tube mouth |
| 14 | Acid area floor brick lining repair |  | Repair in progress |
| 15 | HRS tower, pump tank internal inspection |  | Tower condition was found good. No corrosion or foreign objects were found in side tower and pump tank |
| 16 | Heater and Pre heater tubes plugging (pre heater tubesheet) |  | Heater and pre heater were neutralized, hydro-jet cleaning done and eddy current test was done. Accrodingly 10 tubes were plugged in heater and none in preheater. (heater tubesheet before plugging) |
| 17 | HRS boiler |  | HRS boiler heat exchanger had 3-4 saddle pieces stuck in the tubes. The pieces were removed. |
| 18 | HRS diluter lining repair |  | HRS diluter Teflon lining was found damaged (shrunk) near outlet flange. The diluter piece is sent for shop repair to Chennai |
| 19 | HRS internals |  | Internal parts of acid dilution lance, steam injection pipe, steam line and strainer were in good condition |
| 20 | HRS steam injection valve, vent valve and isolation valve servicing |  | Steam flow is expected to increase |
| 21 | Additional LT to be installed in HRS pump boot |  | Not taken up |

Sulphuric Acid Plant 1

Preface:

Plant was stopped for replacement of Sulphur Furnace along with shell & brick lining; major revamping of Intermediate absorption tower (IAT) and annual inspection of boiler by AD (F&B). Other jobs like overhauling of turbo blower train, boiler bypass duct rectification, replacement of IAT Pump tank, various bellows in the gas section etc. were also planned.

Sulphur Furnace: Complete replacement of Sulphur furnace shell including the  brick lining and damaged Air Registers.

- All the old brick lining inside the sulphur furnace was completely dismantled.

- Both Air Registers & Wind boxes were dismantled after cutting the furnace inlet air duct.

- Old sulphur furnace shell was disconnected from the boiler by cutting and removed from position.

- Newly fabricated modified sulphur furnace shell was positioned after carrying out pneumatic test.

- Modified brick lining carried out in the sulphur furnace.

- Heat dry out for curing of the new brick lining carried out at 550 Deg.C

Old Furnace Removal					New Furnace Erection

New Modified Brick Lining

Old lining design with 90 Deg.		            Modified design with 45 Deg.

Other activities performed during sulphur furnace replacement

- New air registers were installed and commissioned.

- Repairing of damaged wind boxes.

- Secondary Air dampers were overhauled.

- Both the fabric expansion joints were replaced with new fabric.

Boiler bottom Plate: Complete replacement of boiler bottom plate including the old brick lining.

- All the old brick lining in the boiler bottom was completely dismantled.

- All the bottom plates were replaced with new plates of boiler quality after cutting and removing the old damaged plates.

- Brick lining was done with new bricks.

- Heat dry out was carried out along with the sulphur furnace.

Old damaged boiler bottom plate cutting & removal

New plate erection & welding

New brick lining

Other activities performed during boiler bottom plate replacement

- Cleaning of the boiler inlet ring header.

- Thickness survey of the inlet ring header.

Boiler Gas Bypass Duct Modification: Complete boiler gas bypass duct was re - designed and modifications done accordingly.

- The boiler gas bypass duct was re – designed by OEM, M/s Thermal Systems (Hyd.) Pvt. Ltd., Hyderabad to solve problem of frequent failure of the duct.

- Accordingly modified spring supports and metallic expansion bellows were procured.

- Complete duct was dismantled, new duct fabricated and erection done with modified spring supports and modified metallic expansion bellows.

New duct with modified bellows erection.

Modified Spring Supports ready for erection

Other activities performed during gas bypass duct modification

- All the damaged / corroded structural members of the boiler platforms and steam drum platforms were replaced with newly painted structural members.

- Damaged boiler start up vent damper was replaced with new pneumatic operated damper.

- Old damaged thermal insulation was completely removed and new thermal insulation was applied on bypass and outlet ducts.

Overhauling of Turbo-blower train-Last Overahuling of the turbine was done in the year-2011 hence, decision was taken to undertake the overhauling of the complete train.

I. Major jobs carried out :

- Dismantling work started on 23-4-15.

- Turbine, Gear Box & Air Blower overhauled and boxed up on 18.05.15 .

- Oil flushing is carried out before Commissioning.

- Commissioning on 5-6-2015

II. TECHNICAL SPECIFICATIONS:

Turbine:

Make					:	 SIEMENS

Model					:	 GG 26/25-2

Type					:	 SINGLE CASING BACK PRESSURE TURBINE

Inlet steam pressure			:	 60.2   Kg/Cm2

Exhaust steam pressure             	:           3.8 kg/cm2    ±0.25

Inlet steam temperature		:	 480 C0

Rated Output				:	 6.237MW

Range of  speed			:	 7057- 13598 RPM

Turbine Trip Speed			:	14958 RPM

Direction of rotation when

Viewed from Turbine front		:           C.C.W

Location                                       	:           SAP -1

Rotor weight				:           332Kg

Top Casing weight			:           3900Kg

Bottom Casing weight		:           1900Kg

Gear Box:

Make					:	Renk

Speed					:	3160 RPM

Air Blower:

Make					:	KK & K

Gear Ratio				:	4.303

Speed					:	3160 RPM

III Preface: The contract for Major overhaul of the Turbine, Gear Box & Air Blower was awarded to M/S Rotodyne Engineering Services Pvt Ltd in April, 2015. M/S Rotodyne people were mobilized on 19-4-2015. Work started on 23-4-2015.

Following are the observations made:

1. Radial keys are found struck up in b/w casing and Bearing pedestals.

2. On Rotor, 1ST stage (small) fins found damaged.

3. ESV steam side, valve cone to seat contact found less.

4. Servomotor ball bearings and Teflon bushes were not found in healthy condition..

5. ESV “o” rings were found in a condition that needed replacement.

6. Sealing fins on Rotor at B.P Gland area got damaged.

7. All the 3 Control Valve Spindles rusted and not operating smoothly.

8. Journals of Turbine Rotor, Pinion Shaft, Gear Shaft & Blower shaft found rusted and changed to blackish colour.

9. Some of the Tilting pads of Turbine journal bearings and Thrust pads are found worn out and clearance are more than desired.

10. Journal Bearings of Pinion Shaft in Gear box have found more  clearance than desired

11. Drain oil lines at oil seals of Air blower found partially choked.

12. At two places, Pinion teeth (G Box) found peeled off about 3mm width and 10mm length.

Fins on Front Steam gland got Damaged

Lifting of Turbine Rotor

Peeling off Teeth on pinion

III. ASSEMBLY PROTOCOLS on major overhauling of 6.237MW DRIVE  TURBINE For AIR BLOWER :

Turbine:

1.00 BEARING CLEARANCES (MM)

1.01 TILTING PAD JOURNAL BEARING:-        (DIA 100)

Total number of tilting Pads = 5 No’s,                  3-nos in top position,            2 no’s in bottom position

|  | Old tilting pads |  | New tilting pads |  |
| --- | --- | --- | --- | --- |
| Sl no | Front brg pads thickness(mm) | Rear brg pads thickness(mm) | Front brg pads thickness(mm) | Rear brg pads thickness(mm) |
| 1 | 14.97 | 14.98 | 15.04 | 15.06 |
| 2 | 14.96 | 14.96 | 15.05 | 15.06 |
| 3 | 14.98 | 14.94 | 15.05 | 15.05 |
| 4 | 14.95 | 14.95 | 15.03 | 15.04 |
| 5 | 14.96 | 14.96 | 15.03 | 15.04 |

Oil clearances: -

Front                                                   Rear

Front journal OD 		= 99.84                  	                               = 99.84

Bearing Shell  ID without pads 	= 130.10                                                        = 130.10

Pad thickness 			= 15.04		                   = 15.05

15.04 X 2 = 30.08                                          15.05 X 2 = 30.10

Oil clearance =	130.10-(99.84+30.08) = 0.18mm  	              130.10-(99.84+30.10) =0.16mm

1.02 THRUST BEARING PADS:

Total 16 pads,               8pads in each side,           4 in bottom,            and 4 in top

| SL. no | Active side(New) | Non active side(old) |
| --- | --- | --- |
| 1 | 20.03 | 19.96 |
| 2 | 20.03 | 19.97 |
| 3 | 20.03 | 19.96 |
| 4 | 20.03 | 19.96 |
| 5 | 20.03 | 19.95 |
| 6 | 20.03 | 19.97 |
| 7 | 20.03 | 19.96 |
| 8 | 20.03 | 19.96 |

CLEARANCE ;            BEFORE O/H  0.42                                          After o/h: 0.35 mm.

DPT and UT of tilting pads

Gear Box:

BEARING CLEARANCES:

Pinion Shaft:		              Before overhauling			After overhauling

Front		Rear				Front			Rear

Bearing bore dia	100.12		100.14				100.02			100.04

Journal Dia		  99.85		  99.85				  99.84			  99.84

Oil Clearance		    0.27		    0.29				    0.18			    0.20

Gear Wheel Shaft:          Before overhauling				After overhauling

Front		Rear				Front			Rear

Bearing bore dia	160.02		160.03				160.02			160.03

Journal Dia		159.82		159.84				159.80			159.82

Oil Clearance		    0.20		    0.19				    0.22			    0.21

Thrust Bearing clearance of Gear shaft		0.18mm

Backlash between Gear and Pinion	               	0.43mm

Air Blower:

BEARING CLEARANCES:

TILTING PAD JOURNAL BEARING:-        (DIA 200 & 250)

Total number of tilting Pads = 4 No’s,                  2-nos in top position,            2 no’s in bottom position

|  | Tilting pads |  |
| --- | --- | --- |
| Sl no | Front brg pads thickness(mm) | Rear brg pads thickness(mm) |
| 1 | 30.07 | 32.64 |
| 2 | 29.97 | 32.64 |
| 3 | 29.96 | 32.64 |
| 4 | 30.01 | 32.63 |

Front                                                Rear

Front journal OD 		         = 199.65                                    = 249.49

Bearing Shell  ID without pads       = 260.02                                   = 315.15

Pad thickness 			         = 30.00		                 = 32.64

3   0.0 X 2 = 60.00                                   32.64 X 2 = 65.28

Oil clearance =	260.02-(199.65+60.00) = 0.37mm  	              315.15-(249.49+65.28)=0.38mm

Interference=		0.05 to 0.07mm				   0.05 to 0.07mm

Axial Distance between thrust collars =174.60

Axial Distance between thrust pads    =174.00

Oil clearance				0.60mm

Blower Bearings

2.00 OIL GLAND CLEARANCES (MM):

2.01 RADIAL:

FRONT

BEFORE OVERHAULING	                                              AFTER OVERHAULING

L=0.0500

B=0.00

R=0.0500

L=0.055

B=0.03

R=0.05

REAR

BEFORE OVERHAULING	                                              AFTER OVERHAULING

L=0.10

B=0.05

R=0.10

L=0.10

B=0.05

R=0.10

2.02 AXIAL:

FRONT

LEFT 				RIGHT

SA3                      3.38				3.40

SA4		   3.16				3.18

REAR

LEFT 				RIGHT

SA3                      2.66				2.66

SA4		   4.26				4.24

4.0 CENTERING READINGS

BEFOR OVERHAULING                                     AFTER OVERHAULING

0.00

+.07

REC

+.05

0.00

+.00

ROG

+.08

0.00

+.03

RSG

+.12

0.00

-.12

FSG

+.14

0.00

-.08

FOG

+.10

0.00

-.11

TB

+.14

0.00

-.10

FOC

+.16

ROC

+.04

+.12

0,000

+0.08

+0.10

0.00

+.090

REC

+.15

0.00

+.14

ROG

+.10

0.00

+.08

RSG

+.20

0.00

-.12

FSG

+.18

0.00

-.02

FOG

+.16

0.00

+.16

TB

+.06

0.00

+.08

FOC

-.38

ROC

+.06+.066

-.20

0,000

+0.10

+0.14

5.00 ROTOR FLOAT

Before overhauling   Front       = 0.92mm,                     after overhauling front   = 0.95mm

Rear   =2.68 mm                                   Rear   = 2.64 mm

Total = 3.60mm	      Total  = 3.58mm

DISTANCE B/W SHAFT ENDS

A). Turbine to Gear box

333.64

333.65

333.60

289.73mm

289.78mm

289.78mm

B) Gear box to blower

6.00 ALIGNMENT READINGS (MM):-

6.01 TURBINE TO GEAR BOX (DIAL READINGS ON GEAR BOX)       Type of coupling : Gear

type

Coupling float : 7.0mm

BEFORE OVERHAULING:

0.00                                                                                                              0.00

+0.39

R

-0.04

+0.28

-0.01

A

+0.68

-0.02

AFTER  OVERHAULING:

0.00                                                                                                              0.00

+0.12

R

-0.05

+0.31

+0.02

A

+0.41

+0.01

6.02 GEAR BOX TO BLOWER (DIAL READING  ON BLOWER)

BEFORE OVERHAULING: -                                                                Type of coupling : Membrane

type

0.00                                                                                                              0.00

-0.61

R

-0.00

-0.22

-0.02

A

-0.80

+0.05

AFTER  OVERHAULING:

0.00                                                                                                              0.00

-0.58

R

-0.01

-0.25

+0.03

A

-0.82

+0.02

7.00 ROTOR RUN OUTS:-

| Sl.No | Position | Run out in mm |
| --- | --- | --- |
| 1 | Trip lever | 0.01 |
| 2 | Thrust collar front/ rear | 0.01 / 0.01 |
| 3 | Front journal | 0.00 |
| 4 | Front oil gland | 0.01 |
| 5 | Front steam gland | 0.01 |
| 6 | B.P gland | 0.01 |
| 7 | RSG | 0.01 |
| 8 | ROG | 0.01 |
| 9 | REAR JOURNAL | 0.00 |
| 10 | COUPLING HUB | 0.01 |

8.00 STEAM FLOW PATH READINGS (MM):

8.01 AXIAL CLEARANCES:

a) Diaphragms

| Stage | Position | BEFORE O/H |  | AFTER O/H |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Left | Right | Left | Right |
| 1 | A | 8.10 | 8.20 | 8.20 | 8.20 |
|  | B | 4.90 | 5.00 | 4.90 | 4.95 |
|  | C | 4.95 | 5.00 | 5.00 | 5.00 |
|  | D | 6.00 | 6.10 | 6.10 | 6.00 |
| 2 | A | 4.00 | 4.10 | 4.00 | 4.10 |
|  | B | 3.20 | 3.10 | 3.40 | 3.50 |
|  | C | 1.30 | 1.20 | 1.30 | 1.30 |
|  | D | 3.90 | 3.90 | 4.00 | 4.10 |
| 3 | A | 4.20 | 4.30 | 4.40 | 4.20 |
|  | B | 3.50 | 3.80 | 3.50 | 3.80 |
|  | C | 1.50 | 1.50 | 1.50 | 1.50 |
|  | D | 4.10 | 3.90 | 4.40 | 4.30 |
| 4 | A | 4.20 | 4.30 | 4.20 | 4.00 |
|  | B | 4.20 | 4.20 | 4.10 | 4.10 |
|  | C | 2.20 | 2.00 | 2.00 | 1.80 |
|  | D | 4.20 | 4.10 | 4.20 | 4.30 |
| 5 | A | 4.10 | 4.00 | 4.10 | 3.90 |
|  | B | 5.10 | 5.10 | 5.00 | 5.10 |
|  | C | 3.00 | 3.00 | 3.00 | 2.80 |
|  | D | 4.00 | 3.90 | 4.20 | 4.20 |
| 6 | A | 4.10 | 4.10 | 3.90 | 3.80 |
|  | B | 6.50 | 6.70 | 6.50 | 6.40 |
|  | C | 4.40 | 4.30 | 4.20 | 4.10 |
|  | D | - | - | - | - |
| 7 | A | - | - | - | - |
|  | B | 7.60 | 7.60 | 6.90 | 7.40 |
|  | C | 5.50 | 5.40 | 5.50 | 5.20 |
|  | D | 7.40 | 7.10 | 7.40 | 7.50 |

b)Front steam gland

|  | BEFORE OVER HAULING |  |  |  | AFTER OVERHAULING |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Fin no | Left |  | Right |  | Left |  | Right |  |
|  | Front | Rear | Front | Rear | Front | Rear | Front | Rear |
| 1 | 1.00 | 1.95 | 0.95 | 2.05 | 1.00 | 2.00 | 1.05 | 2.00 |
| 2 | 0.90 | 1.90 | 0.95 | 1.95 | 0.90 | 2.00 | 1.00 | 2.00 |
| 3 | 1.00 | 1.85 | 0.95 | 1.90 | 1.00 | 1.95 | 0.95 | 2.05 |
| 4 | 1.00 | 1.90 | 1.10 | 1.95 | 0.95 | 1.95 | 1.00 | 2.10 |
| 5 | 1.10 | 2.00 | 1.00 | 1.90 | 1.00 | 2.00 | 1.00 | 2.00 |
| 6 | 1.20 | 1.95 | 1.10 | 1.95 | 1.10 | 2.00 | 1.05 | 2.10 |
| 7 | 1.10 | 2.10 | 1.00 | 2.00 | 1.10 | 2.10 | 1.00 | 2.00 |
| 8 | 1.00 | 2.00 | 1.00 | 2.00 | 1.05 | 2.00 | 1.00 | 2.05 |
| 9 | 0.95 | 1.95 | 1.00 | 2.00 | 1.00 | 2.00 | 0.95 | 2.00 |
| 10 | 1.00 | 2.00 | 1.00 | 2.15 | 1.10 | 2.05 | 1.00 | 2.00 |
| 11 | 1.10 | 1.90 | 0.95 | 2.00 | 1.00 | 2.00 | 1.05 | 2.05 |
| 12 | 1.00 | 1.95 | 1.00 | 2.00 | 1.10 | 2.00 | 1.00 | 2.05 |
| 13 | 0.90 | 2.10 | 1.00 | 2.10 | 1.05 | 2.00 | 0.95 | 2.00 |
| 14 | 0.95 | 2.15 | 1.00 | 2.10 | 1.00 | 2.10 | 1.00 | 2.10 |
| 15 | 1.25 | 1.90 | 1.10 | 2.00 | 1.10 | 2.00 | 1.05 | 2.05 |

c) B.P gland

|  | BEFORE OVERHAULING |  |  |  | AFTER OVERHAULING |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SLNO | Left |  | Right |  | Left |  | Right |  |
|  | Front | Rear | Front | Rear | Front | Rear | Front | Rear |
| 1 | 1.05 | 2.00 | 1.10 | 2.20 | 1.10 | 2.30 | 1.10 | 2.30 |
| 2 | ------ | ---- | 1.20 | 2.30 | 0.95 | 2.25 | 0.95 | 2.25 |
| 3 | 1.40 | 1.90 | 1.30 | 2.10 | 1.20 | 2.30 | 1.20 | 2.30 |
| 4 | ----- | ---- | 1.25 | 2.20 | ---- | ----- | ---- | ----- |
| 5 | 1.50 | 2.20 | 1.10 | 2.20 | 1.30 | 2.20 | 1.300 | 2.20 |
| 6 | 1.40 | 2.00 | 1.20 | 2.00 | 1.20 | 2.20 | 1.20 | 2.20 |
| 7 | 1.50 | 2.00 | 1.10 | 2.10 | 1.40 | 2.20 | 1.40 | 2.20 |
| 8 | ---- | ----- | 1.00 | 2.20 | ---- | ----- | ---- | ----- |
| 9 | 1.40 | 2.10 | ---- | ---- | 1.10 | 2.30 | 1.10 | 2.30 |
| 10 | 0.90 | 2.40 | 1.20 | 2.00 | 1.20 | 2.20 | 1.20 | 2.20 |
| 11 | 1.00 | 1.95 | 1.30 | 2.00 | 1.20 | 2.10 | 1.20 | 2.10 |
| 12 | 1.20 | 2.10 | ----- | ---- | ----- | ---- | ----- | ---- |
| 13 | 1.00 | 2.00 | 1.30 | 2.20 | 1.20 | 2.30 | 1.20 | 2.30 |
| 14 | ---- | ---- | ----- | ---- | 1.10 | 2.20 | 1.10 | 2.20 |
| 15 | 0.90 | 2.30 | 1.10 | 2.10 | ---- | ---- | ---- | ---- |
| 16 | 1.30 | 2.20 | 1.00 | 2.10 | 1.20 | 2.20 | 1.20 | 2.20 |
| 17 | 1.50 | 2.10 | 1.10 | 2.00 | 1.10 | 2.30 | 1.10 | 2.30 |
| 18 | 1.10 | 2.20 | 1.20 | 2.10 | 1.10 | 2.30 | 1.10 | 2.30 |
| 19 | 1.00 | 2.30 | 1.00 | 2.00 | 1.00 | 2.20 | 1.00 | 2.20 |

d) Diaphragms

|  | BEFORE OVERHAULING |  |  |  | AFTER OVERHAULING |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STAGES | Left |  | Right |  | Left |  | Right |  |
|  | Front | Rear | Front | Rear | Front | Rear | Front | Rear |
| “A”Wheel | 5.20 | 6.00 | 5.00 | 6.30 | 5.20 | 6.20 | 5.20 | 6.20 |
| 1st | 4.00 | 4.50 | 4.00 | 4.40 | 4.30 | 4.30 | 4.20 | 4.30 |
| 2nd | 4.70 | 4.60 | 4.70 | 4.70 | 4.80 | 4.60 | 4.80 | 4.60 |
| 3rd | 5.40 | 5.10 | 5.30 | 5.20 | 5.50 | 5.20 | 5.40 | 5.30 |
| 4th | 6.20 | 6.30 | 6.10 | 6.30 | 6.30 | 6.30 | 6.20 | 6.30 |
| 5th | 7.00 | 7.30 | 7.20 | 7.30 | 7.10 | 7.00 | 7.00 | 7.10 |
| 6th | 8.80 | 8.60 | 8.65 | 8.70 | 8.90 | 8.80 | 8.90 | 8.80 |

e) Rear steam gland:

|  | BEFORE OVERHAULING |  |  |  | AFTER OVER HAULING |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Fins | Left |  | Right |  | Left |  | Right |  |
|  | Front | Rear | Front | Rear | Front | Rear | Front | Rear |
| 1 | 1.00 | 2.00 | 1.10 | 1.95 | 1.00 | 2.00 | 1.00 | 2.10 |
| 2 | 0.95 | 2.00 | 1.00 | 2.10 | 1.00 | 2.00 | 1.05 | 2.10 |
| 3 | 1.00 | 2.40 | 1.00 | 2.00 | 1.00 | 2.10 | 1.00 | 2.00 |
| 4 | 1.00 | 2.35 | 1.20 | 2.20 | 1.00 | 2.15 | 1.05 | 2.05 |
| 5 | 1.10 | 2.35 | 1.00 | 2.20 | 1.10 | 2.15 | 1.10 | 2.05 |
| 6 | 1.20 | 2.20 | 0.95 | 2.30 | 1.00 | 2.10 | 1.00 | 2.10 |
| 7 | 1.10 | 2.25 | 1.20 | 2.00 | 1.10 | 2.15 | 1.10 | 2.10 |
| 8 | 1.00 | 2.50 | 1.10 | 2.05 | 1.00 | 2.20 | 1.05 | 2.10 |
| 9 | 0.95 | 2.60 | 1.20 | 1.95 | 1.00 | 2.20 | 1.05 | 2.10 |
| 10 | 1.00 | 2.50 | 1.10 | 2.00 | 1.00 | 2.20 | 1.00 | 2.20 |
| 11 | 1.10 | 2.55 | 1.20 | 2.30 | 1.10 | 2.25 | 1.10 | 2.15 |
| 12 | 1.30 | 2.40 | 1.00 | 2.40 | 1.10 | 2.20 | 1.10 | 2.10 |
| 13 | 1.20 | 2.20 | 1.10 | 2.30 | 1.00 | 2.20 | 1.00 | 2.10 |

8.02 RADIAL CLEARANCES:

- FRONT STEAM GLAND

BEFORE OVERHAULING

Gland fins to rotor	                                               Rotor fins to gland

L=0.45

R=0.505

L=0.55

R=0.45

AFTER OVERHAULING

Gland fins to rotor	                                                Rotor fins to gland

L=0.40

R=0.450

L=0.50

R=0.55

b)  B.P.  GLAND

BEFOR OVERHAULING

Gland fins to rotor	                                                            Rotor fins to gland

L=0.55

R=0.60

L=0.50

R=0.45

AFTER OVER HAULING

Gland fins to rotor	                                                             Rotor fins to gland

L=0.45

R=0.50

L=0.45

R=0.45

c) REAR STEAM GLAND

BEFORE OVERHAULING

Gland fins to rotor	                                                            Rotor fins to gland

L=0.55

R=0.50

L=0.60

R=0.50

AFTER OVERHAULING

Gland fins to rotor	                                                            Rotor fins to gland

L=0.40

R=0.45

L=0.40

R=0.45

d)”A” WHEEL

|  | BEFORE OVERHAULING |  |  |  | AFTER OVER HAULING |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Diaphragm | Rotor fins to diaphragm |  | Diaphragm fins to rotor |  | Rotor fins to diaphragm |  |  | Diaphragm fins to rotor |  |  |
|  | LEFT | RIGHT | LEFT | RIGHT | LEFT | RIGHT |  | LEFT | RIGHT |  |
| 1st | 1.40 | 1.45 | ----- | ---- | 1.30 | 1.35 |  | ----- | ---- |  |
| 2nd | 1.45 | 1.45 | 0.90 | 0.90 | 1.30 | 1.25 |  | 0.85 | 0.80 |  |
| 3rd | 1.35 | 1.50 | 0.90 | 0.95 | 1.35 | 1.35 |  | 0.85 | 0.80 |  |
| 4th | 1.30 | 1.30 | 0.95 | 0.95 | 1.30 | 1.25 |  | 0.75 | 0.70 |  |
| 5th | 1.25 | 1.25 | 0.95 | 0.90 | 1.30 | 1.30 |  | 0.75 | 0.70 |  |
| 6th | 0.90 | 1.00 | 0.90 | 0.90 | 0.80 | 0.80 |  | 0.65 | 0.70 |  |

BEFORE OVERHAULING			                    AFTER OVERHAULING

L=5.20

R=5.20

L=5.20

R=5.20

e) Radial fin clearances

9.00 FINAL THERMAL GAPS OF DIAPHRAGMS AT PP LEVEL

Before

| Stage | BOTTOM HALF |  | TOP HALF |  |
| --- | --- | --- | --- | --- |
|  | Left | Right | LEFT | RIGHT |
| Steam Chamber | -0.40 | -0.45 | -0.15 | -0.25 |
| 1st | -0.45 | -0.50 | -0.18 | -0.20 |
| 2nd | -0.20 | -0.25 | -0.45 | -0.50 |
| 3rd | -0.30 | -0.35 | -0.10 | -0.15 |
| 4th | -0.60 | -0.65 | -0.10 | -0.12 |
| 5th | -0.45 | -0.50 | +0.10 | +0.12 |
| 6th | -0.10 | -0.15 | +0.10 | +0.12 |

After

| STAGE | TOP HALF |  | BOTTOM HALF |  |
| --- | --- | --- | --- | --- |
|  | LEFT | RIGHT | LEFT | RIGHT |
| Steam Chamber | -0.45 | -0.40 | -0.25 | -0.15 |
| 1st | -0.50 | -0.45 | -0.20 | -0.18 |
| 2nd | -0.25 | -0.20 | -0.50 | -0.45 |
| 3rd | -0.35 | -0.30 | -0.15 | -0.10 |
| 4th | -0.65 | -0.60 | -0.12 | -0.10 |
| 5th | -0.50 | -0.45 | +0.12 | +0.10 |
| 6th | -0.15 | -0.10 | +0.12 | +0.10 |

10.00 SAFETY  SYSTEM:   Radiai and axial clearances between over speed governor. trip lever and thrust bearing safety device

BEFORE OVERHAULING

AXIAL CLEARENCE:      FRONT    =         1.15		REAR = 1.30

RADIAL CLEARENCE   R = 0.80

AFTER OVERHAULING

AXIAL CLEARENCE:      FRONT    =         1.20		REAR = 1.35

RADIAL CLEARENCE   R = 0.85

11.00 CALIBRATION READINGS of governing system

| READING SLNO | Gov. output (Amp) | Servomotor II |  | Servomotor I |  | Servomotor III |  | Sec. oil pressure (Kg/cm2) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Protocol | Actual | Protocol | Actual | Protocol | Actual |  |  |
| 1 | 0 | 40 | 42 | 38 | 38 | 34 | 35 | 0 | 0 |
| 2 | 4 | 40 | 42 | 38 | 38 | 34 | 35 | 1 | 1.2 |
| 3 | 6 | 40 | 40 | 36 | 37 | 34 | 33 | 1.6 | 1.6 |
| 4 | 8 | 38.5 | 40 | 34.5 | 37 | 34 | 33 | 2.1 | 1.9 |
| 5 | 12 | 33.5 | 38 | 30 | 36 | 30 | 29 | 3.2 | 2.6 |
| 6 | 16 | 29.5 | 37 | 30 | 31 | 25 | 27 | 4.6 | 3.8 |
| 7 | 20 | 29.5 | 35 | 30 | 29 | 25 | 25 | 4.6 | 4.2 |

12.00 SPARES CONSUMED:

1. Axial thrust ball bearings            - 3 Nos

2. ESV “O” rings                                 - 2 Nos

3. Journal bearing tilting pads        - 10 Nos (Front and Rear)

4. Thrust pads on one side              -  8 Nos (1Set)

4. Gaskets of Oil and Steam lines

VI.SUMMERY REPORT:

DATE: 23.04.2015

1. Gear coupling b/w turbine & gear box dismantled.
2. Flexible coupling b/w G.box & blower dismantled.
3. All circulation oil lines are disconnected.
4. Gear wheel coupling float checked & recorded.

DATE: 24.04.2015

1. Dismantled the Steam inlet, outlet and vent pipe connections.
2. Dismounted the Stop valve and top bearing pedestals.
3. Took the initial alignment reading b/w turbine rotor to gear box.
4. Took the distance b/w shaft ends of Gear box and Blower.

DATE: 25.04.2015

1. Dismounted Servo motor from the casing and kept on floor for cleaning.
2. Steam exhaust pipe dismantled and kept on the ground.
3. Turbine casing pp bolts are loosened, few are struck-up, to be tried by gas heating.

DATE: 26.04.2015

1. Servo motor -1 overhauling was started.
2. Removed coupling bolts of each servomotor.
3. Removed the struck studs & Nuts of turbine casing pp with the help of gas heating. Still 3 numbers     didn’t come.
4. Exhaust pipe completely removed with the help of heating.
5. Servo motor cone bracket studs removed.

DATE: 27.04.2015

1. Turbine exhaust pipe removed, after completion of roof cutting.
2. Turbine rear bearing end covers removed.
3. Rotor stand as well as sleepers are positioned.
4. Turbine top casing could not be lifted due to 3 more studs & nuts struck-up.
5. Servomotor disassembled , cleaned. Plunger bearing is not matching with old one.

DATE: 28.04.2015

1. Removed parting plane bolts with gas heating finally.
2. Dismantled the Top halves of journal and thrust bearings.
3. Lifted the top casing and placed on sleeper beds.
4. Servomotor-1 assembled, Servomoto-2 dismantled, cleaned but internal cone found damaged and recommended for replacement.

DATE: 29.04.2015

1. Removed the top steam and oil glands.
2. Prepared fixtures for holding dial gauges to measure centering and Alignment readings.
3. Gear box top cover dismantled, placed on floor.
4. Servomotor-2 boxed up with new inner cone.

5. Steam strainer was removed from ESV.
6. Servo motor brackets removed from casing, cleaned.
7. Top casing reversed for sand blasting.

DATE: 30.04.2015

1. Taken required reading of rotor.
2. Measured backlashes, float readings of gear box.
3. Removed pinion shaft of gear box.
4. Removed Turbine rotor and placed on stand for cleaning & sand blasting.
5. Upper & lower casing diaphragms were removed.

DATE: 01.05.2015

1. Taken bearings clearances of pinion shaft and recorded.
2. Turbine upper and lower casings cleaned and also parting planes.
3. Sand blasting done on upper casing diaphragms. 
4. Observed rotor fins got damaged, Hard layer observed peeled off pinion & gear teeth. And photos enclosed.

DATE: 02.05.2015

1. Rotor and Bottom steam glands sand blasting was done.
2. Gear wheel shaft lifted from position and send to work shop for repair.
3. Lubricating oil supply lines in gear box were removed, cleaned and fitted back.
4. Measured the bearing interferences and clearances.

DATE: 04.05.2015

1. Assembled the servomotor-3.
2. E S valve cone lapping and blue matching has been done, Boxed up
3. Gear box cleaned with buffering process.
4. Gear wheel and pinion teeth along with journals were polished.
5. Cleaning of Valve cones of governing valves under progress.

DATE: 05.05.2015

1. Turbine steam inlet & outlet pipe line lapping were done..
2. Rotor thrust collar area and pads polishing has been done.
3. Cleaned the Gear wheel, pinion shafts.
4. cleaning of Flexible couplings (gear-input & membrane-output) done.

DATE: 06.05.2015

1. Diaphragms fixed in turbine upper and lower casings.
2. Tripping device cleaning was done.
3. Pinion and Gear wheel shafts are positioned on the lower casing.

DATE: 07.05.2015

1. Gear box assembly was done.
2. Diaphragms PP levels measured and recorded on both planes. 
3. Turbine Bearings shifted to workshop for U.T , DPT & recollected.
4. Dismantled bearing housing of blower then removed the top bearings.

DATE: 08.05.2015

1. Rotor positioned and alignment under progress.
2. Turbine upper casing reversed.
3. Assembled E.S.V steam side in casing.
4. Governing valves assembled in casing.
5. Turbo Blower bellow one side flange studs and nuts removed.

DATE: 09.05.2015

1. Turbo Blower bellow, another side flange studs and nuts removed.
2. Blower Bellow removed from the position.
3. New bellow shifted from store to work place.
4. Checking & rectification of Turbine rotor centering under progress.
5. At Upper casing area, scaffolding and tent removed.

DATE: 12.05.2015

1. Axial and Radial clearances of ‘A’ wheel & Diaphragms checked & Recorded.

2. Top halves of steam glands assembled.

3. Studs are assembled on Bottom half PP.

4. Placed the taper wedges under the Blower impeller blades for supporting.

5. Removed the blower bearings and conducted the DP and UT test.

DATE: 13.05.2015

1. Turbine casing assembly was done.
2. P.P studs and nuts tightening were done.
3. Gaskets prepared for drain pipe assembly.

DATE: 14.05.2015

1. Placed upper halves of front and rear bearing pedestal covers.
2. Lifted and positioned the steam inlet pipe, bolts tightening was done.
3. Cleaning of Steam & casing Drain pipes ensured and connected.
4. ESV actuator cylinder assembly completed.
5. Blower thrust cum journal bearing and pads cleaned.
7. Bellow clamps prepared to compress for positioning of bellow.

DATE: 15.05.2015

1. Suction side bellow assembly was done.
2. Blower journal cum thrust bearing assembly was done.
3. Completed the blower bearings box up.
4. Turbine steam exhaust pipe lifted, positioned and tightened with fasteners.
5. Oil lines were connected to bearings, SM actuator and Gov. Systems etc.

DATED: - 31.05.2014 TO 09.06.2014

1. Bearings in IGV replaced.

2. Wire meshes were assembled in all lube oil inlet to bearings for flushing.

3. Oil flushing started on 3-6-2015 and completed on 4-6-2015.

4. Wire meshes were removed from bearing inlets. Tuning of Gov. System completed on 5-6-2015.

5. Unit was rolled on 5-6-2015 at 5:30PM up to 10000 rpm. Further loading of blower was continued subsequently. Performance of the equipment found satisfactory w.r.to bearing temperatures, shaft vibrations and other steam and oil parameters.

6. On 8-6-15 customer given clearance for de-mobilization and tools were taken out 9-6-2015.

| Waste Heat Boiler, Economizer, Super heaters |  |  |
| --- | --- | --- |
| 1 | * Thickness measurement of water wall membrane tubes, flag coils, economizer “U” bends, straight tubes, steam headers & bottom casing plates, super heater bends. * Thickness measurement of new sulphur furnace shell & dished end, furnace leg support pipes. * Thickness measurement of down comer pipe lines of WHR boiler. | # No significant reduction in thickness was observed during thickness measurement. |
| 2 | * Economiser bottom casing plate replacement and new brick lining inside casing. | # Complete bottom casing plate was cut & removed as there were holes in some plates. Also bulging was observed on all the plates due to excessive thinning of plate. Also the brick lining was damaged severely & fell down from their locations. # Then fresh brick lining was carried out inside the bottom casing. |
| 3 | * Economiser Outlet Duct & expansion bellow Replacement and new brick lining of outlet duct pedestal support * Removal of unused vent nozzle in outlet duct & provision for temperature & pressure measurement points in the outlet duct | # 02 no of metallic expansion bellows (Tag No. 010-CP-1322.1 & 010-CP-1322.12) in economizer outlet duct was replaced by new bellows along with newly fabricated gas ducts, as the old gas ducts & expansion bellows was leaking frequently. This will improve the reliability of the gas ducting and will also minimize the chances of gas leakage. # Also the brick lining of the outlet duct pedestal support was renewed as the exiting acid resistant brick lining was damaged completely. # The unused & also undesired (at present) nozzle in the outlet gas duct was cut & removed and the location was blinded by providing new plate to minimize chances of leakage of gas. # Tappings for pressure measurement and temperature measurement were also provided in the newly fabricated & erected outlet gas duct. |
| 4 | * Painting of casing plates, Old & new ducts and fresh insulation work on economizer casing & outlet duct | # Power tool cleaning of the casing plates & ducts was carried out. Then a single coat of heat resistant painting was done on it to prevent propagation of under insulation corrosion. # Old insulation was removed and new insulation along with sheeting was done on all the casing portions (top & bottom) along with on outlet gas ducts upto the height of economizer to minimize the radiation loss thru insulation. # Also the brick lining of the outlet duct pedestal support was renewed as the exiting acid resistant brick lining was damaged completely. |
| 5 | * Super Heater-2 Inlet & Bypass Duct & expansion bellow Replacement * Provision for temperature & pressure measurement points in the inlet duct | # 01 no of metallic expansion bellow on super heater-2 inlet gas duct (Tag No. 010-CP-1508.3) & 01 no of metallic expansion bellow in super heater-2 bypass gas duct (Tag No. 010-CP-1509.1) were replaced by new bellows along with newly fabricated gas ducts. This will improve the reliability of the gas ducting and will also minimize the chances of gas leakage. # Tappings for pressure measurement and temperature measurement were also provided in the newly fabricated & erected outlet gas duct. |
| 6 | * Painting of old ducts, old expansion bellows and fresh insulation work on super heater-2 inlet, outlet & bypass ducts | # Power tool cleaning of the ducts along with expansion bellows was carried out. Then a single coat of heat resistant painting was done on it to prevent propagation of under insulation corrosion. # Old insulation was removed and new insulation along with sheeting was done on the ducts & expansion bellows to minimize the radiation loss through insulation. |
| Converter, Heat Exchanger and Gas ducts |  |  |
| 7 | * Converter bed I catalyst support tray repair | # 24 no of new trays replaced along with complete radial & circumferential stiffener plates |
| 8 | * Converter bed II catalyst support tray repair | # 03 no of new trays replaced along with some portion of radial & circumferential stiffener plates |
| 9 | * Converter bed III catalyst support tray repair and shell & duct aluminum coating done | # 02 no of new trays replaced along with complete radial & circumferential stiffener plates # Converter bed III central drum gas division joint was found cracked. The crack was repaired and aluminization was done on the complete inside surface of shell & outlet duct. |
| 10 | * Expansion bellows & gas duct replacement | # Boiler O/L to Converter 1st Bed I/L 1st Bellow (Hydra Type Vertical), Tag No. 010-CP-1306.1/1306.2, Horizontal bellow, Tag No. EJ-05, Converter 2nd Bed O/L to S/H-1 I/L 1st Bellow (Hinged Type Vertical), Tag No. 010-CP-1511.1 were replaced by new bellows. |
| 11 | * Painting of old ducts, old expansion bellows and fresh insulation work on various gas ducts | # Power tool cleaning of the ducts along with expansion bellows was carried out. Then a single coat of heat resistant painting was done on it to prevent propagation of under insulation corrosion. # Old insulation was removed and new insulation along with sheeting was done on the ducts & expansion bellows to minimize the radiation loss through insulation. |
| 12 | Cold heat exchanger internal inspection and repair | # CHE bottom plate beam supports along with bottom plate was replaced by new plates and SS 316L liner was also completely replaced. # CHE area below bottom plate was full of sludge due to gas leakage. The area was cleaned and brick lining was carried out completely at the bottom for the first time. The sealing wall around heat exchanger foundation was removed. Fresh brick lining of pedestals was done after repairing of the pedestal supports by civil dept. # CHE tubes neutralization and hydro-jet cleaning was done, but could not de-choke all the tubes. Hence 14 no of tubes were plugged from top & bottom. # RFET of CHE tubes was planned, but was not completed as cleaning of the tubes was done at a later stage. # CHE shell side was opened for physical inspection of tubes & tubes were found in good condition. # CHE outlet duct bottom half plate was replaced as it was leaked frequently in the past. |
| 13 | * Expansion bellows & gas duct replacement | # IAT O/L to 1531 HE S/S I/L 2nd Bellow (Hinged Type Vertical), Tag No. 010-CP-1416.2, IAT O/L to 1531 HE S/S I/L 3rd Bellow (Hinged Type Vertical), Tag No. 010-CP-1416.3 and IAT O/L to 1531 HE S/S I/L 4th Bellow (Horizontal), Tag No. 010-CP-1416.4 were replaced by new bellows. |
| 14 | * Painting of old ducts, old expansion bellows and fresh insulation work on various gas ducts | # Power tool cleaning of the ducts along with expansion bellows and CHE shell portion upto a height of bypass duct was carried out. Then a single coat of heat resistant painting was done on it to prevent propagation of under insulation corrosion. # Old insulation was removed and new insulation along with sheeting was done on the ducts & expansion bellows to minimize the radiation loss thru insulation. |

Safety valve overhauling

- The high pressure safety valves overhauled after removal from positions.

- After overhauling the safety valves are tested on test bench and set point is adjusted.

| Sr. No | Tag No | Location | Set pressure (Kg/sq.cm.) |
| --- | --- | --- | --- |
| 1 | PSV 1301 | Steam drum PAP side | 74.00 |
| 2 | PSV 1302 | Steam drum SAP side | 75.00 |
| 3 | PSV 1303 | Export steam line | 64.50 |
| 4 | PSV 1304 | Super heater 1 | 70.00 |
| 5 | PSV 1305 | Economiser | 84.00 |
| 6 | PRDS Line | Safety Valve | 7.15 |

Replacement of valves in SAP-1.

All the valves installed in the plant were critically inspected before the shutdown and accordingly the action plan was prepared for their maintenance/ replacement.

Observations:

The valves listed below were either replaced or installed new.

- Sulfur jacketing line drain valve.

- Steam export line one drain valves.

- Steam drum Level Gauge.

- New tapping for pressure gauge in Burner air inlet line.

- CWP-3 pump casing cooling water I/L line vent valve.

- LPS1 header drain line valve.

- De-superheating valve isolation valves.

- CBD line new control valve and isolation valves.

- CBD line drain valves.

Result:

Performance of newly replaced valves is found satisfactory.

Overhauling of isolation valves

Some problems were detected during operation of some isolation valves. These valves are examined and corrective action was taken.

| Sr. No | Valve Location | Size/ Rating | Job carried out. | Spares consumed |
| --- | --- | --- | --- | --- |
| 1. | Ist inlet isolation valve of Tr-1 turbine | 200 NB/ 1500# | Valve dismantaled, cleaning, lapping,blue matching, gear box overhauling done then boxed-up and installed in its position. | Gland Packing, Pr. Seal ring |
| 2. | IInd inlet isolation valve of Tr-1 turbine | 200 NB/ 1500# | Valve dismantaled, cleaning, lapping,blue matching, gear box overhauling done then boxed-up and installed in its position. | Gland Packing, Pr. Seal ring |
| 3. | Back pressure line isolation valve of Tr-1 Turbine. | 500 NB/ 300 # | Valve gearbox dismantaled, cleaning done then boxed-up and installed in its position |  |
| 4. | Super heater 2 inlet Isolation valve in Tr-2. | 200 NB/1500 # | Valve gearbox dismantaled, cleaning done then boxed-up and installed in its position. Gland packing of valve changed. | Gland packing |
| 5. | Ist isolation valve of Pre-heating line | 200 NB/ 1500# | Valve dismantaled, cleaning, lapping,blue matching, gear box overhauling done then boxed-up and installed in its position. | Gland Packing, Pr. Seal ring |
| 6 | IInd isolation valve of Pre-heating line | 200 NB/ 1500# | Valve dismantaled, cleaning, lapping,blue matching, gear box overhauling done then boxed-up and installed in its position. | Gland Packing, Pr. Seal ring |
| 7 | Export line isolation valve | 350 NB/ 1500# | Valve dismantaled, cleaning, lapping,blue matching, gear box overhauling done then boxed-up and installed in its position. | Gland Packing, Pr. Seal ring |
| 8 | Spectacle blind of export line | 350 NB/ 1500# | Spectacle blind dismantaled, cleaning, lapping,blue matching, done then boxed-up and installed in its position | Octagonal ring gasket |

Valve overhauling under progress

Replacement of Damaged Spring supports:

Following damaged spring supports of steam lines have been replaced:

| Sr.No. | Line No. | Support Nos. |
| --- | --- | --- |
| 1 | 010-SHH-1301-60-CS | S-101 and S-102 |
| 2 | 010-SP-1301-300-60-CS | S-106 and S-107 |
| 3 | 010-SP-1303-350-100-AS | S-127,S-128, S-129, S-130, S-136 and S-137 |
| 4 | INT HDR1 to INT HDR 2 | S-139 and S-140 |

Insulation Work:

Major insulation works carried out were:

- Complete Waste heat boiler insulation was carried out from bottom to neck portion.

- Complete boiler bypass duct insulation after duct replacement.

- Complete boiler outlet duct insulation up to converter inlet.

- Bottom and side portion of economizer.

- Complete boiler feed water inlet line to boiler.

New insulation on waste heat recovery boiler

Rotary Equipment:

- Preventive maintenance of both the sulphur burners was carried out.

- Alignment of pulleys checked and corrected.

- Oil flushing done.

- Belts were checked out and damaged belts were replaced.

- Rotary cup and distributer were checked and cleaned

- Bearing of the burners were checked

- Preventive maintenance of both primary air fans was done.

- Balancing of the rotor was done.

Plummer blocks were opened and cleaned.

- Greasing done, belt checked and then again boxed up.

3. Inlet and outlet dampers of both primary air fans were made free.

Replacement of air filter elements and vanes assemblies in Tr-I.

The pressure drop across the filter air elements was running high. On visual inspection it was found that filters elements had got damaged. Filter elements supporting base frames were also found damaged.  It was decided to change the complete filter elements.  In this filtration system air is filtered and dried in drying tower and filtered, dried air is sent to boiler furnace. Air filtration consists of two types of filter elements. 1. Conical air filters 2. Cylindrical air filters.

Conical air filter elements.

No of air filters replaced     : 144

Make                                  : Camfil

Size                                    : 445 mmX324 mmX660 mm long

Cylindrical air filter elements

No of air filters replaced    : 144

Make                                  : Camfil.

Size                                    : 324 mmX660 mm long

Blower

Drying Air Tower

Air Filter

Filtered	Filtered Air	Dry Air

Boiler Furnace

Schematic diagram of air flow to Furnace.

Vane assemblies:

No of vanes replaced		: 540

Make				:Camfil

Replacement of Tr-1 VPT: We had faced problem of molten sulphur leakages in Tr-1 VPT from past few months. It was decided to change the tank with new tank of SS 304.

Old carbon steel vertical pump tank (Tr-1 VPT) was upgraded to SS 304.

New VPT fabricated and erected with 8mm thk roof plate, 10mm thk shell and 12 mm thk bottom plate.

New steam coil also fabricated and positioned inside the tank.

Top platform structure was also replaced with new C.S structure

Diameter of tank : 4000 mm.

Height of tank : 2600 mm.

Sulphur Melter-131

- Old damaged roof plates were removed.

- Rafter beams (old) cut and removed.

- New roof plates fabricated and heat resistance painting done to lower side of the plate for corrosion resistance.

- New rafter beams fabricated and erected.

- New roof plates erected on rafter beams.

Vertical Pump Tank- 3.

- Old carbon steel vertical pump tank (VPT-3) was upgraded to SS 304.

- New VPT fabricated and erected with 8mm thk roof plate, 10mm thk shell and 12 mm thk bottom plate.

- New steam coil also fabricated and positioned inside the tank.

- Top platform structure was also replaced with new C.S structure.

Other jobs done in melter area:

- Five nos pulley rubber lagging was done.

- Conveyor 101 damaged 30 mtrs belt was removed and new belt was jointed by hot vulcanizing.

- Three vertical pump tanks were drained and cleaned.

- All three sulfur melters were drained and cleaned.

Intermediate Absorption Tower (IAT) Revamp job.

The acid resistant bricklining inside the tower got damaged at some locations, which lead to the attack of acid on the side walls of tower and bottom dished end. The acid leakages from the bottom dished end and bulging of side walls were observed.

IAT Shell to bottom dish-end joint cracked circumferentially 120° towards gas inlet (South) side

Gap between two layers of bottom dish-end & Pitting on side walls

The major maintenance activities carried out were as follows:

- IAT top dome removal & refitting.

- Removal of candle filter & refitting.

- IAT U seal removal & refitting.

- IAT return duct removal & refitting.

Tope dome removal and neutrilastion of candle filters

IAT return duct welding

- Complete dismantling of bricklining with brick dome and relining the same.

IAT inside brick lining work under progress.

- Shell plate & bottom disc end plates are replaced by newone,where its thickness found thinned down.

Bottom dished end thickness survey & IAT side wall repairing

Repairing of IAT shell plate

- Acid distribution system is completely replaced by upgraded alloy material CorFre-A10

- Fume extraction pipelines are completely replaced by SS316L as per suggestion.

- Acid analyser Pipelines are completely replaced by new SS316L pipelines.

Removal of Cast iron acid distributor headers of IAT

Newly installed acid distribution system of corefre A10 alloy.

IAT Acid Pump Tank: Acid seepage was observed frequently in IAT pump tank. During visual inspection in last turnaround it was also observed that tank has got corroded both internally and externally. Its acid resistant brick lining was also found damaged. Suitable corrective action was taken at that time and it was decided to upgrade these tanks by Zecor-Z  alloy pump tanks in ATR-2015.

The activities carried our were as follows:

- Pump tank (CS WITH BRICKLINED) completely replaced by upgraded ZECOR-Z pump tank.Size:4mtr Dia X2.5mtr height

- Foundation of pump tank also modified by grizzly support.

IAT pump tank foundation work

- Pump tank was installed.

- Platforms were provided on pump tank for safe working.

IAT Pump tank marching for erection & finally IAT Pump tank installed

- Roof of pump tank was fabricated &replaced by SS316L.

Fabrication of pump tank roof

Final Absorption Tower (FAT): The major maintenance works carried out in the tower are enlisted below:

- Acid distribution system is completely replaced by upgraded CorFre-A10.

- Analyser Pipelines are completely replaced by SS316L

Installation of new acid distribution system.

- Cutting of tope dome and removal of candle filters

- Dismantling of acid U seals, repairing of acid inlet nozzles.

FAT U-seal fitting work under progress

FAT candle filters removal and washing & FAT candle filters removal completed

Drying Tower (DT): Following major maintenance acivities were performed in DT during annual shutdown:

1.Acid distribution system is completely replaced by new one. The material is same as before i.e Cast iron.

2.Air inlet duct nozzle leaking frequently. Some portion of the brick lining was removed out and relined after new plate fitting.

Old & damaged irrigation header and new header installation

3.Demister pads are completely replaced by new one.

| Removed demister pad Corroded Support structure |  |
| --- | --- |

4.Acid outlet nozzles are found corroded, the nozzles are repaired and rebricklined

Repairing of acid inlet nozzle.

DT ACID PUMP TANK: Following major maintenance activities were performed in DT tank.

1. Roof of pump tank was fabricated &replaced by SS316L.

2. Analyser Pipelines are completely replaced by SS316L

3.Fume extraction pipelines are completely replaced by SS316L.

4. Platforms were provided on pump tank for safe working

DT Pump tank pumps base fabrication & DT pump tank roof plate replacement

ACID COOLERS :

- All plate heat exchangers are interchanged

- Shell & tube acid coolers are opened on both sides, hydrojet cleaning and boxed up.

ACID CIRCULATION PUMPS: All acid recirculation pumps are dismantled, overhauled and reinstalled.

Spares consumed:

a)Shaft -02nos

b)Impeller -02nos

c)Volute casing-03 nos

d)Suction head-02nos

e)Wear rings -06nos

f)journal-01no

g)Bearings -07nos

Overhauling of acid pumps

VENTURI TOWER:

Bottom of venture was leaking frequently.It was rectified by bottom plate repair and rebricklined upto a height of one meter.

| Venturi tower bottom brick lining work | Brick lining at Venturi tower nozzle |
| --- | --- |

HEAT RECOVERY SYSTEM (HRS UNIT):

1.Boot pump is replaced by newone as its impeller was eroded & pitted at some places.

2.Heater & Preheater are inspected by eddy current &hydro test.It was found that in Heater,05nos of U-tubes are thinned down. So, those are plugged as per instruction of M/S.MECS,USA.

| Acid Section and HRS |  |  |
| --- | --- | --- |
| 15 | * Heater and Pre heater tubes (pre heater tubesheet) | # Eddy Current testing of Heater and pre heater tubes was carried out. Accrodingly 10 tubes were plugged in heater and none in preheater. (heater tubesheet before plugging) |

3.Thickness measurement survey was carried out on HRS tower and acid, steam & gas ducts & pipelines,found satisfactory.

4.HRS Boiler was inspected,found some saddle chips at the neck of tubes.They are cleaned and boxed up.

Signs of corrosion at the tip of pump & Eddy Current Testing of HRS heat exchanger tubes

5.Control valves ,Block valve, vent valve & NRV were passing.Those are reconditioned and installed.

6.Trough type distributor & gate assembly are inspected and found satisfactory.

7.Diluter was dismantled due to leakage In flange joints during acid recirculation in HRS unit.

After dismantling,it was found that it’s PTFE lining is displaced.Hence

8.HRS steam injection pipeline is replaced by upgraded SS316L.

HRS - irrigation system, gate assemblies and inlet duct inspected. No signs of corrosion

HRS heat exchangers hydro-jet cleaning for tubes inspection

SAP-2 Highlights:

Major Jobs Summary

| Sr No |  | Job | Observation / Action remarks |
| --- | --- | --- | --- |
| Air Filter, Drying Tower and Turbo-blower |  |  |  |
| 1 | Air Filter elements inspection and cleaning (damaged filter elements of train 2) |  | Filter elements were damaged. All filter elements were replaced. (new filter elements installed in train 2) Dyna vanes were not in good condition. All dyna vanes were replaced with SAP-1 dyna vanes. |
| 2 | Turbine trip block servicing |  | Trip block replaced |
| 3 | Turbine all three actuator servicing and calibration |  | Completed |
| 4 | Turbine oil reservoir cleaning and oil replacement |  | Completed |
| 5 | Blower IGV servicing done |  | Done |
| 6 | Air filter auto back flushing system servicing |  | completed |
| Sulphur pump tank, Furnace |  |  |  |
| 1 | Sulphur furnace internal inspection and brick lining repair |  | Furnace neck portion brick had fallen. The same was repaired. Castables repair work carried out on burner side dish end. Boiler bottom portion brick found bulged out, but the same was left unattended |
| 2 | Secondary air dampers to be made free |  | Both dampers serviced to have satisfactory free operation |
| 3 | Both burners overhauling |  | Done |
| 4 | Sampling point to be provided in Sulphur inlet line |  | This job was dropped |
| Waste Heat Boiler |  |  |  |
| 1 | WHB tubes external surface cleaning with dry ice blasting |  | Dry ice blasting was done for WHB, SH1 & 2, Economizer. The deposit on tubes was not very high on the areas cleaned in November last year. But in areas not attended in November, large amount of dust deposition was found. (dry ice blasting work in boiler) |
| 2 | WHB panels thermal insulation to be completely replaced for improved heat recovery |  | This job was dropped |
| 3 | Boiler bypass duct repair |  | Bypass damper was badly eroded. It was replaced with SAP-1 bypass damper as new spare was not available. Bypass bellows – horizontal and vertical were replaced with new, same design Additional supports were provided to check expansion of the duct. |
| 4 | All safety relief valves to be calibrated |  | Completed |
| 5 | Boiler CBD control valve to be installed based on approved suggestion |  | Job was not done |
| 6 | CWP steam flow meter to be set right |  | Job was not done |
| 7 | Safety relief valve installation on blow down tank as per IBR guidelines |  | Job was not done |
| 8 | CWP lines spring supports to be replaced |  | Job was not done as new spring supports did not arrive |
| 9 | CWP oil and water coolers hydro-jet cleaning |  | Done |
| Converter, Heat Exchangers and Gas Section |  |  |  |
| 1 | All catalyst bed screening |  | All converter beds screening done. The top up quantity is as follows: Bed I: RR type: 24 m3 Bed II: HV type: 9 m3 Bed III: HV type: 15 m3 Bed IV: Cs type : 6 m3 HV type: 5 m3 Converter bed I pressure drop reduced from 820 mmWC before shutdown to 320 mmWC after shutdown. The plant total pressure drop reduced from 458 mbar to 445 mbar |
| 2 | All beds catalyst support grid to be checked and repaired if required |  | In bed 1 9 perforated plates were replaced. In bed 3 10 perforated plates were replaced. Support plates in other beds were in good condition – minor repairs done. |
| 3 | All gas dampers to be made free |  | All were made free. SH-2 outlet damper does not operate with actuator due to actuator fixing problem |
| 4 | Cold Heat Exchanger shell and tube side cleaning |  | Tube and shell side inspected and found in good condition. Tube side sludge cleaned. SS liner damaged on bottom plate and shell. The same was repaired. CHE tubes replacement to be planned next year |
| 5 | Converter 1st bed DP transmitter auto flushing arrangement to be provided |  | Job not done |
| 6 | SO2 converter inlet analyzer to be taken in line |  | Job not done |
| Acid Section |  |  |  |
| 1 | All acid PHEs acid to water & inlet to outlet interchange |  | Interchanged |
| 2 | Shell and tube acid coolers hydro-jet cleaning |  | Completed |
| 3 P | DT demister pad inspection |  | Demister pad support beams were corroded and the pad had sagged down. The same was repaired |
| 4 P | DT acid distributors inspection |  | Acid distributor pieces were corroded and broken. 8 pipe pieces were replaced and patch welding was done at 20 places. DT acid distributor to be planned for replacement next year |
| 5 | All acid pumps overhauling done |  | Done |
| 6 | Individual fumes extraction line to be installed for IAT pump tank, as per approved suggestion |  | Job not done |

Sulphuric Acid Plant-2

Preface: Plant was stopped for annual turn around and annual inspection of boiler by AD (F&B).During the turnaround preventive maintenance of Siemens make blower was carried out.. Brick lining of Sulfur Furnace neck portion & preventive maintenance of various rotary machines were other major jobs carried out during shutdown. Besides these activities various isolation and safety valves were overhauled.

Turbine: Preventive maintenance of Turbo-Blower & it’s drive turbine was done and following activities were carried out.

- All the vanes of Blower suction IGV removed, bearings replaced and fitted back. Operation of the IGV through control room checked & found satisfactory.

.

Overhauling of Turbo-blower

2. All 3 actuators dismantled, overhauled and calibration done.

3. All the vanes of Blower suction IGV removed, bearings replaced and fitted back.

4. Oil sump drained, cleaned and oil charged back after cleaning

5. Both the oil coolers cleaned by hydro jet cleaning.

6. Bearings of the Blower were opened, cleaned and boxed up after checking the

clearances.

a. Bearing clearance on DE side is 0.38

b. Bearing Clearance on NDE side is 0.42

c. Axial Thrust is 0.40

Turbine oil sump Manhole opened for cleaning and oil change

Alignment Readings :- The alignment readings were taken and recorded .

Before overhauling:   Turbine To Gear Box (Dial On Gear Box)

-.21

0.00

-.15

-.24

R

-.05

0.00

+.015

-.03

A

+.07

0.00

+.08

+.04

A1

+.07

+.08

+.14

0.00

A2

After Overhauling :   Turbine To Gear Box (Dial On Gear Box)

-.15

0.00

+.04

-.11

R

-.05

0.00

-.01

-.02

A

-.02

0.00

-.05

-.04

A1

-.02

-.02

+.04

0.00

A2

Sulphur Furnace:

Sulfur furnace bricklining was critically examined and following points were observed.

- The neck portion brick lining was found badly damaged.

- Castable was found damaged near burner manhole opening portion.

Damaged castable and Furnace neck portion bricklining

After critical evaluation following corrective measures were taken

- Damaged brick lining including castable portion of the furnace neck was dismantled.

- New brick lining with insulating and fire resistant castable was done on the furnace neck portion.

- The damaged castable around burner manhole opening was removed and new castable was applied.

.

Boiler Gas Bypass Duct:

- Damaged boiler gas bypass damper, duct, supports and two (02) Nos. of expansion bellows were replaced with new ones.

Other activities performed during sulfur furnace maintenance.

1. Secondary Air dampers were overhauled.

2. Both the fabric expansion joints were replaced with new fabric.

| Waste Heat Boiler |  |  |
| --- | --- | --- |
| 1 | * Thickness measurement of water wall membrane tubes, flag coils, economizer “U” bends, super heater bends. | # No significant reduction in thickness was observed during thickness measurement. |
| 2 | Dry ice blasting of tubes was carried out | Heat transfer rate improved |
| Converter, Heat Exchangers and Gas Section |  |  |
| 2 | * Converter bed I catalyst support tray repair | # 09 no of new trays replaced along with complete radial & circumferential stiffener plates |
| 3 | * Converter bed III catalyst support tray repair | # 10 no of new trays replaced along with complete radial & circumferential stiffener plates |
| 4 | Cold Heat Exchanger shell bottom plate liner repair work | SS liner was found damaged on bottom plate and shell. The same was repaired. |

Safety valve overhauling

- The high pressure safety valves overhauled after removal from positions. After overhauling the safety valves are tested on test bench and set point is adjusted.

| Sr. No | Tag No | Location | Set pressure (Kg/sq.cm.) |
| --- | --- | --- | --- |
| 1 | PSV 2301 | Steam drum PAP side | 74.00 |
| 2 | PSV 2302 | Steam drum SAP side | 75.00 |
| 3 | PSV 2303 | Export steam line | 64.50 |
| 4 | PSV 2304 | Super heater 1 | 70.00 |
| 5 | PSV 2305 | Economiser | 84.00 |

Replacement of valves in SAP-2.

All the valves installed in the plant were critically inspected before the shutdown and accordingly the action plan was prepared for their maintenance/ replacement.

Observations:

The valves listed below were either replaced with new one.

- Cold heat exchanger drain valve.

- Steam drum Level Gauge.

- New tapping for pressure gauge in Burner air inlet line.

- CWP-2 pump casing cooling water I/L line vent valve.

- Sulfur jacketing line drain valve.

- LPS1 header drain line valve.

Result:

Performance of newly replaced valves is found satisfactory.

Overhauling of isolation valves

Some problems were detected during operation of some isolation valves. These valves are examined and corrective action was taken.

| Sr. No | Valve Location | Size/ Rating | Job carried out. | Spares consumed |
| --- | --- | --- | --- | --- |
| 1. | Ist inlet isolation valve of Tr-2 turbine | 200 NB/ 1500# | Valve dismantaled, cleaning, lapping,blue matching, gear box overhauling done then boxed-up and installed in its position. | Gland Packing, Pr. Seal ring |
| 2. | IInd inlet isolation valve of Tr-2 turbine | 200 NB/ 1500# | Valve dismantaled, cleaning, lapping,blue matching, gear box overhauling done then boxed-up and installed in its position. | Gland Packing, Pr. Seal ring |
| 3. | Back pressure line isolation valve of Tr-2 Turbine. | 500 NB/ 300 # | Valve gearbox dismantaled, cleaning done then boxed-up and installed in its position |  |
| 5. | Super heater 2 inlet Isolation valve in Tr-2. | 200 NB/1500 # | Valve gearbox dismantaled, cleaning done then boxed-up and installed in its position. Gland packing of valve changed. | Gland packing |

Replacement of Damaged Spring supports:

Following damaged spring supports of steam lines have been replaced:

| Sr.No. | Line No. | Support Nos. |
| --- | --- | --- |
| 1 | INT HDR1 to INT HDR 2 | S-139 and S-140 |

Rotary Equipment:

- Burners

Both the Luro burners overhauled tested on test bench and then installed in position.

Burner make: Luro Saacke

Burner model: SSK 2400

- Alignment of pulleys checked and corrected.

- Oil flushing done.

- Belts were checked out and damaged belts were replaced.

- Rotary cup and distributer were checked and cleaned

- Bearing of the burners were checked

- Maintenance of both primary air fans was done.

- Bothe the fans dismantled and rotor balancing was carried out after overhauling.

- Plummer blocks were cleaned.

- Greasing done, belt checked and then again boxed up.

3. Inlet and outlet dampers of both primary air fans were made free.

Overhauling of acid circulation pumps:

1.All pumps are dismantled and overhauled and reinstalled.

Spare consumed :

a)Shaft -01nos

b)Impeller -01nos

c)Volute casing-01 no

d)Wear rings -02nos

e)Bearings -07nos

f)Discharge elbow -01no

Overhauling of acid circulation pumps

Acid Piping:

1.Acid recirculation pipelines at storage tank A & B are completely replaced by upgraded  SS316L material,size:350mm NB.

2. Acid circulation pipelines In IAT,FAT & DT are completely replaced by upgraded  SS316L material,

Acid Storage area: new acid recirculation line fabrication and replacement

Common Area Jobs:

Major Jobs Summary

| Sr No | Job | Observation / Action remarks |
| --- | --- | --- |
| Sulphur Silo and Conveyors |  |  |
| 1 P | Conveyor 101 structural repair & civil work to prevent water seepage from underground | Completed |
| 2 | All 5 charging hoppers on conveyor 101 to be repaired and made operational | Hopper #1 and 2 made operational |
| 3 | Conveyor 101 tunnel dewatering arrangement to be done to avoid structure corrosion | Not done |
| 4 | All conveyors structural repair and painting | Not done |
| 5 | Conveyor 103 discharge hopper (Surge hopper) top plate and adjacent structure replacement | New top plate and grating were installed. New SS hand railing installed. |
| 6 | Water sprinkling system at conveyor 101 to be restored as a safety point | Not done |
| 7 | Condition checking of all conveyors including head and tail pulley, gear boxes, hoppers, skirt rubber, scrapper plate etc | Partially completed |
| 8 | All conveyor belts tension adjustment and alignment to be done to avoid sway and damage of conveyor belts | Not done |
| 9 | Zero speed switches, sway switches and pull chord switches to be checked and taken in line | Belt sway switches not taken in line |
| Melters VPTs and Filters |  |  |
| 1 | All primary filters revamping | Not taken up |
| 2 | Secondary filter candles replacement | Candles not arrived during shutdown. The job will be taken up when candles are available |
| 3 | Filtration circuit valves and NRVs serviced / replaced | Done |
| 4 | All sulphur pumps servicing | Not done |
| 5 | VPT-3 replacement with SS tank | Done |
| 6 | Melter 130 cleaning and repair | Completed |
| 7 | Melter 132 cleaning, repair and one coil replacement | Completed |
| 8 | Melter 131 coils, agitator and internal repair | Job to be completed along with SAP-1 shutdown |
| 9 | Cleaning of sulphur deposits in filter building | Done |
| 10 | All melters steam and condensate headers replacement | Not done |
| BFW and Steam piping |  |  |
| 1 | HP to LPS-1 PRDS replacement |  |
| 2 | Critical service steam line valves serviced | Done |
| 3 | Steam pre heating line spectacle blind flange leak arrested | Completed |
| 4 | SAP-2 seam drum SRV flange replaced | Completed |
| 5 | Both BFW pump turbine governors servicing and mechanical trip device to be taken in line | Not done |
| 6 | Both turbine lube oil MOP and AOP servicing | Done |
| 7 | Lube oil coolers hydro-jet cleaning | All four BFW coolers tubes were blocked with muck and tubesheets were badly corroded. Coolers need to be replaced. |
| 8 | Additional vent and drain points to be provided in the LP steam header for properly draining condensate during start up | Not done |
| Acid Storage and Transfer |  |  |
| 1 | Vent Air dryers alumina replacement | Not done |
| 2 | Tank A and B circulation line replacement | completed |
| 3 | Import acid area sump to be repaired and sump pump to be installed | Not done |

ANNUAL SHUTDOWN REPORT – APRIL 2015

JOBS UNDERTAKEN BY SAP INSTRUMENTATION

COMMON AREA (SHUTDOWN PERIOD: 01-04-15 to 13-04-15)

- Melting area LT-130, 131, 132, 107, 108, 103, 103A were calibrated.

- Jacketing steam condensate tank LV108 was calibrated.

- Melting steam condensate tank pump auto start and stop interlock with level was checked at 70% and 30% respectively.

- HP Deaerator area control valves LV1536, TV1510A, PV2602A/B, PV1392 and PV1504 were cleaned and stroke checking was done.

- HP Deaerator tank LT1536, LT1538 and PT2602 were calibrated.

- LPS line instruments PT1504, PT0110, TT1510A and PT1392 were calibrated.

- HP Deaerator inlet water line flow indication was provided in the DCS as per approved suggestion.

Orifice plate is installed in Deaerator DM water Inlet line

PCV1555 with inbuilt water injection chamber

HP-LP PRDS got replaced with new set of PCV1555,TCV1554 and water injection chamber

Old PRDS

TCV1554

PCV1555

New Improved version of PRDS

Spray Nozzle

TCV1554

PCV1555

- HP-LP PRDS line PT1555, TT1554 and PI1555 got shifted as per new arrangement of PRDS.

TT1554

PT1555

PI1555

- HP-LP PRDS line instruments PT1554, PT1555, FT1551and TT1554 were calibrated.

- BFP 101A, B, C, S instruments PT101B-LD, PT101S-LD, PT101A-LO, PT101C-LO, PT101A-ES, PT101C-ES, FT101A-IS, FT101C-IS, PS2-A, PS5-A, PS1-A, PS2-C, PS5-C, PS1-C and PT1543 were calibrated.

- BFP 101A and 101C interlock was checked with the following tripping conditions:

  - Lubricating oil pressure low at 1.0 Kg/cm2.

  - Exhaust steam pressure high at 5.6 Kg/cm2.

  - Auxiliary oil pump auto start with control oil pressure low at 7.5 Kg/cm2.

  - Emergency stop from local panel.

- BFP motor driven 101B/S auto start interlock was checked with BFW header pressure low at 85 Kg/cm2 provided respective pump lubricating oil pressure is greater than 0.5 Kg/cm2.

- Process water and cooling water flow meters FT1403 and FT1402 were calibrated.

- Instrument air pressure PT1645 was calibrated.

- Common area DCS shutdown was taken and  following jobs were performed with the assistance of Yokogawa service engineers:

  - Cabinets 300, 301, 302, 303, 304, 305, 402 were cleaned.

  - All modules in the system cabinet 100 were racked out for cleaning.

  - All terminal boards in the marshalling cabinet were cleaned, tightened and their fuses were checked.

  - Relays of Digital input and output relay board were checked for their operation.

  - Cabinet fans were checked and their filters were cleaned.

- Following HIS and Engineering Station related jobs were performed with the assistance of Yokogawa Engineers to mitigate security risks that may affect the control system:

  - All HIS and Engg. Station was replaced with 64-bit operating system with Windows 7 professional edition.

Reason for replacement: Microsoft support for Windows XP has come to an end. This means Microsoft would not provide security updates, non-security hot fixes, assisted support and any online technical support for the Windows XP operating system. Due to this the system could be exposed to security threats from harmful viruses, spyware and malicious software which were earlier being addressed by patches and updates released regularly by Microsoft and will no longer be available.

  - DCS software CENTUM VP has been revised from R4.02.00 to the latest R5.04.20.

  - End Point Security system (Antivirus) has been installed in all HIS and Engg. Station.

Advantages of End Point Security System are:

- Since our network is secured, there is 0% breakdown & 100% availability in Network.so results in breakdown free Operation for operators.

- There is no time delay in any response /input given by operator.

- Good efficiency in operation results in minimizing down time of Equipment’s, results in less operational Cost & Maximizing Production.

- No Panic Situation caused in case of any emergency led by failure of HIS.

- The Downtime of the HIS will be very less comparatively when the HIS failure without any security.

- The Networked DCS system without ENDPOINT SECURITY have open communication and open access for everyone to use their Pen drive to collect plant datas or other confidential official datas. Whereas CS3000 Network with ENDPOINT SECURITY has a very Closed Communication & Full Locked Down so that no datas are stolen and very much secured.

- The use of Pen drives is a major source of Viruses, End Point Security will restrict the use of pen drives  & therefore our system will not get affected by viruses.

- UPS any incomer fail alarm was checked in annunciator panel window no. 20.

- UPS servicing was done with the assistance of service engineer.

SAP-2 (SHUTDOWN PERIOD: 30-03-15 to 15-04-15)

- Diesel flow heads were cleaned and their operation was checked.

- Export steam line instruments FT2302, PT2304, PT2331 and TT2308 were calibrated.

- Boiler drum instruments LT2301, LT2301A, LT2301B and PT2302 were calibrated.

- Boiler area control valves LV2301, TV2326, TV2506, TV2308, TV2203-2, LV2301D, and PV2304 were cleaned and stroke was checked. New positioner was provided for SH-1 3-way temperature control valve TV2506.

- Boiler bypass temperature element TE2204 was inspected and its transmitter TT2204 was calibrated.

- Boiler bypass damper upstream temperature indication is provided in the DCS with the tag name TT2204A.

Temperature Elements (K-Type Thermocouple) installed in upstream (TT2204A) and downstream (TT2204) of Boiler bypass damper:-

TT2204A installed in Damper upstream

TT2204 installed in Damper downstream

- Boiler bypass damper new positioner was installed and stroke was checked.

New YTC make Positioner

- Boiler outlet temperature transmitter TT2203 was calibrated.

- Furnace temperature element TE2202 got replaced and its transmitter TT2202 was calibrated.

- Converter all beds temperature transmitters TT-2501, 2502, 2503, 2504, 2505, 2506, 2507, 2512, 2513 and 2514 were calibrated.

- Molten sulphur flow meters FT2201 and FT2206 were zero calibrated.

- CWP-1, 2, 3, 4 instruments PTLO1-1, PTEXSTM1-1, PS1-1, PS2-1, PS5-1, PS1-4, PS2-4, PS5-4, PTLO4-1, PTEXSTM4-1, FT2303, FT2304, FT2305, FT2306 were calibrated.

- Boiler drum,SH-1,SH-2,Economizer pressure gauges got calibrated

- Acid area instruments LT2420, LT2420A, LT2440, LT2440A, LT2450 and LT2450A were calibrated and their dip tubes were inspected.

- Acid area control valves LV2440, LV2450, AV2440-1, AV2450-1, AV2420-1, AV2440-2, AV2450-2, and LV0204 were cleaned and stroke was checked.

- Acid area concentration analyzers AT-2440, 2450, 2420 were calibrated.

- Blower suction air instruments PT2402, TT2401 and FT2401 were calibrated.

- Blower bearing temperature transmitters TT-2411, 2412, 2413 were calibrated.

- Blower discharge air instruments PT2422, PT2403 and TT2402 were calibrated.

- Air Filter for air blower – All 75 nos. SOV operation was checked out of which 2 nos. SOV got replaced. Old damaged GI cable tray is replaced with FRP tray.

New SOV

Damaged SOV

New FRP Cable tray installed in place of old damaged GI tray

- Turbine inlet steam flow meter FT2560 was calibrated.

- Turbine instruments PT201, PS201, PT301, PS301, PT074, PS073, PS074, PS075 and PS076 were calibrated.

- Turbine, Gear box and Blower vibration probes VE-761, 762, 774, 775, 809, 810, ZE761, ZE762, VEX2411, VEY2411, VEX2412, VEY2412, ZE2411, and ZE2412 were checked.

- Turbine speed probes SE761 and 762 were checked.

- Turbine and Gear box bearing temperature elements TE-215, 217, 245, 249, 261, 265, 269 and 273 were checked.

- Turbine trip block following instruments got replaced:

  - solenoid valve 2282,2283

  - E to H

- Turbine secondary oil pressure indication is provided in the DCS as per approved suggestion.

Solenoid Valves

E to H converter

Secondary Oil Pressure Transmitter

- Turbine oil tank level measuring point (float –type) is relocated as per approved suggestion and another signal cable got laid b/w JB and level element.

Previous installation :

Float Type element installed in congested location

New Installation:

New location of Float type LT

- VPT instruments LT0105A, TT0105A were calibrated.

- VPT level control valve LV0105A stroke checking was done.

- Stack Analyzer AT2451 maintenance was done and thereafter calibrated with standard gas.

- New interlock as per EWR for turbine inlet steam temperature low at 425 deg C was incorporated in Main turbine logic with 2 out of 4 tripping scheme

2. CWP inlet steam line

1. Turbine inlet steam line

4. BFP inlet steam line

3. SAP-2 Export steam line

- Main Turbine interlock was checked before startup with the following tripping conditions:

  - Exhaust steam pressure low at 3.0 Kg/cm2 and high at 5.6 Kg/cm2.

  - Boiler drum level low at 30%.

  - Lubricating oil pressure low at 0.9 Kg/cm2.

  - Emergency stop from speed governor.

  - Emergency stop from local panel.

  - Trip oil pressure low at 3.0 Kg/cm2.

  - Turbine Inlet steam temperature low at 425 deg C.

- Turbine standby lubricating oil pump auto start with oil pressure low at 1.3 Kg/cm2.

- Sulphur pump interlock was checked with acid circulation pumps and turbine running condition.

- CWP-1 and CWP-4 interlock was checked with the following tripping conditions:

  - Lubricating oil pressure low at 0.75 Kg/cm2.

  - Exhaust steam pressure high at 4.5 Kg/cm2.

  - Auxiliary oil pump auto start with control oil pressure low at 7.5 Kg/cm2.

  - Emergency stop from local panel.

- DT to IAT concentration control valve AV2440-1 auto closing interlock was checked with IAT pump tank level LT2440 high at 85%.

- SAP-2 DCS shutdown was taken and  following jobs were performed with the assistance of Yokogawa service engineers:

  - Cabinets 200, 201, 202, 203, 204, 250, 401 were cleaned.

  - All modules in the system cabinet 200 were racked out for cleaning.

  - All terminal boards in the marshalling cabinet were cleaned, tightened and their fuses were checked.

  - Relays of Digital input and output relay board were checked for their operation.

  - Cabinet fans were checked and their filters were cleaned.

EARTH PIT

- Old Earth Pit of DCS & UPS are replaced with two New Earth Pits.

UTILITIES     &       offsite

SAP cooling tower distribution valves:

- All the cooling tower’s Flow distribution valves (14 Nos.) were inspected and overhauled thoroughly.

- 6 Nos. Damaged Flow distribution Valves were dismantled from position and brought down to our workshop for overhauling.

- The bush, Disc, spindle (shaft) and hole were found worn out.

- Complete new bush assembly and Disc fitted and erected on the site for operation.

- Missing Valve operating levers were placed for smooth operation.

- Missing/damaged distribution nozzles of hot basin deck were replaced with new nozzles.

SAP cooling tower blow down valves:

- 7 nos. of cooling tower blow down valves were dismantled from position for inspection and overhauling, out of 7, 2 were found not operating as desired.

- 2 new valves were fitted in place of old damaged blow down valves.

Recirculation PUMP A

- Pump Top cover dismantled.

- Individual parts were inspected visually.

Some of the critical problems observed during dismantling/inspection, which are mentioned below.

- Minor Pitting found on both side of suction eye of  Impeller.

- Thrust bearing found ok.

- D.E & NDE side journal bearings found in good condition with little scratching & dents.

- Gland packing were severely eaten up but Gland sleeves were in good condition.

- A small hole about 2 mm in dia. found on impeller vane.

- Top casing water throwing eye area coating was in damaged condition.

Remedial action taken against the problems:

- A complete Rotor assembly (repaired) was made ready for erection.

- Both sides bearing housing were cleaned with diesel, throat bushing, casing wear ring and gland packing portion were also buffed and properly cleaned.

- Both side journal bearings polished and blue matching was done with an excellent area covering of about 95%.

- NDE side THRUST Bearing replaced with a new 6318C3 bearing.

- Discharge & Suction Valves gear boxes were overhauled & made free.

- Brush able ceramic coating applied on damaged/ weared portion of Top & Bottom casing  to enhance its life.

- New Casing gasket & Hollow core type PTFE gland packing provided.

- Finally pump boxed up, alignment done and  readings are mentioned below

Alignment reading:

Axial reading

0

Radial reading

0

0

0

-02

-05

05

07

Balancing report of CT pump “A” rotor assembly

Recirculation PUMP B:

- Pump Top cover dismantled.

- Individual parts were inspected visually.

Following observations were found:

- Gland sleeves are in good condition only Gland packing’s were damaged.

- Pitting found on both side of Impeller,s suction eye area.

- Both NDE and DE side journal bearing were found in good condition with minor scratching and dents on its surface.

- Thrust bearing found in good condition.

- Found impeller touching casing on one side.

Fig: impeller touching pump casing                                         Fig: Gland packing damaged

Remedial action taken against the problems:

- The pitting portion of impeller,s eye was welded & grinded properly and sent to workshop for   Dynamic  mass balancing.

- An extra mass of 23.3 gm at 266 deg was added to the impeller for balancing.

- Individual  parts like throat bush, gland pusher, casing wear ring, were cleaned and buffing done where ever necessary.

- Both the bearings housing were cleaned with diesel and throat bush sitting position, casing neck ring sitting position were also cleaned properly.

- Both side journal bearings polished and blue matching was done with an excellent area covering of about 95%.

- NDE side THRUST Bearing was replaced with a new 6318C3 bearing.

- Discharge valve gear box overhauled & was made free.

- New Casing gasket & Hollow core type PTFE gland packing provided.

- Clearance of both NDE & DE side journal bearing were taken and are 0.13mm & 0.15mm respectively.

- Finally bearing housing top cover and casing top cover tightened.

Fig: Welding of pitted portion	Fig: Cleaning to be done

Alignment reading:

Axial reading

0

Radial reading

0

0

+07

+02

0		-02

-07

BALANCING   REPORT OF CT PUMP “B” IMPELLER

Recirculation PUMP C

- Pump Top cover dismantled.

- Individual parts were inspected visually.

Following observations were made during inspection:

- Gland sleeves were severely worn out & Gland packings were so hard.

- Pitting found on both side of Impeller suction eye area.

- Both DE & NDE side journal bearings found in good condition.

- NDE side thrust bearing was found damaged.

- Found impeller shifted towards DE side, and about to touch pump casing.

Remedial action taken against the problems:

- A complete new Rotor Assembly of CD4MCu was placed and assembled.

- Individual  parts like throat bush, gland pusher, casing wear ring, were cleaned and buffing done where ever necessary

- Old journal bearings were replaced by completely new journal bearings and blue matching was done with an excellent area covering of 95%.

- Both the bearings housing were cleaned with diesel and throat bush sitting position, casing neck ring sitting position were also cleaned properly.

- NDE side THRUST Bearing was replaced with a new 6318C3 bearing.

- Both sides Bearing housing were replaced with new housing.

- Brush able Ceramic coating applied on damaged/corroded portion of  top & bottom casing  to enhance its life.

- New Casing gasket & Hollow core type Sq.PTFE gland packing provided.

- Clearance of both NDE & DE side journal bearing were taken and are 0.13mm & 0.14mm respectively.

- Finally bearing housing top cover and casing top cover tightened.

Fig: New bearing housing for pump C	                     Fig: Top casing coated with brush able ceramic coating

Alignment reading:

Radial reading                                                                                                 Axial reading

0	0

04

+09

08	09

-05

+12

BALANCING   REPORT OF CT PUMP “C” IMPELLER

Recirculation PUMP S

- Pump Top cover dismantled.

- Individual parts were inspected visually.

Following observations were found:

- Gland sleeves are in good condition only Gland packing’s were damaged.

- Pitting found on both side of Impeller suction eye area.

- Both NDE and DE side journal bearing were found in good condition with minor scratching and dents on its surface.

- Thrust bearing found damaged.

- Suction valve found damaged/passing.

Remedial action taken against the problems:

- The pitting portion of impeller eye was welded & grinded properly and sent to workshop for     Dynamic mass balancing.

- An extra mass of 20 gm at 235 deg was added to the impeller for dynamic mass balancing.

- Individual  parts like throat bush, gland pusher, casing wear ring, were cleaned and buffing done where ever necessary

- Both the bearings housing were cleaned with diesel; throat bush sitting position, casing neck ring sitting position were also cleaned properly.

- Both side journal bearings polished and blue matching was done with an excellent area covering of about 95%.

- NDE side THRUST Bearing was replaced with a new 6318C3 bearing.

- Discharge valve gear box overhauled & was made free.

- New Casing gasket & Hollow core type Sq.PTFE gland packing provided.

- Clearance of both NDE & DE side journal bearing were taken and are 0.12mm & 0.14mm respectively.

- Finally bearing housing top cover and casing top cover tightened.

- Pump “S” suction valve of 1200 mm dia. was replaced with a new butterfly valve.

Fig: pump erection job at site                                                                Fig: Pump “S” suction valve replace

Alignment reading:

Radial reading                                                                                                 Axial reading

0	0

-02

-06	-04		-05

-08	-09

DM PLANT VESSEL ISOLATION VALVE:

Manual isolation valves of each vessel of old DM plant were brought to lower level for safe and approachable operation.

Instrument Air Header

Remaining part of newly fabricated SS304 instrument air header line towards Ammonia storage area hooked up done near reciprocating compressor house to U&O electrical substation.

ETP

1. Clarifier 1 out let line modified-spool piece provided in between-for easy cleaning of this line   by detaching flanged joints.

2. Flow meter installed at clarifier-2 discharge line.

Ammonia Storage:

1. Damaged insulation of ammonia transfer line 8” to DAP, near TP7 & in front of U&O electrical substation, replaced with new insulation.

2. Gland leakages of different sizes of identified ammonia valves were repaired.

3. Ammonia transfer pump “A” suction strainer cleaning and checking done.

Fig: Ammonia transfer pump strainer cleaning                                 Strainer ready for box up.

Orifice fitting:

Orifice fitted on the following lines

1. 6” NB filter water line to ammonia storage area.

2. 6” NB Raw water makeup line for neutralization pit.

3. 6” NB filter water line to township horticulture.

4.16” NB fire hydrant line.

Miscellaneous Job:

1. Filter water line, 700NB, leakage arrested at 12 different positions near TG.

2. Tapping for PH meter provided on SAP cooling tower discharge line header.

3. TG makeup water line leakage arrested at 4 places near U & O substation.

Fig: Filter water line patch welding	Fig: Welding at filter water line

DM Plant

1. Control valves

- Stroke checking of all the control valves installed in DM Plant area had been done.

- Minor adjustments in the positioner and I/Ps were done wherever required.

- All the control valves I/Ps and Positioner were properly cleaned and covered with polythene.

2. Junction Box

All the junction boxes in the DM plant area were properly cleaned, TB tightness ensured and covered with the polythene wherever required.

3. DCS Maintenance

- Controlled shutdown for complete DCS and HMI stations had been taken under the supervision of service engineer from Yokogawa.

- Power supply card of FCS0103 found faulty and replaced with the spare one.

- All the HMIs and Engineering station CPUs were cleaned with blower and reinstalled.

- All the CPU cards, Power supply cards and I/O cards were removed from the back plane and cleaning done by the Yokogawa team and reinstalled.

- Backup of all configured machines have been taken.

- AMC80 card was installed for FCS101.

- Wiring for the AMC80 card was completed.

- Healthiness of VLNet cable was checked.

- All Panels dressing completed

- End Point Security system (Antivirus) has been installed in all HIS and Engg. Station.

Advantages of End Point Security System are:

- Since our network is secured, there is 0% breakdown & 100% availability in Network.so results in breakdown free Operation for operators.

- There is no time delay in any response /input given by operator.

- Good efficiency in operation results in minimizing down time of Equipment’s, results in less operational Cost & Maximizing Production.

- No Panic Situation caused in case of any emergency led by failure of HIS.

- The Downtime of the HIS will be very less comparatively when the HIS failure without any security.

- The Networked DCS system without ENDPOINT SECURITY have open communication and open access for everyone to use their Pen drive to collect plant datas or other confidential official datas. Whereas CS3000 Network with ENDPOINT SECURITY has a very Closed Communication & Full Locked Down so that no datas are stolen and very much secured.

- The use of Pen drives is a major source of Viruses, End Point Security will restrict the use of pen drives  & therefore our system will not get affected by viruses.

4. UPS Maintenance

- Controlled shutdown of UPS had been taken.

- General AMC checkups done by the Emerson engineer.

- UPS taken in line after completion of the AMC jobs.

5. EARTH PIT

- Old Earth Pit of DCS & UPS are replaced with two New Earth Pits.

Ammonia Storage

1. DCS Maintenance

- Controlled shutdown for complete DCS and HMI stations had been taken under the supervision of service engineer from Yokogawa.

- All the HMIs and Engineering station CPUs were cleaned with blower and reinstalled.

- All the CPU cards, Power supply cards and I/O cards were removed from the back plane and cleaning done by the Yokogawa team and reinstalled.

- Backup of all configured machines have been taken.

End Point Security system (Antivirus) has been installed in all HIS and Engg. Station.

Advantages of End Point Security System are:

- Since our network is secured, there is 0% breakdown & 100% availability in Network.so results in breakdown free Operation for operators.

- There is no time delay in any response /input given by operator.

- Good efficiency in operation results in minimizing down time of Equipment’s, results in less operational Cost & Maximizing Production.

- No Panic Situation caused in case of any emergency led by failure of HIS.

- The Downtime of the HIS will be very less comparatively when the HIS failure without any security.

- The Networked DCS system without ENDPOINT SECURITY have open communication and open access for everyone to use their Pen drive to collect plant datas or other confidential official datas. Whereas CS3000 Network with ENDPOINT SECURITY has a very Closed Communication & Full Locked Down so that no datas are stolen and very much secured.

- The use of Pen drives is a major source of Viruses, End Point Security will restrict the use of pen drives & therefore our system will not get affected by viruses.

2. UPS Maintenance

- Controlled shutdown of UPS had been taken.

- General AMC checkups done by the Emerson engineer.

- UPS taken in line after completion of the AMC jobs.

EARTH PIT

- Old Earth Pit of DCS & UPS are replaced with two New Earth Pits.

C.	Utility and Ammonia

SHUTDOWN MAINTENANCE JOBS CARRIED OUT IN ELECTRICAL

DURING ANNUAL TURN AROUND (29th Apr- 16th May 2015)

1.0.	Utility, Ammonia and Cross country Conveyor

1.1	General Maintenance jobs

| Sl. | Type Of Jobs Carried Out/Performed | Job performed By |
| --- | --- | --- |
| 1 | Preventive Maintenance of 33 KV switchgear at Utility & Ammonia Bus Section-B | Departmentally |
|  | Dedusting, Busbar tightness checking, sealing of panels, space heater checking and replacement, Breaker healthiness checking, Testing of closing ,tripping & interlocking Ckt. |  |
| 2 | Preventive Maintenance of 33 KV switchgear at Utility & Ammonia Bus Section-A | Departmentally |
|  | Dedusting, Busbar tightness checking, sealing of panels, space heater checking and replacement, Breaker healthiness checking by on off operation and testing of closing ,tripping & interlocking Ckt. |  |
| 3 | Preventive Maintenance of 6.6 KV switchgear at Utility Bus Section-B | Departmentally |
|  | Dedusting, Busbar tightness checking, sealing of panels, space heater checking and replacement, Breaker healthiness checking by on off operation and testing of closing ,tripping & interlocking Ckt |  |
| 4 | Preventive Maintenance of 6.6 KV switchgear at Utility Bus Section-A | Departmentally |
|  | Dedusting, Busbar tightness checking, sealing of panels, space heater checking, Breaker healthiness checking, Testing of closing ,tripping & interlocking Ckt. |  |
| 5 | Preventive Maintenance of 415 Volt PCC at Utility. De-dusting, Bus bar tightness checking, All joints and terminal check for heating and pitting and breaker healthiness checking etc. | Departmentally |
| 6 | Dedusting, checking of Charger & battery bank, checking of relay & alarm contacts for UTILITY and AMMONIA S/S. | Departmentally both |
| 7 | Thorough Over hauling, Checking, cleaning and testing of SIEMENS make LT AIR CIRCUIT BREAKER – 8 numbers. | External agency(Siemens) |
| 8 | Thorough Over hauling, Checking, cleaning and testing of SIEMENS make 6.6 KV vacuum circuit breakers. | External agency(Siemens) |
| 9 | Testing of selected relays installed in the 33kV panel, 6.6 KV switch gear panel , PCC and emergency MCC panel at utility and Ammonia. | External agency(Power system) |
| 10 | Preventive Maintenance of MCCs ( Siemens Compressor MCC, MCC-2B, Old DM plant MCC, Raw water MCC, and Conv.MCC at Utility. De-dusting, Bus bar tightness checking, all power cable/lead, control connection tightness checking and motor feeders healthiness checking etc. | Departmentally |
| 11 | O/H of Filter water transfer pump motor - 101B, 475KW, 1500 RPM and Over hauling the Ammonia transfer pump at ammonia | Departmentally |
| 12 | Maintenance of conveyor Pull chord switches at R-5 conveyor. | Departmentally. |
| 13 | Preventive Maintenance of MCCs ( ABB MCC, New Zypsum pond MCC, 500 kVA Tr MCC, PDB, LDB, at old Substation and MCC maintenance at new Export tank substation) at Ammkonia . Jobs Carried out:- De-dusting, Bus bar tightness checking, all power cable/lead, control connection tightness checking for any heating at joints and contactors,Motor feeders control healthiness checking by performing on off operation.etc. | Departmentally |

1.1	New jobs Installation and commissioning

| Sl. | Type Of Jobs Carried Out/Performed | Job performed By |
| --- | --- | --- |
| 1 | Retrofitting, commissioning and testing of 6.6 kV Vacuum contactor feeders with Breaker feeders. For 2 nos BFW motors (each 900 kW) and 2 Nos (Cenrifugal air compressor feeders. (each 650kW) at Utility Substation. | External agency & Departmentsl(Siemens) |
| 2 | Shifting of Battery banks from stores to Utility and ammonia areas, Installation, Performing Charging and discharging cycles using Salt bath, testing and commissioning the Battery banks for both Utility and Ammonia areas. | Departmentally. |
| 3 | Shifting of Battery Chargers from stores to Utility and ammonia areas, Installation, Performing capacity testing by salt bath discharge, and commissioning the Battery banks for both Utility and Ammonia areas. | Departmentally. |
| 4 | Shifting the Incoming power cables from Old DC Charger & Battery set to new Battery Charger/ battery bank. | Departmentally. |
| 5 | Shifting the MCC-2A DC Power source from 1 no DC Distribution board to 2 no Dc distribution board. | Departmentally. |
| 6 | Shifting of 3 numbers Zypsum pond motor cables from Old Panel to new Zypsum pond MCC and testing and commissioning of the same. | Departmentally. |
| 7 | Retrofitting of old Differential relays with new P642 differential relays in 33 kv panel at Ammonia substation. | External agency( Santy suppliers) |
| 8 | Shifting of cables from MCC2B1 to MCC 2B and isolating the MCC-2B panel for scrap. | Departmentally. |
| 9 | Modification and preparation of Breaker feeder for new Silo Conveyor R-11A. | Departmentally. |
| 10 | Replacement of BMR with MiCom P211 relays for motor feeders of CTP, PCTP, PDG-1 &2, Gypsum pond pumps-A, B , C and Back wash pump-A. Total 10 numbers | Shanti suppliers. |

INDEX

| Sr. No. | TOPIC | PAGE NO. |
| --- | --- | --- |
| 1 | COOLING TOWER PUMPS | 02 - 04 |
| 1.1 | COOLING TOWER PUMPS - B | 02 - 03 |
| 1.2 | COOLING TOWER PUMPS - D | 03 - 04 |
| 2 | TG COOLING TOWER | 04 - 08 |
| 2.1 | CLEANING OF TG CT SUMP AND BASIN | 05 - 06 |
| 2.2 | TG COOLING TOWER INSPECTION & REPAIRING | 06 |
| 2.3 | BLOW DOWN VALVES | 06 |
| 2.4 | REPLACEMENT OF PAP PROCESS WATER LINE VALVE AT CT PUMP S DISCHARGE | 07 |
| 2.5 | REPLACEMENT OF 4” GATE VALVE IN COOLING WATER LINE TO OLD CHLORINATION SYSTEM | 07 |
| 2.6 | FLOW CONTROL VALVES | 07 |
| 2.7 | CLEANING OF NOZZLES | 07 |
| 2.8 | INSPECTION OF VAG FILTER | 08 |
| 2.9 | REPAIRING OF TG CT SUCTION & DISCHARGE EXPANSION BELLOWS. | 08 |
| 3 | STEAM SYSTEM | 09 - 14 |
| 3.1 | REPLACEMENT OF OLD HP TO LP PCV WITH NEW ONE: | 09 - 11 |
| 3.2 | REPLACEMENT OF TG2 PRDS PRESSURE CONTROL VALVE | 11 - 12 |
| 3.3 | MODIFICATION IN LP STEAM LINE TO DAP | 12 - 14 |
| 4 | TG CONDENSERS | 14 - 17 |
| 4.1 | REPLACEMENT OF 1000 NB TG1 CONDENSER ISOLATION VALVE | 14 -15 |
| 4.2 | CONDENSER TUBE CLEANING | 15 - 16 |
| 5 | OIL COOLER TUBE CLEANING | 16 - 17 |
| 5.1 | OIL COOLER WATER LINE STRAINERS | 18 |
| 6 | ISOLATION AND SAFETY VALVES OVERHAULING | 19 - 21 |

1. COOLING TOWER PUMPS

TG CIRCULATING WATER PUMP

Make				: MATHER & PLATT

Type of pump			: 30”/30” ALE-T DV

Capacity			: 7750 m3/hr

Net head			: 37.86 M

Drive				: Electric Motor

1.1 COOLING WATER PUMP -B

Cooling water pump-B was opened for inspection.

Activity involved:

1. De-coupled for motor overhauling.

2. Removal of Top casing.

3. Inspection of Rotor assembly, journal bearings and Ball bearing were done.

4. Rotor assembly impellor (SS304) was found in eroded condition. Then it was replaced with new rotor assembly (CD4MCU) after balancing.

5. NDE side Ball bearing (6315) was replaced as play was found in old one.

6. Cleaning of top and bottom casing, neck ring.

7. Then the pump was Boxed-up

Execution of job:

This job was executed departmentally by Technician and semiskilled & unskilled manpower supplied by M/S OMM Traders, W.O.No.-6600/252004142522.

After motor received, alignment job completed & the pump is ready for operation

CWP-B  box up work under progress:

Alignment readings

Pump “B”. (Coupling flange Gap: 5 mm)

Radial			Axial1			         Axial2

(-0.06)                                  (+0.07)                                 (+0.07)

(0.0)------R----- (-0.02)        (0.0) ------A1------(+0.12)         (+0.15)----A2----(0.0)

(-0.01)                                  (+0.03)                                     (+0.03)

1.2 COOLING WATER PUMP -D

Cooling water pump-D was opened for inspection.

Activity involved:

1. De-coupled for motor overhauling.

2. Removal of Top casing.

3. Inspection of Rotor assembly, journal bearings and Ball bearing were done.

4. Rotor assembly impellor (CD4MCU) was found in eroded condition. Then it was replaced with old rotor assembly from pump-B (SS304) after filling with titanium devcon putty.

5. Cleaning of top and bottom casing, neck ring.

6. Then the pump was Boxed-up

Photograph of Erosion on Rotor assembly impellor:

Execution of job:

This job was executed departmentally by Technician and semiskilled & unskilled manpower supplied by M/S OMM Traders, W.O.No.-6600/252004142522.

2. TG COOLING TOWER (MAKE: PAHARPUR COOLING TOWER LTD.)

Type		: Induced draft

No of cell		: 10 (Ten)

Model no		: 6615-4.0-10

Capacity		: 33000m3/hr.

2.1 CLEANING OF TG CT SUMP AND BASIN

Problem:

Ingress of fly ash and dust from neighboring plants in cooling tower. The parameters of cooling water are maintained by chemical dosing & supplying blow down water to PAP. However the sludge deposited in basin & sump.

Planning:

It was planned to clean the sludge, debris expected to settle down from the sump & basin during annual shut down.

Execution of job:

The cleaning of sump & basin job was executed by M/S Prasana Rout  (W.O no-6600/252004150598) .

BEFORE BASIN CLEANING				     AFTER BASIN CLEANING

AFTER SUMP CLEANING

2.2. TG COOLING TOWER INSPECTION & REPAIRING:

Agency Involved: M/s Paharpur Cooling Tower			    W.O. No.: 252004141875

Duration: From: 01st April 2015		To: 09th April 2015               Total Days: 09 Days

Detail: Inspection of cooling tower was done and rusted structure nut bolt of 8th, 9th & 10th cell was replaced. Mastic applied to seal the leakages from end wall of the cooling tower. Damaged partition wall in between cell no 1 & 2 and 9 & 10 repaired.PVC sheets fitted below the bottom louver of south side cooling tower to avoid spillage of water.

2.3 BLOW DOWN VALVES

- 05 nos. of new blow down valves were replaced (No. 2nd, 4th, 6th, 8th & 10th) & remaining 02 valves were overhauled.

Execution of job:

This job was executed by M/S OMM Traders, W.O.No.-6600/252004142522.

2.4 REPLACEMENT OF 6”, 150# GATE VALVE IN COOLING WATER LINE TO PAP PROCESS WATER.

One   6”, 150#  Gate valve replaced in Tapping from CWP– S to PAP  process water as it was not in operated condition.

2.5 REPLACEMENT OF 4”, 150#  GATE VALVE IN COOLING WATER LINE TO OLD CHLORINATION SYSTEM .

- One   4”, 150# Gate valve replaced in Tapping from cooling water header to old chlorination line.

- Execution of job

This job was executed by M/S OMM Traders, W.O.No.-6600/252004142522.

2.6 FLOW CONTROL VALVES

All (20 nos.) flow control valves of cooling tower were overhauled & then boxed up. The job was executed departmentally.

2.7 CLEANING OF NOZZLES

Cleaning & replacement of 300 nos. of of damaged nozzles were carried out departmentally

2.8 INSPECTION OF VAG FILTER

Inspection of VAG filter was done after opening the manholes & after cleaning manholes were boxed up.

Execution of job:

This job was executed by M/S OMM Traders, W.O.No.-6600/252004142522.

2.9 REPAIRING OF TG CT SUCTION & DISCHARGE EXPANSION BELLOWS.

Cooling water pump suction & Discharge Expansion bellows were damaged and repaired by application of brushable ITW Flexon by the party. (Order no.- 6600/ 252004152572 BEFORE REPAIRING PHOTOGRAPH 	          AFTER REPAIRING PHOTOGRAPH

3. STEAM SYSTEM

3.1 REPLACEMENT OF OLD HP TO MP PCV WITH NEW ONE:

Agency Involved: Departmentally & manpower support from M/s Omm traders

Duration: From: 29th March 2015		To: 12th April 2015                 Total Days: 15 Days

PHOTOGRAPH OLD HP TO MP STEAM HEADER SYSTEM BEFORE MODIFICATION:

PCV (Make Forbes Marshal)

Attemperature Line

Detail: There are two HP to MP PRDS, one is old and other is new. In old HP to MP PRDS both pressure reduction and spray for attemperature occurs at PCV (Forbes marshal make) i.e integrated type PCV. During ATR 15 old HP to MP integrated PCV (Forbes marshal make) replaced with new PCV (Fisher make).

Drawback:

- Valve plug was getting damaged regularly due integrated assembly of attemperator and PCV & also valve stem wrecked frequently.

- Valve stroke movement was not uniform.

PHOTOGRAPH OLD HP TO MP STEAM HEADER SYSTEM AFTER MODIFICATION:

New PCV

Attemperature Line

Details: In modified system integrated assembly of attemperator and PCV are replaced with new PCV (Fisher make) having separate attemperature point.

Advantage: In new system chances of Valve plug getting damage will be less and valve stroke will become smooth hence overall reliability of old HP to MP PRSD improved.

3.2 REPLACEMENT OF TG2 PRDS PRESSURE CONTROL VALVE:

Agency Involved: Departmentally & manpower support from M/s Omm traders

Duration: From: 29th March 2015		To: 12th April 2015                 Total Days: 15 Days

PHOTOGRAPH OF TG 2 PRDS PRESSURE CONTROL VALVE REPLACEMENT JOB:

PCV (Fisher make)

PCV (Forbes Marshal)

Details: TG 2 PRDS pressure control valve was of Forbes Marshal make and it was   replaced with new pressure control valve of Fisher make.

Drawback:

1. Valve was not able to maintain set discharge pressure.

2. Valve was getting stuck frequently at one position.

Advantage:  After replacement of pressure control valve discharge pressure is maintained and valve operation become smooth hence overall reliability of TG 2 PRDS improved.

3.3 MODIFICATION IN LP STEAM LINE TO DAP:

Agency Involved: M/s Royal Enterpriser   			      W.O. No: 252004160096

Duration: From: 8th April 2015		To: 12th April 2015                 Total Days: 06

ACTUAL LP STEAM SYSTEM TO DAP:

ACTUAL LP STEAM SYSTEM TO DAP:

Details: LP steam to DAP is supplied through tapping of 10” line taken from the upstream of PCV 1514 installed in 950 NB LP steam header to PAP. One more provision of 14” line was there for LP steam to DAP from the downstream of PCV 1514 at pressure 1.25 Kg/cm2 but as sufficient pressure was not obtained from this line so it was always in isolated condition. Hence LP Steam to DAP was supplied through 10” line.

Disadvantage: As LP steam to DAP was supplied through 10” line so during running of all DAP at full load it was difficult to maintain the LP steam pressure.

MODIFIED LP STEAM SYSTEM TO DAP:

Details: In modified system old tapping of 14” line from downstream of the PCV were removed and 10” piping portion of the LP steam line to DAP taken from upstream of PCV 1514 was converted to 14” by using dismantled pipe.

Advantage: Now even running of all DAP at full load LP steam pressure is maintained.

PHOTOGRAPH OF MODIFICATION IN LP STEAM LINE TO DAP:

4. TG CONDENSERS:

4.1 REPLACEMENT OF 1000 NB TG1 CONDENSER ISOLATION VALVE:

Agency Involved: M/s R.S. Engineering   			      W.O. No: 252004151571

Duration: 	From: 1st April 2015		To: 12th April 2015                 Total Days: 12 Days

Photograph of 1000 NB TG 1 condenser isolation valve replacement job:

Details: Two 1000 NB condenser isolation valves of kirloskar brother ltd. make with companion flange was procured through it’s authorize dealer M/s Industech ltd. During ATR 15 both inlet and outlet valve (Audco Make) of one pass of TG 1 condenser is replaced with new one.

Problem: All valves installed at condenser inlet and outlet pipelines are passing so it becomes impossible to inspect & clean the condenser tubes in plant running condition.

Advantage: After replacing the old audco make butterfly valves with new KBL make valve there is no water passing so it becomes possible to inspect & clean the condenser tubes in plant running condition.

4.2 CONDENSER TUBE CLEANING:    Condenser Specification

Type                      : - 	Shell and tube type surface condensers

No. of tubes          : - 	7000

Diameter of tube   : - 	25mm

Length of tube      : - 	9 mts.

M.O.C. Of tubes   : - 	SS304

Agency Involved: M/s 5-S Engineering Co.   	                   W.O. No: 252004151295

Duration: From: 31st March 2015		To: 03rd April 2015                 Total Days: 04

Problem:  It was observed in the past that temperatures and vacuum in the condenser are increased due to ash and dust ingress into cooling tower which in turn tend to deposit inside the condenser tubes.

We planned to clean the condenser tubes by hydrojet method with pressure 180 -200 bar during shutdown.

Action taken: Work was allotted to 5-S Engineering company P.O. No.-6600/252004151295 to carry out the job by hydrojet method using flexible hoses within three days time.

Job execution:  The job was executed by 5S –E ngineering under the supervision of IFFCO Engineer. Job started on 31/03/2015 and completed on 03/04/2015.

Ash, sludge and some wooden pieces were found inside water box of condensers

Cleaning of condenser tubes by hydrojet            Condenser tubes after cleaning method

5. OIL COOLER TUBE CLEANING:

Agency Involved: M/s 5-S Engineering Co.   	                   W.O. No: 252004151295

Duration: From: 04th April 2015		To: 04th April 2015                 Total Days: 01

NUMBER OF TUBES:-178

DIAMETER OF TUBES:-19mm

LENGTH OF TUBES: - 1.83 mts.

Problem: Due to deposition of ash & sludge in the tubes it is observed that the oil temperature rise.

Planning: It was planned to clean the tubes of oil cooler by hydrojet method.

The job was allocated to 5S Engineering included in the same work order with the condenser cleaning- OrderNo.-6600/252004151295

Job execution: Job was carried out by the 5S Engineering in one day under the supervision of IFFCO Engineer. Cleaning was done at 180-200 bar pressure. Job started on 04/03/2015 and completed on same day.

Sludge found on tube sheet of oil cooler

5.1 OIL COOLER WATER LINE STRAINERS:

Cooling water line to oil cooler is provided with strainers; it was observed that due to choking of strainers proper cooling of oil does not take place resulting in high temperature of oil.

Planning: It was planned to take out the strainers clean it.

Job execution: Strainers were taken out cleaned and boxed up.

| SR. NO. |  | VALVES |  | SPECIFICATIONS |  | OBSERVATIONS |  | ACTIVITIES CARRIED OUT |  | SPARES USED |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | TG-1 PRDS ISOLATION |  |  |  |  |  |  |  |  |  |
|  |  | 1st isolation |  | 150nb, 1500# Gate valve, pressure seal type |  |  |  | 1. Dismantling . 2. Cleaning 3. Lapping of valve seat. 4. lapping of valve disc. 5. Blue matching checked. 6. Box-up. |  | 1. Pressure seal ring-1 no. Pure Graphite (8X16X150) 2520142100145000 2. Gland Packing Ring- 7 nos. Pure Graphite (8X8X32) 2520142100124800 |  |
|  |  | 2 nd isolation |  | 150nb, 1500# Gate valve, pressure seal type |  | Retainer ring found damaged. |  | 1. Dismantling . 2. Cleaning 3. Lapping of valve seat. 4. lapping of valve disc. 5. Blue matching checked. 6. Box-up. |  | 1. Pressure seal ring-1 no. Pure Graphite (8X16X150) 2520142100145000 2. Gland Packing Ring- 7 nos. Pure Graphite (8X8X32) 2520142100124800 3. Retainer ring (5X8X150)-1 no.( Made from P11 pipe line) |  |
| 2 |  | Old HP to LP isolation |  | 200nb, 1500#, Gate valve, Pressure seal type |  |  |  | 1. Dismantling . 2. Cleaning 2. Lapping of valve seat. 3. lapping of valve disc. 4. Blue matching checked. 5. Box-up. |  | 1. Pressure seal ring-1 no. Pure Graphite (10X18X200) 2520142090145000 2. Gland Packing Ring- 7 nos. Pure Graphite (10X10X45) 2520142090124800 |  |
| 3 |  | TG-1& 2 4530 |  | 200nb, 300#, Gate valve |  |  |  | 1. Dismantling . 2. Cleaning 3. Lapping of valve seat. 4. lapping of valve disc. 5. Blue matching checked. 6. Box-up. |  | 1. Gland packing rope fitted- 8mm metallic . 2. Metallic gasket- 3mm (Bonnet) |  |
| 4 |  | MP Vent Isolation Valve |  | 200nb, 300#, Gate Valve |  | Leakage from valve bonet and flanges |  | 1. Dismantling . 2. Cleaning 3. Lapping of valve seat. 4. lapping of valve disc. 5. Blue matching checked. 6. Steel putty used to prepare valve flanges. 7. Box-up. |  | 1. Gland packing rope fitted- 8mm metallic . 2. Metallic gasket- 5mm (Bonnet) |  |
| 5 |  | TG-1 Ejectors air side Valves V4151, V4152 & V4153 |  | 150nb, Gate Valve |  |  |  | 1. Dismantling . 2. Cleaning 3. Lapping of valve seat. 4. lapping of valve disc. 5. Blue matching checked. 6. Box-up. |  | 1. Gland packing rope fitted- 10mm metallic . 2. Metallic gasket- 3mm (Bonnet) |  |
| 6 |  | TG-1 Cross over Drain V1910 |  | 65nb, 1500# Gate valve, pressure seal type |  |  |  | 1. Dismantling . 2. Cleaning 3. Lapping of valve seat. 4. lapping of valve disc. 5. Blue matching checked. 6. Box-up. |  | 1. Pressure seal ring 2. Gland Packing Ring |  |
| 7 |  | LP Steam to DAP isolation |  | 350nb,, 150# Gate valve, |  |  |  | 1. Dismantling . 2. Cleaning 3. Lapping of valve seat. 4. lapping of valve disc. 5. Blue matching checked. 6. Box-up. |  | 1. Gland packing rope fitted- 10mm metallic. 2. Metallic gasket- 3mm (Bonnet) |  |
| 8 |  | MP Safety Valve |  | 150nb,600#, |  |  |  | 1. Dismantling . 2. Cleaning 3. Lapping of valve seat. 4. lapping of valve disc. 5. Blue matching checked. 6. Box-up. |  | 1. 3mm metallic gasket |  |

6. ISOLATION AND SAFETY VALVES OVERHAULING:

Agency Involved: M/s EFCO MASCHINENBAU                   W.O. No: 252004141936

Duration: From: 02nd April 2015		To: 10th April 2015                 Total Days: 09

1PCV4510

ISSUES REPORTED

- Valve was reported for slow performance.

- It’s I/P location was not suitable for carrying out hassle free maintenance.

MAINTENANCE ACTIVITIES

- Overhauling was performed. Packing set and gasket were replaced

- I/P location were changed.

- Air regulators for I/P and Control valve were changed.

SPARES USED

Gasket, Packing ring were changed.

2PCV4510

ISSUES REPORTED

1. Valve was reported for abnormal stroke movements on few occasions

MAINTENANCE ACTIVITIES

- Valve stroke was adjusted.

- Overhauling was performed and the plug was found to be corroded. Hence was replaced along with packing set and gasket.

- Air regulators for I/P and Control valve were changed.

SPARES USED

Gasket, Packing Ring and Plug were changed.

PCV2632

ISSUES REPORTED

- Leakage from gland packing of the valve.

- Valve stroke was uneven.

MAINTENANCE ACTIVITIES

- Valve plug was found to be distorted and was replaced.

- Cage was cleaned by sand blasting.

- Overhauling was performed. Piston rings were damaged and were replaced.

- Air regulators for I/P and Control valve were changed.

SPARES USED

Plug, Gasket, Piston Ring and packing ring were replaced.

PCV2630

ISSUES REPORTED

- Leakage from actuator was noticed which resulted in reduced performance.

- Valve was getting stuck at a particular position

MAINTENANCE ACTIVITIES

- O-Ring for the actuator was changed.

- Proper lubrication was performed for plug. Stroke adjustment was also performed.

- Air regulators for I/P and Control valve were changed.

SPARES USED

O-ring set

. TCV2631

ISSUES REPORTED

- Sluggish performance of the valve.

- Improper stroke length

MAINTENANCE ACTIVITIES

- Valve plug was replaced with new one.

- Stroke adjustment was done

- Overhauling was performed. Packing set and gasket was replaced.

SPARES USED

Packing set, gasket and Plug

PCV1551

ISSUES REPORTED

- Valve plug was getting damaged regularly due integrated assembly of attemperator and PCV.

- Valve stroke movement was not uniform.

MAINTENANCE ACTIVITY

- Arca Make PCV1551 was replaced with Fisher make PCV1551.

- Attemperator assembly was also changed.

- Fisher make PCV1551 plug was replaced.

- Cage was cleaned with sand blasting

- Overhauling was performed for the valve. Piston and packing ring along with gasket were replaced.

- Air regulators for I/P and Control valve were changed.

SPARES USED

Plug, Gasket, Piston Ring, Packing Ring

PCV2631

ISSUES REPORTED

- Valve was not able to maintain set discharge pressure.

- Valve was getting stuck at one position

MAINTENANCE ACTIVITY

- Arca Make valve was replaced with Fisher make Valve

- Cage was cleaned with sand blasting.

- Overhauling was performed. Piston ring, gasket and packing ring were replaced.

- Air regulators for I/P and Control valve were changed.

SPARES USED

Piston Ring, Gasket and Packing Ring

PCV909

ISSUES REPORTED

- No hand wheel was present in the valve.

MAINTENANCE ACTIVITY

- IL make and Hand Wheel enabled valve was installed for the same.

- I/P cable and instrument location for the valve was re-routed

- PT909 was subsequently re-routed.

- Valve stroke was checked and slight adjustment was made for the same

COMMISSIONING-LCV1406

INSTRUMENT ACTIVITIES:

- Spare channel was identified and I/P was installed for the same.

- Cable laying from I/P to JB and tubing from I/P to positioner was performed.

- Closed loop logic of LCV1406 with LT1406 was made in DCS

PAP VENT AREA

INSTRUMENT ACTIVITIES:

- Air regulators for PCV1513, PCV1514, PCV909 and PCV1514A were replaced with new one.

- Minor Stroke adjustment was performed for PCV1513, PCV1503 and PCV1514A.

- Greasing for PCV1513, PCV1514, PCV1503, PCV1514A was performed.

TRIP INSTRUMENT CALIBRATION

TG1 and TG2 trip switches were calibrated i.e. all the lube oil and vacuum switches.

DCS RELATED ACTIVITIES

SIEMENSDCS- ENERGY CENTRE

- HMI and controllers were formatted individually.

- Hard disk for sa083502 was found to be faulty. It was replaced with a new one.

- All the 10 controllers were sprayed with TECH SPRAY.

- Data base server migration was performed

- Anti-virus patch was updated.

- Drives and Control Valves testing were performed.

- SoftOM software for the HMI was updated.

- 2 No. Engineering back up station were created.

- Time Synchronization was performed with sa083101 as master

- Hooter logic was also cross checked and made through.

- 03FC01 panel dressing was completed

UPS RELATED ACTIVITIES

- Emerson Make 2 No. 25KVA UPS were taken into line.

- Battery for the same new UPS was taken into line.

EARTH PIT

- Old Earth Pit of DCS & UPS are replaced with two New Earth Pits.

| SHUTDOWN JOB STATUS AT ENERGY CENTRE (ELECTRICAL) DURING ATR-2015 |  |  |  |
| --- | --- | --- | --- |
| SL.NO | Job description | Agency / internal resources | Spare / components replaced, used. |
| 1 | 33 KV Bus Section I&II VCB cleaning, VCB chamber cleaning, tightness checking, physical checking of CT &PT , control connection checking, space heater checking and replacement ,indication lamp checking and replacement, both section busbar insulation resistance checked between phases and between phase and earth . Section -I : Ph-Ph :- 530 G-Ohm and Ph-Earth : - 600 G-Ohm. Section-II : Ph-Ph:- 490 G ohm and Ph-Earth :- 570 G-ohm | Departmental & External (Puja Engineering) | Space Heaters, Indication Lamps, 7SJ Relay front facia , Red insulating varnish, contact cleaner and markin Cloth etc. |
| 2 | 6.6 KV Bus Section I&II VCB cleaning, VCB chamber cleaning, tightness checking, physical checking of CT &PT , control connection checking, space heater checking and replacement ,indication lamp checking, Tie bus bar cleaning, both section bus bar insulation resistance checked between phases and between phase and earth . Section -I : Ph-Ph :- 720 G-Ohm and Ph-Earth : - 102 G-Ohm. Section-II : Ph-Ph:- 890 G ohm and Ph-Earth :- 72 G-ohm | Departmental & External (Puja Engineering) | Space Heaters, Indication Lamps, 7SJ Relay front facia , Red insulating varnish, contact cleaner and markin Cloth etc. |
| 3 | 415 Volt PCC Bus Section I,II and III ACB cleaning, ACB chamber cleaning, tightness checking, control connection checking, space heater checking and replacement ,indication lamp checking, all section bus bar megger taken between ph- Earth and found OK. Replacement of one Incomer ACB,3200A by spare one at TR#40 | Departmental & External (Puja Engineering) | 3200A, GE make ACB, Red insulating varnish, contact cleaner and markin cloth. |
| 4 | TG#1 & TG#2 MCC cleaning ,thorogh maintenance, replacement of worn out contactors, kits, BMR, checking of control connection ,inspection and replacement of control terminals CT terminals etc. | Departmental & External (Puja Engineering) | Power circuit terminals, Contactor Kits of ML-10 : 2 Sets, ML-6 : 2 Sets and MN-5 BMR: 1 No. |
| 5 | 220 Volt ,50 Amps New Battery Charger (make Universal) for TG 2 installation & commissioning, load testing and taken in service. | External & departmental both. | New Universal make Battery Charger and one no. voltage transducer. |
| 6 | Both HV/LV side chamber cleaning, oil leakage arrest, bushing tightness, terminals tightness, bus duct maintenance & painting done. | Departmental & External (Nirman Associates) | Bus duct repairing & painting . |
|  | Both HV/LV side chamber cleaning, oil leakage arrest, bushing tightness, terminals tightness, bus duct maintenance and NGR box maintenance done. Neutral side stud was replaced in NGR(TR-36) | Departmental & External (Swagatika Enterprises) | Bus duct and NGR maintenance. |
|  | One radiator was replaced in TR-4 and three no of radiators were replaced in TR-5. Oil leakage arresting was done in both transformers. | Departmental & External (Voltamp Ltd) | New Radiators : 4 Nos. |
| 7 | 33 KV and 6.6 KV VCB and vacuum contactor feeder overhauling done. Retrofitting of one no vacuum contactor feeder to Vacuum Circuit Breaker. | Siemens | Overhauling job completed and retrofitting of one breaker is also done.(New 6.6 KV VCB, Siemens make) |
| 8 | TG#1 & TG#2 all motorised actuator valve Auma and limit torque cleaning , thorogh maintenance and testing of operation from local as well as remote. | Auma / Limitoque | Pending |
| 9 | Protective Relay and Current Transformer Testing . | Power System | Completed for all relays installed in all 33kV and 6.6 kV O/G incomers and feeders. |
| 10 | Thorough overhauling and maintenance of L&T make ACBs . | External (S.K.Engineers) | ACBs of TG-1 MCC ( Both Incomers) completed. |
| 11 | Preventive maintenance and fault rectification of Rockwell LMS system | External(Rockwell) | Details of job carried out as per attached annexure. |
| 12 | New Server made ready and clients created (also for DCS C/R),maintenance of all processor, sub-processor panels, Desktops, CPUs, modification in energy report formats, Client screens | Rockwell | Details of job carried out as per attached annexure. |
| 13 | SAP & TG Cooling Tower pump motor (HT) overhauling and cooling tube replacement. (TG , 1020KW: CWS101A,CWS101S & CWS101D), Comp. Cooling water Pump Motor, 180KW : 103S, (SAP, 1150KW : CWS 102S) | External | New Cooling Tubes, Bearings and Painting. |
| 14 | Shifting of power cables, control cables of two TGCT fan motors from old TGCT panel to new panel | Departmentally & from external party. | Cable termination items, lugs, glands etc. |
| 15 | Existing Battery Charger preventive maintenance and operation, battery bank status checking, | External | Health Check up. |
| 16 | Capacitor Bank cleaning and maintenance, RVT maintenance and oil top-up | Departmentally | HV bushing stud , 200A :1 No. |
| 17 | Installation, commissioning, testing of Micom P642 in E/C-2 33 kV feeder for differential protection. | Departmentally & from external party. | New P642 relay. |
| 18 | Interconnection of S/Y and S/G DCDB | Departmentally | 25A D/P Switch : 2 nos., and SM63 Fuse Base and carrier : 4 Nos. |
| 19 | Maintenance of all PT Cubicle,CT cubicle,Space heater cubicle for both generators | Departmentally | CT Terminal : 8 Nos. |

INDEX

| SR. NO. | TOPIC | PAGE NO. |
| --- | --- | --- |
| 1 | C6 CONVEYOR GALLERY REPLACEMENT | 3 -11 |
| 2 | Coal Handling Plant | 12 - 18 |
| 3 | Boiler # 01 ( OR – 806) | 19-23 |
| 4 | Boiler # 02 ( OR – 805) | 24-27 |
| 5 | Cleaning & Repair of Ash silo & Vent filter and overhauling of ash unloader -2. | 28-30 |
| 6 | Boiler -2 ESP Inspection & corrective action | 31 - 32 |
| 7 | Duct Inspection & corrective action | 33-36 |
| 8 | Chimney Inspection & Cleaning. | 37-37 |
| 9 | Replacement of expansion bellow in between ID discharge Duct & chimney | 38- 39 |
| 10 | Overhauling of Diff. Valves & NRV of main steam line of Boiler # OR/805 & OR/806. | 40-55 |
| 11 | Miscellaneous Maint. In AFBC Boiler | 56 - 56 |

- C6 CONVEYOR GALLERY REPLACEMENT

Belt Description : 	Belt Width – 800mm , Belt Speed – 1.0 m/sec

Length – 46.00 mtr. (C/C) ,  Length along Belt Line – 46.98 mtr.

Capacity – 150TPH / 165 TPH (Rated / Design)

Cover grade – M24, Top / Bottom Cover thk.– 4/4

Max. Working Tension – 13700N, Rating / Duty – 1000/4 HD

Duck Material – N/N

Gear Box  -         	Type – Helical, Size – SCH – 160, Ratio – 35.5 :1

Motor Rating -	Power - 15 KW, Speed – 1440 RPM

Problem:

Conveyor  gallery structures was badly corroded / damaged and no one allowed to walk on walk way due to unsafe condition. So maintenance of carrying / return idlers, bend pulleys , take-up pulley & snub pulley are very difficult to attend, so it needs replacement immediately .

Activity involved:

- Pedestal casting for additional two nos. trestle

- Removal of existing power , pull chord , Zero speed switch cable

- Removal of skirt boards & skirt rubber

- Locking dead weight

- Removal of belt

- Removal of bend , take- up & snub pulleys.

- Removal carrying & return idlers.

- Dismantling of galleries.

- Erection of additional trestle 02 nos.

- Erection of galleries 05 nos.

- Alignment of all the galleries.

- Erection of pulleys, Idlers and belt

- Jointing of belt

- Erection of skirt board ,skirt rubber & release of take – up pulley.

- Laying & jointing of all the power cable

- Alignment of belt & Trial run taken

- Hood cover  SS 304 sheet 0f 02 mm thk. Erection.

Execution of Job:

Planning has been made for replacement during the shutdown with additional trestle support for heavier cross section of gallery.  Accordingly pedestal casting , pre- fabrication of trestle & gallery are started .

Initially  pedestal job carried out by civil department through M/S Coastal construction against W.O No. 252004151795 . The said agency start the piling job in-between transformer 03 & 04 by demolishing of transformer separation fire wall , asbestos sheet followed by pedestal casting of additional new trestle no. 01 and it was continued for pedestal casting of additional new trestle no. 02 in-between transformer 01 & 02 .

To carry out the execution of civil job, Transformer shed purlin dismantled phase wise and temporary pipe rack support column fabricated & erected for safe of pipes and clearance given for piling work. Pre- fabrication of 02 nos. of trestle and 05 nos. of galleries having length of 5.50 mtr., 7.50 mtr.,9.00 mtr., 8.00 mtr., 9.50 mtr. to accommodate 39.50mtr.length and replace existing galleries having length 5.50 mtr. , 16.50 mtr., & 17.50 mtr.are executed by M/S Behera Engineering works Pvt. Ltd. against W.O No. 252004151627.

Both the additional supporting trestles & all the 05 nos. of  galleries pre- fabrication are completed in all respect at ground level i.e both sides walk way 1000mm width each covered by G.I gratings and S.S 304 hand railings for safety point of view with epoxy painting.

During the shutdown period M/S Behera Engineering works Pvt. Ltd. start the job round the clock as per activity schedule . Dismantled the existing gallery in 03 pieces phase wise with proper safety , then erection of additional two trestle are carried out after that 05 nos. of new fabricated galleries are erected one by one by maintaining angle of repose from 6degree to 14 degree in between tail and head end of said conveyor. 800 mm width belt erection and hot vulcanizing done after erection of carrying idlers , return idlers, proper lagging of bend pulleys & snub pulley.  Then alignment of belt & trial run taken. Conveyor  hood are fabricated & erected by S.S 304, 02 mm thk. sheet to avoid further corrosion and fumes comes from DAP plant.

To execute the above mentioned job M/S Swagatika Enterprises are supported to carry out removal of existing power cable, pull chord , Zero speed switch cable & light post. After clearance from mechanical , cable laying , dressing with new cable trays, jointing , erection of light post are done in very short period of time against W.O no. 252004152360 in all respect.

Dismantling of Conveyor gallery started from tail end.

Dismantling of gallery going on with the help of two cranes.

Corroded / damaged C6 conveyor gallery.

Pedestal foundation for the additional trestle.

New gallery erection going on, after erection of the additional two trestles.

Final erection & alignment of gallery completed.

Comparison between before & after modification.

| Sl.No. | Item Description | Before Modification | After Modification |
| --- | --- | --- | --- |
| 01 | Trestle | Two ( 02) | Four (04) |
| 02 | Nos. of Gallery | Three (03) 1st – 5.50 mtr. 2nd – 16.50 mtr. 3rd – 17.50 mtr. | Five (05) 1st- 5.50 mtr. 2nd – 7.50 mtr. 3rd - 9.00 mtr. 4th – 8.00 mtr. 5th - 9.50mtr. |
| 03 | Structural Steel used | 22.00MT | 32.256MT |
| 04 | Fabricated gallery | Angles used as load carrying beam | Channels used as load carrying beam |
| 05 | Conveyor Hood | 2mm thk. G.I Sheet | 2mm thk. S.S 304 Sheet |
| 06 | Hand Railing | M.S Pipe | S.S 304 pipes |
| 07 | Chute , Carrying Idlers & brackets , return Idlers, Pulleys. | Corroded & damaged | Chute repaired by new painted plates, new carrying idlers & brackets , all pulleys lagging done. |
| 08 | Walk way | One side width – 1000mm & Other side – 500mm | Both side walk way – 1000mm each |
| 09 | Feature Maintenance | Difficult for maintenance | Very easy for maintenance. |

| Modified C6 Conveyor Project cost |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Sl. | Job Type | Description | Qty. Used | Rate | Total |
| 1 | Mechanical Jobs | Dismantling , Fabrication, erection of structures gratings & handrailing. | 01 | 554750.00 | 554750.00 |
| 2 |  | Installation of carrying iddler, Return Iddlers,Pulley, laying & jointing ofConveyor belt. | 01 | 127125.00 | 127125.00 |
| 3 |  | Fabrication & erection of conveyor hood & handrailing. | 01 | 100000.00 | 100000.00 |
| 4 |  | S.S Plate for C6 Conveyor Hood | 2000 | 276.00 | 552000.00 |
| 5 |  | Cost of Gratings | 96 | 8200.00 | 524800.00 |
| 6 |  | S.S Pipes for Hand railing | 200 | 675.00 | 135000.00 |
| 7 |  | Cost of used structural steel | 32.256 | 42500.00 | 1370888.50 |
| 8 |  | Cost of Belt | 110 | 1929.54 | 212249.40 |
| 9 |  | Cost of return Idler & carryingiddlers. | 1 set | 74000.00 | 74000.00 |
| 10 | Electrical Jobs | Backpulling & Relaying, Straight Through Jointing of Cables, Installation of G.I. trays, Installation of light posts & fixtures, Installation of conveyor safety equipments (Pullcords, ZSS, Hooters). | 01 | 374255.00 | 374255.00 |
| 11 | Civil Jobs | Construction of support foundations for two nos. of additional trestle of the conveyor | 01 | 719790.00 | 719790.00 |
| 12 | Misclaneous Jobs | Painting of structural steel & Erection of asbestos sheeting with wall painting. | 1 Lot | 400000.00 | 400000.00 |
| 13 |  | Misclaneous expenditure | lum sum | 100000.00 | 100000.00 |
| Total Project Cost : |  |  |  | रु 52,44,857.90 |  |

2. COAL HANDLING PLANT

IN HOUSE GRINDING JIB REPAIRING SECONDARY CR-1A

Secondary crusher -2

1.Damaged shaft of rotor repaired by building up through welding

2.Damaged sleeve replaced

3.Gap adjustment system made free.

4.Repairing of chutes.

Secondary crusher grinding gib & rotor

Rostas of secondary screen   overhauled

Hard-facing of grinding jib

done for better life

Nbc3 & 3a gear box & coupling oil check & fillings & chute repairing

Along with this following activities done during ATR-2015

1. Rubber lagging to the pulleys of conveyor NBC-6,NBC-2A,NBC-2

2. Secondary screen damaged panels replaced.

3. Repairing of damaged chutes.

4. Fire line extension in coal yard for extinguishes fire in Coal.

5. Damaged carrying idler replaced in conveyor NBC-6,NBC-2,NBC-2A,NBC-3A

6. All the gear boxes checked, cleaned the breather, top  up of  oil done

7. Repairing of feeding hopper at NBC-2A

3. BOILER-1  JOBS

1.Furnace cleaning

2.Bubble caps pinning, bed material charging in furnace.

3.Refractory work in furnace.

4.SS Shield fitted in evaporator coil bottom portion.

Furnace cleaning ,bubble caps pinning & bed material charging was carried out by M/S jyoti enterprises (WO no.-252004152403)

SS-304 shielding fitted in bottom portion of evaporator coil to avoid erosion. Job was carried out deptt.

Refractory applied in boiler-2 furnace at damaged portion in furnace wall. Refractory  job was carried out by M/S Western Corrosion controller(WP No.-252004142834).

Inspection of Boiler # 1 & 2  Pent House, Air preHeater, Primary Super Heater  & Convection bank area :-

Observations:-

- Ash leakage observed in Boiler # 1 & 2 Convection area( Goose neck).

- Ash deposit found in Boiler # 1& 2 Convection bank tube area.

- Ash deposit & leakages found in Boiler # 1 & 2 pent house  area.

- Ash deposit found in Boiler # 1 & 2 APH 1st pass and 2nd pass  area & some holes found choked in APH 1st pass & 2nd pass & also some tubes are eroded.

- Refractory found damage in Convection bank area & Pent House of Boiler # 2 .

- Leakage observed in Boiler # 1 & 2 Convection bank ash drain pipe ( 10 Inch) & Ash Hopper.

Action taken: -

- Ash Leakage arrested in Convection bank area by applying refractory in both Boiler.

- Ash deposit Cleaning done by air in Convection bank area of both Boiler.

- Boiler # 2 Pent house inside  ash cleaning done.

- Ash deposit cleaning done by water & holes de choking done in APH 1st & 2nd pass of both Boiler.

- Around 450 nos of Shielding fitted in Boiler # 2 APH 1st pass & 2nd Pass in eroded tubes.

- Boiler # 2 pent house inside leakages arrest by welding & applying refractory.

- Both Boiler Convection bank ash drain pipe ( 10 Inch) leakages arrested by bend replacement  & Ash Hopper leakages arrested by one side plate changed.

Dry Ice Cleaning done in  Pressure part tubes of  Boiler # OR/805 in below mention area.

- Convection Bank tubes.

- Primary Super heater tubes.

- Economiser  tubes & L-Bends.

- Inbed Evaporator  tubes.

- Wall tubes( LHS,RHS,Front & Rear).

- Riser  tubes.

Following area HR & normal  painting done  in Both Boiler during ATR-15.

- Both Boiler PA line Vertical piece with sliding gate valve(HR).

- Both Boiler Ash drain pipes(HR).

- Boiler # OR/805 all 05 nos windbox inside(HR) .

- All 04 nos safety valve silencer(HR).

- C-7 Conveyor Trolly ( Normal).

4. BOILER-2(OR-805) JOBS

FURNCE JOB

1. Furnace cleaning

2.Scaffolding prepration in furnace for manual pr.parts cleaning & dry ice blasting.

3.Application of phoscast-90 XR refractory in evaporator coil in furnace.

4.Bubble caps pinning, bed material charging in furnace.

5.Refractory work in furnace

Furnace cleaning was carried out by M/S jyoti enterprises (WO no.-252004152403)

Scaffolding prepared by M/S Unique constructions & engg. for two purpose.

a.Manual pr.parts cleaning

b.Dry ice blasting for pr.parts cleaning.

Bubble caps pinning & bed material charging was carried out by M/S Jyoti enterprises(WO No.-252004152403)

Refractory applied in boiler-2 furnace at damaged portion in furnace wall. Refractory  job was carried out by M/S Western Corrosion controller(WP No.-252004142834).

ATTEMPERATOR HEADER REPLACEMENT

Attemperator header was found sagged and tilted to the downward direction towards IBSH inlet .A spool piece of 600 mm was fitted in SH inter connecting vertical to make horizontal of attemperator header.Radiography & SR done of all four joints in attemperator header & spool piece.

Attemperator header replacement job was carried out by M/S Unique construction & engg.(WO no.-252004151041)

Attemperator header was in deformed condition(before replacement)

5.   Cleaning & Repair of Ash Silo & Vent Filter :

Cleaning of Ash Silo, Inspection of Vent filter Bags & Overhauling of Ash un-   loader # 2

Observations:

a) It was observed that during normal boiler operation heavy ash leakage was there due to leakages from bends at silo top, conveying line and bends near ash unloader area and leakage at reducer near ash vessel.

b) Choked vent filter bags had caused infiltration of air vent.

c) Due to continuous running of ash un-loader most of the rotary parts had worn out causing frequent breakdown of the un-loaders.

Action taken:

a) Damaged ash conveying bends at the top of ash silo and near ash unloader area and damaged portion of conveying line were replaced.

b) All 72 vent filter bags were taken out, and then inspection of all

filter bags done and found most of the bags are in damaged condition .then all the 72 vent filter bags get replaced .

c) All damaged parts of ash unloader-2, were replaced such as Drive sprocket, trunion wheels, lip seal, adjusting sprockets and its bearings.

d) Ash silo top cleaning was done.

Result:

Ash emission from the top of ash silo has reduced and ash un-loaders are working satisfactorily.

Photos  Related to SILO and ASH Unloader .

06. Boiler -2 ESP Inspection & corrective action.

Observations:

a) It was observed that the emitting shaft of first field was bent and its corresponding hammers & anvils get badly damaged. Also emitting and collecting field some hammers & anvils found in bad condition.

b) The drive mechanism of emitting, collecting fields are found in healthy condition.

Action taken:

a) Damaged emitting shaft and corresponding hammers and Anvils were replaced.

b) Also worn out  and damaged hammers and anvils get replaced for other  collecting and emitting fields.

PHOTOS Related to ESP-2

07. Duct inspection & corrective action.

Observations:

a) It was observed that ID Discharge Duct top is found in corroded and torn out condition. The top portion found in damaged condition.

b) The total ID discharge duct may be replaced in next possible opportunity.

c) Some ash also found deposited inside the ID discharge duct.

Action taken:

- Damaged  portion of the duct get repaired by providing 6mm of MS plate over it.

- The ash deposited inside the duct get removed and cleared.

- The duct inside is made free from debris and foreign material .

The photos of duct is as follows

08. Chimney Inspection & Cleaning.

Observations:

- It was observed that the ash deposition inside Chimney is very less.

- The deposited ash get cleaned and then chimney door get boxed up.

The photos inside the chimney is as follows

09. Replacement of  expansion bellow of ID Discharge Duct & chimney.

Observations:

It is observed that the expansion bellow of ID Discharge duct & chimney for both boilers are found badly damaged and corroded.

Action taken:

So both the expansion bellows get replaced with newer one.

PHOTOS Related to Expansion bellows are as follows.

10.  Overhauling of Main Steam Stop Valves & NRV of main steam line of Boiler # OR/805 & OR/806.

The various high pressure valves and safety valves overhauling and maintenance are carried out during ATR-15. The job was carried out by M/S EFCO Maschinebau India Private Limited under work order no 6600/252004152397 and 6600/252004141936.

The details are described as follows with some photographs.

| The following valves overhauling and maintenance are carried out during ATR-2015. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl. No. | Valve Name |  |  | Valve Size |  | Jobs Carried out |  | Spares consumed |  | Remarks |
| Boiler# 1 (OR-806) |  |  |  |  |  |  |  |  |  |  |
| 1 | Steam Drum Safety Valve (LHS) |  | 2.5''X6.0'' |  |  | Overhauling, Lapping, Blue matching & On line testing done |  | No |  | Set pr. 74 kg/cm². Nozzle seat is required to cut about 0.3 mm to 0.8 mm. |
| 2 | Steam Drum Safety Valve (RHS) |  | 2.5''X6.0'' |  |  | Overhauling, Lapping, Blue matching & On line testing done. The damaged parts are replaced with new spares. |  | 1. Disc insert 2. Thrust bearing adapter 3. Disc holder retainer 4. Spindle assembly 5. Guide ring 6. Nozzle ring 7. Disc holder 8. Guide |  | Set pr. 75 kg/cm². Nozzle seat is required to cut about 0.3 mm to 0.8 mm. |
| 3 | Main Steam Line (SH) Safety valve |  | 2.0''X4'' |  |  | Overhauling, Lapping, Blue matching & On line testing done. |  | 1. Thrust bearing adapter. 2. Guide ring 3.Spring washer top 4. Spring washer bottom 5. Spring 6. Guide |  | Set pr. 66.2 kg/cm². Nozzle seat is required to cut about 0.3 mm to 0.8 mm. |
| 4 | Start up vent isolation valve |  | 4'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 5 | Main Steam line NRV |  | 10'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring |  |  |
| 6 | MSSV (1500 class) |  | 10'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 7 | Feed isolation main valve |  | 6'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 8 | 100% CV inlet isolation valve |  | 6'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 9 | 100% CV outlet isolation valve |  | 6'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 10 | 30% CV inlet isolation valve |  | 4'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 11 | 30% CV outlet isolation valve |  | 4'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| Boiler# 2 (OR-805) |  |  |  |  |  |  |  |  |  |  |
| 12 | Steam Drum Safety Valve (LHS) |  | 2.5''X6.0'' |  |  | Overhauling, Lapping, Blue matching & On line testing done. |  | No |  | Set pr. 74 kg/cm². Nozzle seat is required to cut about 0.3 mm to 0.8 mm. |
| 13 | Steam Drum Safety Valve (RHS) |  | 2.5''X6.0'' |  |  | Overhauling, Lapping, Blue matching & On line testing done. |  | 1. Spring washer top 2. Spring washer bottom 3. Spring |  | Set pr. 75 kg/cm². Nozzle seat is required to cut about 0.3 mm to 0.8 mm. |
| 14 | Main Steam Line (SH) Safety valve |  | 2.0''X4'' |  |  | Overhauling, Lapping, Blue matching & On line testing done. |  | No |  | Set pr. 66.2 kg/cm². Nozzle seat is required to cut about 0.3 mm to 0.8 mm. |
| 15 | Main Steam line NRV |  | 10'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring |  |  |
| 16 | MSSV (900 class) |  | 10'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  | Spindle and brush nut found stuck up. The same made free. |
| 17 | Feed isolation main valve |  | 6'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 18 | 100% CV inlet isolation valve |  | 6'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 19 | 100% CV outlet isolation valve |  | 6'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 20 | 30% CV inlet isolation valve |  | 4'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 21 | 30% CV outlet isolation valve |  | 4'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 22 | CBD tank vent isolation valve |  | 6'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Gasket 2. Gland rope |  |  |
| Deaerator & PRDS Line |  |  |  |  |  |  |  |  |  |  |
| 23 | Steam isolation valve (Main) |  | 4'' |  |  | Overhauling, Lapping, Blue matching done. Spindle drilled and lock pin provided. |  | 1. Pr. Seal ring 2. Gland packing rings |  | Spindle was free and the valve was out of operation. Now the valve is operating smoothly. |
| 24 | Steam isolation valve (before 1st PCV) |  | 4'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 25 | Steam isolation valve (after 1st PCV) |  | 6'' |  |  | Overhauling, Lapping, Blue matching done. |  | 1. Pr. Seal ring 2. Gland packing rings |  |  |
| 26 | PRDS line 2nd PRV |  | 8''X10'' |  |  | Overhauling, Lapping, and test bench pr. Set & leak test done. |  | No |  | Set pr. 1.85 kg/cm² |
| 27 | Deaerator top PRV |  | 3''X4'' |  |  | Overhauling, Lapping, and test bench pr. Set & leak test done. |  | No |  | Set pr. 0.70 kg/cm² |
| Steam Blow Out valve |  |  |  |  |  |  |  |  |  |  |
| 28 |  | Steam isolation valve (900 class) Spare valve |  |  | 10'' |  | Overhauling, Lapping, Blue matching done. |  | 1. Thrust bearing one set 2. Pr. Seal ring 3. Gland packing rings |  |

Photographs of valve overhauling job during ATR-15.

Boiler-A drum safety valve LHS

Boiler-A drum safety valve RHS

Boiler-A drum safety valve RHS damaged nozzle ring

Boiler-A drum SV RHS new disc

Boiler-A drum SV RHS new spindle assembled

Boiler-A drum SV RHS damaged disc holder

Boiler-A SH SV

Boiler-A SH SV nozzle seat

Boiler-A MSSV lapping job under progress

Boiler-A MS line NRV

Boiler-A start up vent valve

Boiler-B drum SV LHS

Boiler-B drum SV RHS

Boiler-B SH SV

Boiler-B SH SV disc got scratches

Boiler-B MSSV

Boiler-B MSSV spindle

Boiler-B MS line NRV

Feed water isolation valves

Steam blow valve

Steam blow valve lapping under progress

Valve disc blue matching

11. Miscellaneous Maint. Jobs carried out During ATR –      15 in AFBC Boiler

1.450 NB swing type NRV / check valve replaced in deaerator along with  2 no new spiral wound gaskets of 150# and new bolts of size: M-30 X 150 – 32 Nos.

2. Five no of damaged bellows of ash drain lines in BOILER-2 cut and removed out. New bellows of size: 150NB (Qnty- 05 no) replaced with complete fit-up & welding.

3. New 4” water line (59 Mtrs length) fabricated and installed near ESP of boiler-2 as a common header drain line. The corroded old drain line cut and removed out.

4. The damaged bank ash drain line size: 12” – BLR-2 fabricated and replaced on the both side of BLR-2.

5. The damaged bank ash drain line (Size: 10” –BLR-1) fabricated & replaced on only one side (central work shop side) in BLR-1.

6. Some of the damaged PA-Lines of BLR-2 replaced with new SS-304 – 5” lines. Total quantity replaced = 9No x 1200mm = 10.800mtr, with new flanges.

7. Repairing and welding works carried out inside the wind boxes of BLR-2.

8. About 12 mtrs of SS-304 (6” size line) from air receiver tank top to ground level discharge control valve completely replaced. The old corroded MS-6” SIZE-line cut and removed out.

9.SS-304 (2” diameter) inlet line for A/C of control room modified & hooked up in 8” process water line .Initially it was connected with the 4” diameter fire water line of C-6 conveyor walk way.

10. Steam drum internals removed for inspection & refitted after IBR-inspection of the drum, with new champion style-54 gaskets (3mm thk) and molykote.

11. Economiser casing of BLR-2 removed for inspection & dry ice blasting / cleaning & thickness measurement works. The casing refitted after inspection with new asbestos ropes and new bolts M-16 X 80.

-------------- X X X ---------------

Jobs related to Deaerator Area

- Deaerator first PRDS control valve-50 PIC 003 has been changed with new complete set of valve and after erection, commissioning valve calibration has been done and stroke checked.

2.Deaerator second PRDS Control Valve – 50 PIC 005 pneumatic Actuator has been changed and after changing maintenance, calibration and stroke checking of valve has been done.

3.Deaerator water level control valve (50 LCV 001) has been changed with new complete set of valve and after changing, valve Calibration and stroke checking has been done.

4.PRDS outlet steam pressure Transmitter (50PT 003) loop testing and calibration has been done.

5.Maintenance, calibration and loop testing of Deaerator level transmitters (50 LT 001) have been done.

6.Deaerator level transmitter (50 LT 002) has been changed.

7. Maintenance, calibration and loop testing of all the flow transmitters (50 FT 002, 50 FT 001) have been done.

8. Maintenance, calibration and loop testing of all the Temperature transmitters (50 TT 004) have been done.

9. Deaerator level switch LSLL 020 and Temperature Thermocouple 50 TT 054 cable changed and rerouting has been done.

10. Damaged isolation valves of Deaerator level transmitters, pressure & Flow transmitters have been   replaced with new isolation valves.

11. Maintenance and calibration of Deaerator level switch (50 LSLL 020) has been done.

Jobs Related to BFW Area

1. BFW Pump A, B & C all suction and discharge pressure gauges calibration has

been done.

- BFW Pump A, B & C suction pressure transmitter calibration and loop testing has been done.

- Junction box maintenance and termination tightness has been done.

- BFW Pump tripping logic on Deaerator low levels with Level switch 50 LSLL 020 has been checked.

Jobs Related to New Air Compressor Area

1.Control panel maintenance and termination tightness has been done.

2. All pressure switches and gauges maintenance and calibration have been done.

- All Temperature switches maintenance has been done.

Jobs Related to ESP Area

- Overhauling and maintenance of all the ash intake power cylinders (50 XV 553A/B, 50 XV 554A/B, and 50 XV 555A/B) have been done.

- BLR – 1 & 2 Ash Hopper Level Sensors & switches (high & low) maintenance and calibration have been done.

- BLR -1 & 2 Ash handling system’s all Solenoid valves servicing and maintenance have been done.

- BLR – 1 & 2 Ash handling system’s all the pressure switches (high & low) maintenance and calibration have been done.

- BLR – 1 & 2 Ash handling system’s ash conveying valve maintenance have been done.

- Junction box maintenance and termination tightness have been done.

Jobs Related to Wind box Area

- Overhauling & maintenance of all wind box damper power cylinders (Tag Name- 50 HIC 416A/B, HIC 417A/B, HIC 418A/B, HIC 419A/B, HIC 420A/B) have been done and after stroke also checked.

- Junction box maintenance and termination tightness have been done.

Jobs Related to Furnace Area

- Inspection of all furnace thermo well & thermocouple has been done of both the Boiler.

- Inspection of furnace bed height all U – Tube have been done and 02 No of damaged U – Tube changed in BLR – 2’s 4th & 5th bed and 02 no of damaged U – Tube changed in BLR – 1’s 4th bed.

- BLR – 1 & 2 furnace bed height all U – Tubes have been flushed.

- BLR – 1 & 2 furnace bed height damaged Draft gauges have been changed.

- Calibration & loop testing of Furnace Pressure Transmitters (50PT 301A/B, 50PT 302A/B) has been done at both Boilers.

- Overhauling and maintenance of feed water control valve 50 FIC 106 A/B & 50 FIC 104 A/B has been done.

- BLR -1 & 2 Feed water transmitter 50 FT 106 A / B have been changed.

- Maintenance of PH, Conductivity transmitters (A/B) have been done.

- Overhauling and maintenance of OFA damper pneumatic power cylinder (A/B) have been done.

- Maintenance and calibration of O2 analyzer (A/B) have been done.

- Cleaning and maintenance of BMS local control panel has been done. Burner logic and test firing also done.

- Overhauling and maintenance of diesel control valves 50 FV 106 A/B and it ON – OFF valves, burner air damper pneumatic power cylinder have been done.

Jobs Related to Steam Drum Area

- BLR – 1 & 2 steams drum & line Pressure Gauges servicing & calibration have been done.

- BLR - 1 & 2 Drum Level Transmitters Calibration & Loop Testing have been done.

- BLR – 1 & 2 steam drum and line pressure transmitter calibration and loop testing have been done.

- Overhauling and maintenance of Attemperator control valve 50 TIC 205 A/B have been done and after calibration and stroke checking have been done.

- Damaged isolation valves of the Drum Pressure transmitters, Drum level transmitters, main steam pressure transmitters, main steam flow transmitters, feed water flow transmitters have been replaced with new isolation valves.

- Maintenance & loop testing of CBD Flow transmitter (50 FT 109 A/B) have been done.

- Maintenance of Hydra step (electrodes, local and remote display panels) has been done at both Boilers.

Jobs Related to Analyzers

- BLR 1 & 2 SPM Analyzers (50 SPM A, 50 SPM B) maintenance, alignment & calibration have been done.

- BLR 1 & 2 Flue Gas Analyzers (50 SOX A/B, 50 NOX A/B, 50 CO A/B) maintenance and calibration have been done.

- Calibration of Oxygen analyzers have been done of both the Boilers. The analyzers have been calibrated with known concentration of zero and span gases.

- All PH (50 AI 008, 50 AI 107A/B) & Conductivity analyzer (50 AI 009, 50 AI 207A/B) maintenance & calibration has been done.

Jobs Related to Fan Damper Pneumatic Actuators

- Boiler -1 & 2 FD fan Damper Actuators (Pneumatic Power Cylinders) Tag Name- 50 HIC 402A/B, 50 HIC 403A/B Overhauling, maintenance & stroke checking have been done.

- Boiler – 1 & 2 ID fan Damper Actuators (Pneumatic Power Cylinders) Tag Name- 50 HIC 301A/B, 50 HIC 302A/B Overhauling, maintenance and stroke checking have been done.

- Boiler -1 & 2 PA fan Damper Actuators (Pneumatic Power Cylinders) Tag Name- 50 HIC 408A/B, 50 HIC 409A/B Overhauling, maintenance & stroke checking have been done.

- A Draft gauges have been installed in BLR -1 & 2 FD Fan discharge duct to measure the Air flow capacity of Fan.

Jobs Related to Control Room Area

- Maintenance, Servicing & Testing of all DCS & PLC Cards with panels have been done.

- 01 No of faulty Analog IO (AMC 80) card has been replaced in FCS 0103.

- A faulty VLNet cable has been changed.

- Maintenance of all operating station with its consoles.

- Marshalling panel’s maintenance and termination tightness have been done.

- Maintenance of RTU panels (for transmitting of run feedback data of CHP screens and crushers to Boiler DCS) at Boiler has been done. Fault check of the systems also done.

- End Point Security system (Antivirus) has been installed in all HIS and Engg. Station.

Advantages of End Point Security System are:

- Since our network is secured, there is 0% breakdown & 100% availability in Network.so results in breakdown free Operation for operators.

- There is no time delay in any response /input given by operator.

- Good efficiency in operation results in minimizing down time of Equipment’s, results in less operational Cost & Maximizing Production.

- No Panic Situation caused in case of any emergency led by failure of HIS.

- The Downtime of the HIS will be very less comparatively when the HIS failure without any security.

- The Networked DCS system without ENDPOINT SECURITY have open communication and open access for everyone to use their Pen drive to collect plant datas or other confidential official datas. Whereas CS3000 Network with ENDPOINT SECURITY has a very Closed Communication & Full Locked Down so that no datas are stolen and very much secured.

- The use of Pen drives is a major source of Viruses, End Point Security will restrict the use of pen drives  & therefore our system will not get affected by viruses.

UPS Related Jobs -

      - Maintenance and testing of UPS have been done.

      - Maintenance and testing of Battery bank have been done.

Miscellaneous Jobs –

- All field junction box Maintenance and termination tightness have been done.

- Maintenance and calibration of Current Transducer have been done.

3. All field cables dressing have been done and damaged cable trays have been removed from field.

Jobs Related to CHP Area:

- Maintenance of RTU panels (for transmitting of run feedback data of CHP screens and crushers to Boiler DCS) at CHP has been done. Fault check of the systems also done.

- Cleaning and maintenance of all PLC panels, other PLC components and all the HMI stations has been done.

- Maintenance and checking of UPS and its battery have been done.

- A Communication card (CRA 930 00) has been changed with new cards and taken in line.

- Belt Weigher control panel and field load cell maintenance have been done.

EARTH PIT

- Old Earth Pit of DCS & UPS are replaced with two New Earth Pits.

| Annual Shutdown-2015 Maintenance Report for (Boiler & CHP) |  |
| --- | --- |
| Sl. | Job Description |
| C6 Conveyor Revamping Job : |  |
| 1 | Removal of power & control cables from C6 conveyor, |
| 2 | Cutting & Back pulling of power & control cables from C6 conveyor, |
| 3 | Removal of Junction Boxes, Lighting Fixtures, Pull Chord switch from C6 conveyor, |
| 4 | Dressing after back pulling of Cables in C5 conveyors before dismantling of conveyor structure, |
| 5 | Fixing of G.I. Cable tray on new C6 conveyor, |
| 6 | Fixing of G.I. Earth Strip on new C6 conveyor, |
| 7 | Fixing of G.I. Cable tray on new C5 transfer tower for cable rerouting, |
| 8 | Fixing & Painting of Pull Cord Supports on new C6 conveyor, |
| 9 | Relaying & Dressing of Power & Control Cables which were back pulled from C6 Conveyor, |
| 10 | Jointing of Power & Control cables at C6 conveyor, |
| 11 | Fixing of Lighting post, Lighting Fixtures, Junction boxes on C6 conveyor, |
| 12 | Fixing of gratings & extension of platform in C5 transfer tower, |
| 13 | Laying of cables between light posts, glanding, terminating & illuminating the fixtures, |
| 14 | Installation of a new pull cord panel at S/S for new scheme of pull cord protection, |
| 15 | Installation of a F.P. J.B. for new scheme of pull cord protection at C5 T.P., |
| 16 | Laying & termination of cables from S/S to the F.P. J.B. at C5 T.P., |
| 17 | Laying & termination of cables from F.P. J.B. at C5 T.P. to individual conveyor for pull cord, |
| 18 | Laying & termination of cables between pull cords, |
| 19 | Cable Laying, Glanding & termination of cables from new pull cord panel to C4, C5, C6, C7 feeders, |
| 20 | Testing of new pull cord scheme after installation of new pull cord panel, |
| 21 | Laying & termination of cables between light posts & illuminating the fixtures, |
| 22 | Laying & termination of cable for giving power supply to curtain for inauguration & Testing the same, |
| 23 | Laying & termination of cable from C6 feeder to a LCS for inauguration of C6 conv. & Testing the same, |
| 24 | Inauguration of C6 conveyor completed by Hon. Dir.(Tech.) on 15/04/15. |
| Other Maintenance Jobs: |  |
| 1 | Maintenance of 6.6KV Sec-A switchgears at Boiler, |
| 2 | Maintenance of all I/C & O/G feeders of Sec-A, |
| 3 | Maintenance of 6.6KV Sec-B switchgears at Boiler, |
| 4 | Maintenance of all I/C & O/G feeders of Sec-B, |
| 5 | Maintenance of Boiler PCC (Sec-A, B, C & D), |
| 6 | Maintenance of Boiler all Air Circuit Breakers of PCC (Sec-A, B, C & D), |
| 7 | Maintenance of Boiler MCC, |
| 8 | Maintenance of Boiler Emergency MCC, |
| 9 | Maintenance of HBL Make Battery Charger at New CHP, |
| 10 | Maintenance of Universal Make Boiler Battery Charger, |
| 11 | Maintenance of Boiler 1&2 ESP MCC & Controller Panel, |
| 12 | Maintenance of Boiler Damper Actuator Panel, |
| 13 | Maintenance of Boiler MLDB, |
| 14 | Maintenance of Boiler PLC panel, |
| 15 | Maintenance of all Rotork make actuators, |
| 16 | Maintenance of all AUMA make actuators, |
| 17 | Maintenance of Boiler-1 ESP all three fields, |
| 18 | Maintenance of Boiler-2 ESP all three fields, |
| 19 | Replacement/Repair/Installation of lighting fixtures at transformer yard, |
| 20 | Overhauling of 425KW BFW-2 motor , |
| 21 | Overhauling of 110KW PA Fan-1A motor, |
| 22 | Overhauling of 110KW PA Fan-2A motor, |
| 23 | Overhauling of 30KW Motor of C5 Conveyor, |
| 24 | Overhauling of 15KW Motor of C6 Conveyor, |
| 25 | Overhauling of 7.5KW motor of C7 conveyor, |
| 26 | Overhauling of 5.5KW motor of RBFD conveyor, |
| 27 | Cleaning & Painting of 4nos. 6.6KV/415V, 2MVA transformers at Boiler along with painting of support structure, Fencing & new asbestos sheeting, |
| 28 | Cleaning & Painting of 2nos. 6.6KV/415V, 2MVA transformers at CHP along with painting of support structure, |
| 29 | Control & protection checked for the above 6nos. Transformers, |
| 30 | Overhauling, contact resistance & timings tested by M/s SIEMENS service personnel for 6.6KV I/C-1, I/C-2, TR-1, TR-2 & a spare I/C feeders at CHP, |
| 31 | 7sj600 relay tested for 6.6KV I/C-1, I/C-2, TR-1, TR-2 & Sec. Crusher-1,1A,2,2A , PMCC I/C-1 & 2 and a spare crusher feeder by M/s Power System Consultant service personnel at CHP. |
| Annual Shutdown Maintenance completed for the year 2015 & Boiler-1 started on 13/04/2015 & Boiler-2 started on 16/04/18 |  |

ATR-2015

GENERAL ENGINEERING SECTION

Work carried out during Annual Shut Down 2015:

- Tappings in 6” steam line & 4” condensate line taken for Molten Sulphur Unloading System.

The steam line shall be used to supply steam to the steam coil, to be used to keep sulphur in molten state inside the unloading tank. The used up steam/ condensate shall be connected to the condensate line to avoid any wastage.

(Tapping in existing Condensate Line in Molten Sulphur Area)

(Tapping in existing Condensate Line in Molten Sulphur Area)

- Tapping in existing Fume Stack in PAP for connecting additional Fume extraction system in PAP

A Tapping was taken from existing Fume Stack in PAP by connecting a rectangular short piece with blind flange with the Stack. Both existing Stack and rectangular short piece are FRP constructed. The job was carried out by M/s Plastochem under WO no: 5515/252004150996 dated 23.09.2014. The total job was done in one day i.e. 06.04.2015 during Annual Shutdown.

(Tapping in existing FRP Stack)

- Replacement of  PRDS and  modification of  H.P./L.P steam pipe line  during ATR 2015

Previously there was integrated type of PRDS in SAP for letting down HP steam to LPS1 steam for use in sulphur melting area. The old system was having a chronic problem of steam line leakage and seizure of control valve stem randomly. System has been modified and replaced with new separate pressure control valve and de-superheating station. It also involved re-routing of BFW feed water pipe line, and L.P. steam pipeline for better flexibility to avoid steam leakage. All the material used, were IBR approved and has been properly inspected by Factory and boiler inspector. The same safety valve has been used after overhauling and re-calibration .

In addition to above all the corroded platform, ladder, structure and pipe supports have been replaced with new one with proper painting.

(Old integrated type PRDS system)

(Modified PRDS system with separate PCV, TCV with BFW & LP steam re-routed line)

(Modified ladder with new platforms and supports)

- Tappings taken in Phosphoric Acid Plant for New Evaporation Train

In order to integrate upcoming 8th Evaporation Train in Phosphoric Acid Plant, tappings  were taken by M/s Essar Projects during our annual shutdown.

(Tapping in existing Steam Line)

(Tapping in existing Cooling Water Line)

ATR-2015

Role of Civil Maintenance Department

In the Annual Maintenance Shutdown this year, various repair & maintenance activities, both major & minor in nature were carried out by the Civil Maintenance department across all the plants. A detailed description of all the major activities taken up and effectively completed within the stipulated time period is given below

Revamping of scrubber foundation of DAP-B for accommodating dust fan foundation placed on M/s Nirmal Kumar Swain.

The subject job included major modification in the existing foundation of the dust fan so as to accommodate a larger dust fan with higher operating capacity. The Civil work for the foundation was taken up after partly dismantling the old foundation. The new foundation was constructed monolithically with the old by means of chemical anchoring of reinforcement bars. The job was completed within the stipulated time frame as per contractual specifications.

Providing & Fixing Acid/Alkali proof bricks at various locations in plant during shut down placed on M/s Western Corrosion Controller.

Acid brick lining was damaged at Cell No. 2 & 3 in cooling tower of the Phosphoric Acid plant so it was decided to renew the brick lining and finishing it with Furane based mortar in desired locations, the job was executed during shutdown.  Similar repairs were also done at various locations in Sulphuric Acid Plant during ATR-2015.

Renovation of refractory brick lining in DAP trains B & C placed on M/s Western Corrosion Controller.

The combustion chambers at DAP Train-B&C required renovation of refractory and insulation brick work, it was taken up during the shutdown. Also, inside the duct of the chamber castable refractory brick work was repaired ,this required dismantling of the existing refractory, castable & insulation bricks and carting the debris from 4th floor of DAP.

The job was completed as per the specifications of the work order and in the prescribed time period.

Construction of additional support foundation pedestals for C6 Conveyor trestle.

C6 conveyor gallery in CHP had undergone considerable sagging; it was decided to erect additional supports for the newly fabricated gallery so as to enhance the reliability of the conveyor gallery structure under static & dynamic loads. The Civil work had to be carried out in utmost coordination with Mechanical & Electrical Maintenance sections. The structural supports were erected on newly casted RCC Pedestals (4 Nos.) which are supported on Pile foundation. A total of 8 piles of 500mm dia. were bored up to 15m depth to attain the desirable load bearing capacity. The job was completed well within the time frame and to the satisfaction of

The user department.

Apart from the aforesaid activities, there were several minor maintenance jobs that were carried out by the Civil Maintenance Department during shut down, most of them were completed to the satisfaction of the concerned department.

During shut down, the coordination among various departments to achieve a common goal of timely start up of the entire plant was remarkable. The repair, maintenance & revamping jobs carried out by the Civil Maintenance Department shall essentially enhance the efficiency of operations in the plant which shall also be reflected in the organization as a whole.

ATR-2015 BAGGING

MECHANICAL

| Slat No-1 | Lubrication of bearings done & coupling bolts replaced | 04 nos of Pin-bush replaced for FBC-3 Coupling & EP-2 grease 2 kg |  |
| --- | --- | --- | --- |
| Slat No-2 | one bearing (222211EK) found damaged |  |  |
| Slat No-3 | Lubrication of bearings done & 03 nos bearing found damaged & got replaced, Gearbox oil flushed | Bearing 22211 EK/C3 - 02 nos (non-drive end) , Bearing 22215 EK/C3- 01 no( drive end ) | Sleeve H311 - 02 nos , Sleeve H315 -01 no |
| Slat No-4 | Lubrication of bearings done & 03 nos bearing found damaged & got replaced, Gearbox oil flushed | Bearing 22215 EK/C3 - 02 nos (drive end) Bearing 22211 EK/C3 - 01 nos (non drive end) |  |
| Slat No-6 | Lubrication of bearings done & 01 nos bearing found damaged & got replaced, Gearbox oil flushed | Bearing 22211 EK/C3 - 01 nos (non-drive end) , | Sleeve H311 - 01 nos , |
|  | Non drive end bearings replaced | Bearings 22211 EK/C3….02no, Sleeve:H 311.....…………02no |  |
| Slat No-7 | Lubrication of bearings done & 01 nos bearing found damaged & got replaced, Gearbox oil flushed | Bearing 22211 EK/C3 - 01 nos (non-drive end) , | Sleeve H311 - 01 nos , |
| Slat No-9 | All bearings greased & gear box oil flushed. Two bearings replaced. | Bearing 22215 EK/C3- 02 no( drive end ) Sleeve H 315- 02 no |  |
|  | Non drive end bearings replaced | Bearings 22211 EK/C3….02no, Sleeve:H 311.....…………02no |  |
| Slat No-10 | All drive-end bearings greased & gear box oil flushed. No bearings found damaged |  |  |
|  | Non drive end bearings(01 no) replaced | Bearings 22211 EK/C3….01no, Sleeve:H 311.....…………01no |  |
| Slat No-11 | All drive-end bearings greased & gear box oil flushed. No bearings found damaged |  |  |
|  | Non drive end bearings replaced | Bearings 22211 EK/C3….02no, Sleeve:H 311.....…………02no |  |
| Slatno-13 | Non drive end bearings greasing done |  |  |
| Slat no-14 | Lubrication of bearings, one drive end bearing found damaged & got replaced & gearbox oil flushed. | Bearing 22215 EK/C3----01 no Sleeve-H315----01no |  |
|  | Non drive end bearings greasing done |  |  |
| 101 Conv | 04 nos of pulley lagging done by M/s Thejo Enggr.)Bend pulley bearing found damaged & got replaced | Bearing 22217 EK/C3 - 01 nos |  |
| 104 Conv | Motor & gearbox decoupled & removed from base frame as gearbox replacement jobs tob done1) Gear box & motor base frame welding done. 2) All bearings undergone greasing 3) One bearing found damaged & got, 4) Takeup bearings found damaged & got replaced | New BTN-200 gear box with new FGC-5 gear coupling & FBC-4 pin-bush Couplings Bearing 22224 EK/C3 - 01 nos (drive-end) Bearing 22220 EK/C3 - 02 nos (Take-up)) | Gearbox was running for last 15 years with noise |
| 107 Conv | Snub, bend pulley bearings (total 04 nos) greasing done, High speed couplings i.e. Fluid Coupling SDFC-320 decoupled, Skirt rubber fixation done at one side |  |  |
| 108 Conv | Snub, bend pulley bearings (total 04 nos) greasing done, High speed couplings i.e. Fluid Coupling SDFC-320 decoupled, Skirt rubber fixation done at one side |  |  |
| 111 Conv | Pulley lagging done by M/s THEJO Engg |  |  |
| 112 Conv | New take-up pulley replacement is under progress |  |  |
| 113 Conv | Counter weight lifted up for pulley lagging by M/s S.V.Industries |  |  |
| 117 Conv (Shuttle Conv) | Drive Pulleys & Snub Pulley bearings greasing done. |  |  |
| 130 Conv | High speed coupling i.e Fluid coupling SDFC-410 decoupled1) Old motor removed & new motor lifted up 2) Input flexible coupling fitted with new Motor(75 kW), 3) Runner Half Coupling fitted with Fluid Coupling & 4) Output Half Coupling Fitted with Gearbox HTN 300. | Input Flexible Coupling- 01 no, Out put half Coupling- 01no, Runner half coupling- 01 no | As per vibration reported by Inspn Deptt |
| 132 Conv | Belt replacement done by M/s S.V.Industries and Belt joint (Hot Vulcanization) sterted by M/s Thejo Engg | 300 Mtr length, 1400 mm width Nylon belt |  |
| 204 Conv | Drive pulley replacement jobs New support fabrication is under progress for lifting the pulley, motor & gearbox by M/s OMM Trader t | New HTN-200 gearbox with new FBC-4 Coupling(high speed side) & new FGC-8 Coupling(low speed side).Gear box Model:HTN 200- 01No, Gear Coupling FGC 8- 01 no, Pin-Bush coupling FBC 4- 01 no | As Drive pulley is to be modified for belt speed enhancement |
| Instrument Air Pipe Line replacement job | SS Pipe with fittings like valves, Elbows, nipples &Tees fabrication done. |  |  |
|  | i) slat no-2, slat no-3 , slat no-4, slat no-14 & slatno-7 new SS pipes(1/2'') hooked up & welding completed, ii) Main header Outlet pipe(2''NB) from Air Reciever tank connected to new SS pipe(2'' NB). | 1/2'' SS pipe, valves, tees, elbows & nipples | Old MS Pipe cut away & disconnected |
|  | New header SS line got closed at both ends, slat no-9, slat no-10 & slat no-11 new lines hooked up & welding completed. | 1/2'' SS pipe, valves, tees, elbows & nipples | Old MS line got severely corroded as a result leakage of line is prevailing most often by which BAGGING PROCESS is getting hampered |
|  | all slats ss air line hooked up , job completed. |  |  |
|  | Vibrators air line hook up job |  | Hopper vibrators air line are to be connected with new SS header air line. Air line job totally completed. |
| Portable Conv: NO 1 | lubrication done & gearbox oil flushed |  |  |
| Portable Conv: NO 2 | Non drive end bearings replaced, lubrication done & gearbox oil flushed | Bearings 22211 EK/C3….01no, Sleeve:H 311.....…………01no |  |
| Portable Conv: NO 3 | lubrication done & gearbox oil flushed |  |  |
|  | New belt mounted by deptt people | Nylon belt 650mm width & 17.0 Mtr length |  |
|  | Drive & non drive pulley & belt found damaged & removed. New Drive pulley fitted, New belt mounted. | 1)Nylon Belt 650mm width,Length:17.0 mm 2) Pulley dia;325mm, facewidth:700.0mm |  |
|  | Oil fushed & misc maint. done, Tail pulley replaced. | Pulley dia;325mm, facewidth:700.0mm |  |
| Portable Conv: NO 4 | Non drive end bearings replaced, lubrication done & gearbox oil flushed |  |  |
| Portable Conv: NO 8 | Non drive end greasing done |  |  |
| Portable Conv: NO 9 | Non drive end greasing done |  |  |
| Portable Conv: NO 10 | Non drive end greasing done |  |  |
| Portable conv -11 | Oil flushed & misc maint. done, New belt mounted & both Head & Tail pulley replaced. | Pulley dia;325mm, facewidth:700.0mm Pulley dia;250mm, facewidth:700.0mm Nylon Belt, 650.0mm width & length 17.0 Mtr. |  |
| Pulley Lagging | Pulley lagging for 107 conveyor (Bend pulleys & Snub Pulley) done by M/s THEJO ENGG |  |  |
|  | Pulley lagging for 108 conveyor (Bend pulleys & Snub Pulley) done by M/s THEJO ENGG |  |  |
|  | Pulley lagging for 108 conveyor & 107 conv Snub Pulleys done by M/s THEJO ENGG |  |  |
|  | Pulley lagging for snub & pressure pulleys of 130 Conv & Snub pulley of 204 conveyor done by M/s THEJO ENGG | Dia:327mm, Face width:1150mm |  |
|  | Pulley lagging for both the Bend pulleys of 130 conveyor done by M/s THEJO ENGG | Dia:400mm, Face width:1600mm…..02no |  |
|  | Pulley lagging of both bend pulleys done for 116 conveyor by M/s THEJO ENGG | Dia:327mm, Face width:1150mm |  |
| Vibrating Screen Mesh Replacement | Screen meshes replacement job for VIBRATING SCREEN-120 (02 nos meshes)& VIBRATING SCREEN-123 (04 nos meshes) job taken up |  | Total 04 nos of screen of 123 VIBRATING SCREEN have been replaced, job completed for 123 VIBRATING SCREEN |
|  | Screen meshes replacement job for both the screen(120 & 123) completed |  | Screen Mesh replacement Job Completed |
| 126 Divertor | Divertor motor freed, but Flap Gate getting jammed, rectification of gate is under progress |  |  |
|  | Flap Gate freed |  |  |
| Divertor No-302 | Divertor new shaft fitted with bearings & plummer block, welding job is yet to be done | EN-8 Shaft with length 1750.0mm |  |
|  | Electro-Mechanical linear Actuator fixing done & operated. | Bearings-22211EK/C3---02 no, Sleeve-H311-----------------02 no | Plummer block:SNA 511---- 02 nos used |